# GUIDE oN 
GRANTS AND PUBLIC PROCUREMENT 
UNDER PRE-ACCESSION INSTRUMENTS

Final version

MAY 2004

GUIDE oN  GRANTS AND PUBLIC PROCUREMENT  UNDER PRE-ACCESSION INSTRUMENTS	1

INTRODUCTION	3

CHAPTER 1.	THE OBJECTIVE AND APPLICABILITY	3

1.1	The Objective	3

1.2	Applicability	4

Chapter 2.	How to use the guide	4

GUIDELINES	6

Section  1.	Overview of basic principles	6

Section 2.	Procurement Planning And Tender Preparation	19

Section 3. 	Tender proceedings	32

Section 4.	Consultant Services Contracts	40

Section 5	Supply contracts	72

section 6.	Works contracts	98

Section 7.	 Grant Contracts	123

Section 8.	 Relations with international organisations and other donors	160

# INTRODUCTION

CHAPTER 1.	THE OBJECTIVE AND APPLICABILITY

1.1	The Objective

The European Commission’s Guide on the award of external aid contracts has proved to be a valuable instrument for the beneficiaries of Community funding, in particular in the acceding and candidate countries. From the date of their accession, however, the new Member States will apply national procurement procedures which comply with the Acquis Communautaire. With this in mind, the Commission called for an analysis of the Practical Guide in comparison with the European Community Directives on the award of public contracts (the Directives). This was undertaken in 2003 and concluded that the Practical Guide contained a number of inconsistencies and incompatibilities with the Directives.

Following this comparative analysis, the Services of the Commission decided to prepare a new guide compatible with the Directives, but also covering contracts under the thresholds, in order to assist candidate countries and in some cases new Member States to use the same methodology and documentation as under the previous Practical Guide and to promote the use of good practice.

The new document entitled “Guide on Grants and Public Procurement under pre accession instruments” lays down operational guidelines to be applied by beneficiaries of pre accession assistance.

1. A beneficiary in a non-member State which lets a procurement contract subject to Community financing under pre-accession instruments is required to use the procedures set out in this document, including the Annexes. 1. This document is recommended to New Member States still benefiting from pre accession instruments under the system of ex ante control.

This guide is not designed for use by contracting entities in the energy, water, transport or telecommunications sectors for which a separate directive applies.

1.2	Applicability

This new guide is designed to provide guidance for use at the contracting authority level. It covers the whole procurement process, from the planning stage until performance of the contract has been completed and further supplies, services or works may be required. The main legal background for the guide is for candidate countries a combination of the conditions for Community funding and national public procurement legislation implementing the European Directives on public procurement (the Directives), and for new Member States still benefiting from pre accession instruments under the system of ex ante control their national legislation adopted in the field of public procurement, in particular to implement the Community directives. In these last circumstances it should be noted that the guide has no binding effect and is just an operational tool to be used in conformity with the existing national provisions.

The guide should be used in the following circumstances:

For non-Member States (mandatory)

As stipulated by the Financing Agreement established between the Beneficiary and the European Commission, it is mandatory to use the guide in connection with the implementation of projects and programmes financed by pre-accession instruments under the ex-ante or ex— post control procedures laid down therein.

Non-member countries are also encouraged to use the guide, following national adaptation as necessary, for public procurement financed from sources other than funds provided by the Community, such as the state budget.

For some Member States (as a recommendation)

Subject to national laws and regulations, this document is recommended to New Member States still benefiting from pre accession instruments under the system of ex ante control.

For these tenders, Phare eligibility rules remain applicable but procurement is open to Third Countries which have signed bi or multilateral agreements with the EC under the conditions of these agreements (mainly Government Procurement Agreement of the World Trade Organisation ).

Chapter 2.	How to use the guide

As described in Chapter 1 above, the guide is intended to serve two purposes, namely as a mandatory instrument for those third countries where procurement contracts are let subject to Community financing under pre-accession instruments, and, secondly, as a voluntary, but strongly recommended, instrument for some new Member States to use in the context of remaining pre accession financing.

This guide is intended to provide professional guidance to purchasers, technicians and other staff within contracting authorities in their tasks of organising and conducting procurement operations efficiently and in accordance with procurement laws and regulations.

The rules and procedures of the Practical Guide have been revised in the relevant parts in order to ensure compatibility with the EC Directives on public procurement. They comprise:

Section 1. Overview of basic principles

Section 2. Procurement planning and tender preparation

Section 3. Tender proceedings

Section 4. Service Contracts

Section 5. Supply Contracts

Section 6. Works Contracts

Section 7. Grants Contracts

Section 8 Relations with international organisations and other donors

Annexes

The Annexes provide a full set of standard documents for mandatory use by non-member States and for recommended use by Member States subject to national adaptation in different stages of the procurement process. The use of these documents, based on the standard documents of the Practical Guide, has been shown to improve the quality of the procurement work within the contracting authorities. Significant standard documents cover the tender dossier, tender evaluation report format and a number of international contract models.

# GUIDELINES

Section  1.	Overview of basic principles

This Guide explains the contracting procedures which apply to EC external aid contracts financed under PHARE and ISPA. It provides the procedures to be used in decentralised systems with ex-ante approval by the European Commission (Decentralised Implementation System).

It mainly differs from the existing “Practical Guide to contract procedures financed from the EC general budget in the context of external actions” generally used by the services of the Commission in the context of external relations in its compliance with the EC directives on procurement presently applied in May 2004.

The Guide does not cover contracts awarded by the Commission on its own account. These come under Title V, Chapters 1 and 2, of the Financial Regulation and Commission services should use in-house contract procedures and models to deal with them.

It does not cover also contracts awarded by contracting entities in the energy, water, transport or telecommunications sectors for which a separate directive applies .

## 1.1 Decentralised Implementation System

There are three possible approaches to managing the procedures for projects financed under the external aid programmes of the EC:

- Centralised: the European Commission is the Contracting Authority and takes decisions for and on behalf of the beneficiary country. In this case, actions to be performed by the Contracting Authority throughout this Guide should be interpreted as being carried out by the European Commission, acting for and on behalf of the beneficiary country.

- Decentralised:

- Ex-ante:	decisions concerning the procurement and award of contracts are taken by the Contracting Authority and referred for approval to the European Commission. Details are specified throughout this Guide

- Ex-post:	decisions foreseen in the Financing Memorandum are taken by the Contracting Authority without prior reference to the European Commission.

The implication of the Commission for the decentralised contracts consists simply on its authorisation to the financing of the contracts. In case of non-respect of the procedures established in the present Guide, the expenditure related to the operations involved are ineligible in terms of Community financing.

The interventions of the Commissions’ representatives within the decentralised procedures for the conclusion or implementation of the contracts financed in the context of external actions are only to see whether or not the conditions for the Community financing are met. They will not, in any case, have as an objective nor as a possible effect, the attempt against the principle by which the decentralised contracts become national contracts that are only prepared, elaborated and concluded by the decentralised Contracting Authority. The tenders and candidates for these contracts cannot be considered as beneficiaries of the acts carried out by the Commissions’ representatives for the implementation and conclusion of the contracts.  They must only hold a legal bound with the decentralised Contracting Authority and the Commissions’ representatives acts may not cause the substitution of a Contracting Authority’s decision by a decision taken by the Community.

In all cases, the Contracting Authority assumes full responsibility for its actions and will be accountable for these in any subsequent audit or other investigation.

This guide includes the procedures to be observed in the case of Decentralised Implementation System that corresponds to the ex ante approval situation described above. There are strict rules governing the way in which contracts are awarded. These help to ensure that suitably qualified contractors are chosen without bias and that the best value for money is obtained, with the full transparency appropriate to the use of public funds. They are guaranteed by the implication of the services of the Commission in each major step of the procedures for ex ante approval.

## 1.2	Record Keeping and controls

All projects funded by the European Communities are subject to audit at any stage, whether during the award process, during execution of the project or once the project has been completed.

The Contracting Authorities must keep all the documents relating to the award of contracts for a period of seven years from payment of the balance. These documents must be made available for inspection by the European Commission and the European Court of Auditors. These must include the originals of all tenders submitted, together with the corresponding tender dossiers and any related correspondence.

## 1.3	Rules of nationality and origin

### 1.3.1 Principle

Participation in tendering procedures is open on equal terms to all persons coming within the scope of the Community Treaties and, in accordance with the specific provisions in the basic instruments governing the cooperation sector concerned, to all such natural and legal persons who are nationals of the beneficiary third countries or of any other third country as are expressly mentioned in those instruments. See Annex A2 for the list of countries for each aid programme or instrument.

The relevant regulations for the application of this Guide are Phare and Ispa. Note that as from the first of May 2004, Estonia, Hungary, Latvia, Lithuania, Poland, Czech Republic, Slovakia and Slovenia became Member States and should not be considered anymore more as Beneficiary countries under Phare and Ispa. Malta and Cyprus were covered by a separate regulation (Council Regulation (EC) No 555/2000 of 13 March 2000 (as amended by Council Regulation (EC) No 2500/2001 of 17 December 2001) and became Member States as well.

In duly substantiated exceptional cases, it may be decided, on the basis of the specific conditions laid down in the basic acts governing cooperation, to allow third-country nationals other than those referred to in the previous paragraph to tender for contracts. Where an agreement on widening the market for procurement of goods or services to which the Community is party applies, the contracts for procurement financed by the budget are also open to third-country nationals other than those referred to in the previous two paragraphs, under the conditions laid down in this agreement.

This nationality rule also applies to the experts proposed by service providers taking part in tender procedures for service contracts financed by the European Community. For the purposes of verifying compliance with the nationality rule, the tender dossier requires tenderers to state the country of which they are nationals by presenting the documents usual under that country's law.

If the Contracting Authority suspects that a candidate/tenderer has only a registered office in an eligible country or state and that the nationality of the candidate/tenderer is ineligible, the candidate/tenderer is responsible for demonstrating effective and continuous links with that country's economy. This is to avoid awarding contracts to firms whose nationalities are ineligible but which have set up 'letter box' companies in an eligible country to circumvent the rules on nationality.

Rule of origin: All supplies and equipment purchased under a supply contract must originate in the EU or in an eligible country, as defined in the nationality rule above. The same goes for supplies and equipment purchased by a contractor for works or service contracts if the supplies and equipment are destined to become the property of the beneficiary country once the contract is completed.

In its tender, a tenderer must state the origin of supplies. Contractors must present a certificate of origin to the Contracting Authority when bringing supplies into the beneficiary country, when provisional acceptance of the supplies takes place or when the first invoice is presented. The contract will specify which of these options is applicable.

Certificates of origin must be made out by the competent authorities of the supplies' or supplier's country of origin and comply with the international agreements to which that country is a signatory.

It is up to the Contracting Authority to check that there is a certificate of origin. Where there are serious doubts about origin, it will be up to the European Commission's services in Brussels to decide on the course of action.

### 1.3.2.	Exception to the rule on nationality and origin

Exceptions to the rule on nationality and origin may be made in some cases. The award of such a derogation is decided on a case-by-case basis by the Commission before the procedure is launched.

(a)	With regard to nationality, the European Commission may exceptionally allow nationals of countries other than those stipulated in the applicable Regulation to participate in tenders and contracts, on a case-by-case basis.

(b)	With regard to the origin of supplies, the same exception applies as under (a). Note, however, that the frequently used argument that a product of ineligible origin is cheaper than the Community or local product does not constitute grounds for awarding a derogation.

If the award of contract is preceded by a tender procedure, the derogation must be in mentioned in the procurement notice.

## 1.4	Thresholds

1.4.1	The thresholds of the directives are in the main aligned with those in the GPA so that EU economic operators are treated no less favourably under the Directives than GPA economic operators under the GPA. There are slightly higher thresholds for contracting authorities such as local authorities and bodies governed by public law and there are much higher thresholds for supplies and services contracts in the utilities sectors. The GPA thresholds are expressed in SDR (Standard Drawing Rights). The Commission calculates the Euro or national equivalents, in principle every other year, by reference to the exchange rates over the 12 months to the previous August. The results are published in OJEU and made available on the SIMAP web-site (www.simap.eu.int). They apply to values net of value added tax.

1.4.2	The thresholds at 1 January 2004 are:

| Contracting Authority | Supplies Dir.93/36 | Services Dir.92/50 | Works Dir.93/37 |
| --- | --- | --- | --- |
| Central government bodies listed in Annex 1 of the GPA & their successors | €154 014* (SDR130 000) | €154 014** (SDR130 000) | €5 923 624 (SDR5 000 000) |
| Other, mainly regional and local authorities and bodies governed by public law | €236 945 (SDR200,000) | €236 945 (SDR200 000) | €5 923 624 (SDR5 000 000) |
| Contracts subsidised for the most part by contracting authorities |  | €200 000*** | €5 000 000 |
| Indicative notices Small lots | €750 000 | €750 000 €80 000 | €5 000 000 €1 000 000 |
| * | For defence authorities: only for products listed in the GPA, otherwise €200 000. |
| ** | Except Part B services, research and development services and certain telecoms services (CPC 7524, 7525, 7526): all €200 000. |
| *** | Services and works related to civil engineering projects or building work for hospitals, facilities for sports, recreation and leisure, school and university buildings or buildings for administrative purposes. |

## 1.5	Publication of Notices

1.5.1	Where the Directives apply, the dispatch of notices to the OJEU is mandatory. The dispatch of a full prior indicative notice (PINs) gives the possibility to the contracting authority to take advantage of the reductions in minimum time limits for responses or tenders. A full PIN is one containing as much as is available of the information needed for a contract notice. It must have been dispatched to the OJEU not less than 52 days, and not more than a year, before dispatch of the contract notice. It is assumed that notices will be published within 12 days, 5 days in cases of urgency, except that contracting authorities are required to state whether award notices for Part B services are to be published.

1.5.2	PINs are intended to give advance warning of procurement intentions for:

supplies, where the total estimated value in the coming 12 months in a product area is €750 000 or more;

services, where the total estimated value in the coming 12 months in one of the Part A categories is €750 000 or more;

works where the estimated value of a contract exceeds the normal threshold.

For supplies and services, PINs and notices of buyer profiles are to be dispatched as soon as possible after the beginning of the contracting authority’s budgetary year. For works the relevant time is as soon as possible after the planning decision to proceed

1.5.3	The form of notices for dispatch to the OJEU has been mandatory since 1 May 2002.

1.5.4	There is provision for notices to be dispatched to the OJEU in Luxembourg in hard copy by post, by fax or preferably by electronic means directly, through SIMAP or through an accredited data entry point with XML facilities. Notices which are transmitted by electronic means or in cases of urgency under the accelerated procedure, will be published within five days of dispatch. Otherwise notices will be published within 12 days.

It may be a condition of funding or receipt in other languages that notices must be dispatched electronically and at an earlier date. Notices not dispatched electronically in accordance with the format and modalities laid down under the Consolidated Directive will be limited to 650 words.

1.5.5	Contract notices are published in the official language chosen by the contracting authority. A summary is published in the other Community languages. Contract notices for accelerated procedures in cases of urgency must be sent electronically or by fax.

1.5.6	Contract award notices have to be dispatched to the OJEU no later than 48 days after the award of the contract. As indicated above, award notices for Part B services must indicate whether they are intended for publication. Contract award notices are not required for individual contracts under a framework agreement, just for the framework agreement itself. Contract award notices for contracts awarded under a dynamic purchasing system can be grouped on a quarterly basis for dispatch within 48 days of the end of the quarter.

1.5.7	The Directives provide that notices are to include the information required by the standard forms but that information on the award of contracts or framework agreements may be withheld from publication where its release would impede law enforcement or otherwise be contrary to the public interest, would harm the legitimate commercial interests of public or private economic operators, or might prejudice fair competition between them. They also provide that notices and their contents may not be published at the national level prior to their dispatch to the OJEU, that notices at the national level shall not include information other than that in the notices dispatched to the OJEU but that notices at the national level must include a reference to the date of dispatch to the OJEU. Contracting authorities are also required to retain proof of dispatch of notices to the OJEU. The proof may consist of an acknowledgment from the OJ Office.

## 1.6	Time limits

1.6.1	The Directives set out the minimum time limits that may be allowed for responses to notices, invitations and requests for information, depending on the award procedure. The minima are subject to an over-riding requirement for sufficient time to take account of matters such as the complexity of the contract, the time needed to prepare a tender, the possible need for site visits and the bulkiness of the documentation. The Directives do, however, provide for time limits to be reduced where a full and current PIN has been published.

### 1.6.1.1	Open Procedure

Tenders: must allow at least 52* days from dispatch of contract notice, which may be reduced to 36 days in general, or at least 22 days, following a full PIN.

Contract documents: must be provided within 6 days of a timely request.

Additional information: must be provided not later than 6 days before the deadline for tenders.

### 1.6.1.2	Restricted procedure  and negotiated procedure with publication

Accelerated procedure: There is provision for the restricted and negotiated procedures to be accelerated where urgency renders the normal time limits impracticable.

Requests to participate: must allow at least 37 days from dispatch of the contract notice (15 if accelerated).

Contract documents: to be made available with invitations to tender or participate, on-line or without delay via a third party.

Additional information: to be provided no later than 6 days before the deadline for tenders (4 if accelerated).

Restricted procedure tenders: must allow at least 40 days from invitation to tender (10 if accelerated), which may be reduced to 36 days in general or at least 22 days following a full and current PIN.

## 1.7	Grounds for exclusion

Candidates or tenderers will be excluded from participation in a procurement procedure if:

(a) they are bankrupt or being wound up, are having their affairs administered by the courts, have entered into an arrangement with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations;

(b) they have been convicted of an offence concerning their professional conduct by a judgment which has the force of res judicata;

(c) they have been guilty of grave professional misconduct proven by any means which the Contracting Authority can justify;

(d) they have not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those of the country of the Contracting Authority or those of the country where the contract is to be performed;

(e) has not fulfilled obligations relating to the payment of taxes in accordance with the legal provisions of the country in which they are established or those of the contracting authority

(f) they have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the Communities' financial interests;

(g) following another procurement procedure or grant award procedure financed by the Community budget, they have been declared to be in serious breach of contract for failure to comply with their contractual obligations.

(h) are guilty of serious misrepresentation in supplying the information required by the Contracting Authority as a condition of participation in the contract procedure or fail to supply this information.

The Contracting Authority will accept, as satisfactory evidence that the candidate or tenderer is not in one of the situations described in (a), (b) or (e), production of a recent extract from the judicial record or, failing that, a recent equivalent document issued by a judicial or administrative authority in the country of origin or provenance showing that those requirements are satisfied. The Contracting Authority will accept, as satisfactory evidence that the candidate or tenderer is not in the situation described in (d), a recent certificate issued by the competent authority of the Member State concerned. Where no such certificate is issued in the country concerned, it may be replaced by a sworn or, failing that, a solemn statement made by the interested party before a judicial or administrative authority, a notary or a qualified professional body in its country of origin or provenance. Depending on the national legislation of the country in which the tenderer or candidate is established, the above documents relate to legal persons and/or natural persons including, where considered necessary by the Contracting Authority, company directors or any person with powers of representation, decision-making or control in relation to the candidate or tenderer.

Candidates must supply the proof usual under the law of the country in which they are established that they do not fall into the categories listed above

## 1.8	Administrative and financial penalties

Without prejudice to the application of penalties laid down in the contract, candidates or tenderers and contractors who have been guilty of making false declarations or have been found to have seriously failed to meet their contractual obligations in an earlier procurement procedure will be excluded from the award of all contracts and grants financed by the Community budget for a maximum of two years from the time when the infringement is established, as confirmed after an adversarial procedure with the contractor. That period may be extended to three years in the event of a repeat offence within five years of the first infringement.

Tenderers or candidates who have been guilty of making false declarations will also receive financial penalties representing 2% to 10% of the total value of the contract being awarded. Contractors who have been found to have seriously failed to meet their contractual obligations will receive financial penalties representing 2% to 10% of the total value of the contract in question. That rate may be increased to 4% to 20% in the event of a repeat offence within five years of the first infringement.

In the cases referred to in Article 93(1)(a), (c), (d) and (f) of the Financial Regulation, the candidates or tenderers will be excluded from the award of all contracts and grants for a maximum of two years from the time when the infringement is established, as confirmed after an adversarial procedure with the contractor.

In the cases referred to in Article 93(1)(b) and (e) of the Financial Regulation, the candidates or tenderers will be excluded from the award of all contracts and grants for a minimum of one year and a maximum of four years from the date of notification of the judgment.

Those periods may be extended to five years in the event of a repeat offence within five years of the first infringement or the first judgment.

The cases referred to in Article 93(1)(e) of the Financial Regulation are the following:

(a)	cases of fraud as referred to in Article 1 of the Convention on the protection of the European Communities' financial interests drawn up by the Council Act of 26 July 1995;

(b)	cases of corruption as referred to in Article 3 of the Convention on the fight against corruption involving officials of the European Communities or officials of Member States of the European Union, drawn up by the Council Act of 26 May 1997;

(c)	cases of participation in a criminal organisation, as defined in Article 2(1) of Joint Action 98/733/JHA of the Council;

(d)	cases of money laundering as defined in Article 1 of Council Directive 91/308/EEC.

Where the award procedure or performance of the contract is vitiated by substantial errors or irregularities or by fraud, the Commission will suspend performance of the contract. Where such errors, irregularities or fraud are attributable to the contractor, the Commission may in addition refuse to make payments or may recover amounts already paid, in proportion to the seriousness of the errors, irregularities or fraud.

The purpose of suspending the contract is to verify whether presumed substantial errors and irregularities or fraud have actually occurred. If they are not confirmed, performance of the contract will resume as soon as possible. A substantial error or irregularity is any infringement of a provision of a contract or regulation resulting from an act or an omission which causes or might cause a loss to the Community budget.

## 1.9	Visibility

Unless otherwise requested or agreed by the European Commission, contractors for services, supplies or works must take the necessary measures to ensure the visibility of the EU financing or co-financing. Such measures must be in accordance with the applicable rules on the visibility of external action laid down and published by the Commission.

## 1.10 Time limits for tendering and contracting

### 1.10.1	Tender with ”suspension clause”

Before initiating any tender procedure, the service, supply or works to be contracted must have been approved in a Financing Memorandum and the funds must be available, except in the case of procedures with “suspension clause”. In exceptional and duly justified cases, tender procedures may be published with a suspension clause.  This means that a tender procedure is launched before a financing decision is issued or a financing memorandum is signed between the European Commission and the beneficiary country. The award of that contract is therefore subject to the conclusion of the financing agreement and the provision of funding. Because of its implications, the existence of a suspension clause must be explicitly mentioned in the procurement notice. The tender procedure will invariably be annulled if the European Commission's decision-making procedure is not completed or the financing agreement is not signed.

### 1.10.2	Prohibition of retroactive awards

Contracts are considered to take effect from the date of signature of the last signatory. Contracts or contract addenda cannot be awarded retroactively under any circumstances. This means that no disbursements can be effected and no goods and services provided prior to the signature of the contract and/or addendum. All contracts must show the true dates of signature of the contracting parties.

## 1.11	Cancellation of award procedures

The Contracting Authority may, before the contract is signed, either abandon the procurement or cancel the award procedure without the candidates or tenderers being entitled to claim any compensation. If a contract award procedure is cancelled, all tenderers must be notified in writing and as soon as possible of the reasons for the cancellation.

Cancellation may occur where:

- the tender procedure has been unsuccessful, i.e., no qualitatively or financially worthwhile tender has been received or there is no response at all;

- the economic or technical data of the project have been fundamentally altered;

- exceptional circumstances or force majeure render normal performance of the contract impossible;

- all technically compliant tenders exceed the financial resources available;

- there have been irregularities in the procedure, in particular where these have prevented fair competition.

|  | ( | If a contract award procedure is cancelled, all tenderers must be notified in writing and as soon as possible of the reasons for the cancellation. |
| --- | --- | --- |

After cancelling a tender procedure, the Contracting Authority may decide:

- to open negotiations in the absence of tenders or suitable tenders under an open or restricted procedure, provided the terms of the contract are not substantially altered and on condition that a report is sent to the Commission if requested;

- not to award the contract;

- to launch a new tender procedure: either an open or a restricted procedure, or a negotiated with a call for competition in the event of cancellation justified by irregular or unacceptable tenders under an open or restricted procedure, provided the terms of the contract are not substantially altered and following a further contract notice unless all the compliant tenderers in the original procedure are included.

Whatever the case, the final decision is taken by the Contracting Authority with the prior agreement of the European Commission. In no event will the Contracting Authority be liable for any damages whatsoever including, without limitation, damages for loss of profits, in any way connected with the cancellation of a tender even if the Contracting Authority has been advised of the possibility of damages. The publication of a procurement notice does not commit the Contracting Authority to implement the programme or project announced.

## 1.12	Ethics clauses

Any attempt by a candidate or tenderer to obtain confidential information, enter into unlawful agreements with competitors or influence the committee or the Contracting Authority during the process of examining, clarifying, evaluating and comparing tenders will lead to the rejection of its candidacy or tender.

Without the Contracting Authority's prior written authorisation, a contractor and its staff or any other company with which the contractor is associated or linked may not, even on an ancillary or subcontracting basis, supply other services, carry out works or supply equipment for the project.

This prohibition also applies to any other programmes or projects that could, owing to the nature of the contract, give rise to a conflict of interest on the part of the contractor.

When putting forward a candidacy or tender, the candidate or tenderer must declare any potential conflict of interest, and any link with other  tenderers or parties involved in the project. Should such a situation arise during performance of the contract, the contractor must immediately inform the Contracting Authority.

|  | ( | Civil servants or other officials of the public administration of the beneficiary country, regardless of their administrative situation, must not be engaged as experts by tenderers. |
| --- | --- | --- |

The contractor must at all times act impartially and as a faithful adviser in accordance with the code of conduct of its profession. It must refrain from making public statements about the project or services without the Contracting Authority's prior approval. It may not commit the Contracting Authority in any way without its prior written consent.

For the duration of the contract, the contractor and its staff must respect human rights and undertake not to offend the political, cultural and religious mores of the beneficiary state.

The contractor may accept no payment connected with the contract other than that provided for therein. The contractor and its staff must not exercise any activity or receive any advantage inconsistent with their obligations to the Contracting Authority.

The contractor and its staff are bound to maintain professional secrecy for the entire duration of the contract and after its completion. All reports and documents drawn up or received by the contractor during the performance of the contract are confidential.

The contract governs the contracting parties' use of all reports and documents drawn up, received or presented by them during the performance of the contract.

The contractor must refrain from any relationship likely to compromise its independence or that of its staff. If the contractor ceases to be independent, the Contracting Authority may, regardless of injury, terminate the contract without further notice and without the contractor having any claim to compensation.

The Commission reserves the right to suspend or cancel project financing if corrupt practices of any kind are discovered at any stage of the award process and if the Contracting Authority fails to take all appropriate measures to remedy the situation. For the purposes of this provision, "corrupt practices" are the offer of a bribe, gift, gratuity or commission to any person as an inducement or reward for performing or refraining from any act relating to the award of a contract or implementation of a contract already concluded with the Contracting Authority.

More specifically, all tender dossiers and contracts for works, supplies and services must include a clause stipulating that tenders will be rejected or contracts terminated if it emerges that the award or execution of a contract has given rise to unusual commercial expenses.

Such unusual commercial expenses are commissions not mentioned in the main contract or not stemming from a properly concluded contract referring to the main contract, commissions not paid in return for any actual and legitimate service, commissions remitted to a tax haven, commissions paid to a recipient who is not clearly identified or commissions paid to a company which has every appearance of being a front company.

The contractor undertakes to supply the Commission on request with all supporting documents relating to the conditions of the contract's execution. The Commission may carry out whatever documentary or on-the-spot checks it deems necessary to find evidence in cases of suspected unusual commercial expenses.

|  | ( | It is the obligation of the Contracting Authority to ensure that the contract award procedure is concluded in a transparent manner, based on objective criteria and disregarding any possible external influences. |
| --- | --- | --- |

## 1.13	Appeals

Notwithstanding the national remedies system, tenderers believing that they have been harmed by an error or irregularity during the award process may petition the Contracting Authority directly. The Contracting Authority must reply within 90 days of receipt of the complaint.

Where informed of such a complaint, the European Commission must communicate its opinion to the Contracting Authority and do all it can to facilitate an amicable solution between the complainant (tenderer) and the Contracting Authority.

If the above procedure fails, the tenderer may have recourse to procedures established under the beneficiary country's national legislation.

|  | ( | Should a Contracting Authority fail to adhere to the contract award procedures provided for in this Guide, the European Commission reserves the right to refuse to finance the contract or to suspend, withhold or recover funding for the contracts concerned. |
| --- | --- | --- |

Section 2.	Procurement Planning And Tender Preparation

## 2.1	Introduction

This section describes a generic approach to procurement planning and tender preparation. Some of the early steps in the process described in this section have to be taken before it becomes clear whether this guide applies. For this reason, the recommendations made in this section are intended to reflect good public procurement practice at large.

The outcome is likely to correspond better to actual needs, both current and future, and to minimise whole-life costs — the costs of acquisition and use of goods and services, or the costs of construction, operation and maintenance of facilities, as well as the costs of disposal, decommissioning and deconstruction at the end of the life cycle.

## 2.2	Defining the Needs

Defining the needs is an essential, early step in the procurement process. A proper definition of the needs will help determine the scope of the goods, works or services to be procured, identify the inputs to be provided by the client, and set standards and requirements against which future performance delivery can be assessed.

At this stage, it is advantageous to consider the need not in terms of the characteristics of the goods, works or services supposedly required. This should be dealt with only later, in the feasibility study stage. Instead, in order to allow the optimum solution to be found, the needs should be defined in terms of the objectives to be reached: the benefits and advantages to be obtained, the performance or service level to be reached, the functions to be carried out, or the knowledge, skills or insight to be gained.

The definition of needs must also take account of the contracting authority’s circumstances, for example in relation to financial, technical, economic, social and environmental aspects.

Examples:

There is no point in proceeding if there is no prospect of budget availability.

The contracting authority might well be constrained by policy objectives, regulatory requirements or binding technical rules.

When advisory services are provided, recommendations must be made and reports submitted with due consideration of the beneficiary’s ability to act upon them, both in the immediate future and in the longer term. Capacity building and institutional development may be a necessary complement.

Skills required for operation and maintenance must be available at reasonable cost and conditions during the working life of plant and equipment. Additional vocational training facilities may be required.

## 2.3	Identifying the Parties

At an early stage in the procurement process, it is essential to identify the various parties and interests concerned in the project. They will all have different interests, roles and responsibilities. Many will have rights to intervene in the preparation or implementation process. Ignoring any of the interested parties at the beginning may upset project implementation and cause unnecessary delays and cost increases.

Among the parties to be considered are the following:

End-users and (final) beneficiaries: those who will make direct use of or otherwise benefit from the results of a project;

Economic operators: the suppliers, contractors, consultants and other service-providers active or potentially active in the market and those who might wish to be so;

Taxpayers and the general public: often represented by ministries, politicians or special interest groups;

Regulatory and supervisory bodies: and other authorities concerned, including internal and external auditors;

Funding institutions and financiers; and in particular in the present context the Commission in relation to any Community funding;

Parties to any existing or related contract;

Third parties: rights holders, land owners, neighbours;

The responsible official in the contracting authority, the client, must ensure that public consultation procedures etc. as may be prescribed by national legislation, especially for works, are duly prepared and carried out.

## 2.4	Regulations, Standards, Licences and Approvals

Depending on the nature of the project, various regulations and standards have to be complied with and permits, licences and approvals obtained. In order to encourage tenderers to participate, and to minimise the risk for costs and delays later in the project, it is in the interest of the client to determine these at an early stage, and to resolve any regulatory issues and make any applications which can be dealt with prior to inviting tenders.

For goods, typical cases concern the physical characteristics of the products and their compliance with applicable standards and requirements.

For works, typical cases concern the planning, zoning or similar permissions for the works, environmental requirements and permits, and verification and approval of the conformity of designs with applicable building codes and similar standards.

For services, typical cases concern the tax situation of foreign experts and the application of professional qualification requirements. In the present context there may questions of eligibility to address.

The tender documents must clearly set out which permits etc. have been (or are being) obtained by the client and may advantageously indicate which permits etc. must be obtained by the supplier, contractor or consultant. The contract must set out the responsibilities of each of the parties for complying with laws, regulations, etc in this respect.

It should be noted that requirements for certain standards must not be made in a discriminatory way. Similarly, inspection, testing or other verification of conformity with such standards or the like may not be done in a way that has the effect of rejecting goods or works which are produced or carried out under equivalent standards or which otherwise can be demonstrated to meet the corresponding requirements.

## 2.5	Feasibility

Once the needs have been identified, it is necessary to determine in somewhat greater detail the feasibility of meeting them by various means possible, so that an informed decision can be taken on which solution and approach to select for the implementation of the project. This is often done in the form of a feasibility study carried out for this purpose by experts in the field concerned, in close consultation with the parties concerned. If sufficient internal resources are available, the contracting authority may prefer to carry out the study in-house, otherwise a suitably qualified external consultant should be engaged.

It is important to start out by considering a sufficiently wide range of possible solutions, and to narrow down the choice only little by little. Each step taken in this process must be clearly described and suitably documented.

Among the aspects to be covered by the feasibility study are the following:

(i)	the technical possibilities at large for meeting the needs;

(ii)	institutional, technical, natural, environmental, social and other conditions affecting the choice of solution for meeting the needs;

(iii)	products, processes, designs, skills and know-how available on the market, issues of reliability and maintainability;

(iv)	suppliers, contractors, operators and consultants active in the market;

(v)	skills and resources of the contracting authority, both for preparation and procurement and for monitoring, supervision and contract administration during implementation;

(vi)	possible distribution of tasks and responsibilities for preparation, design, execution, operation and maintenance (as applicable): who would plan and decide, work out specifications, design works, write Terms of Reference, carry out procurement, check supplies, supervise work, administer contracts, supply goods, carry out construction, provide advice or other services, put supplies to use, operate and maintain plant and equipment, use facilities, make use of advice received or other services provided, etc.;

(vii)	time frames, both for the preparation and procurement process and for the implementation of the project;

(viii)	user acceptability and other social aspects;

(ix)	environmental impact, possible remedial actions;

(x)	risk analysis of the different solutions envisaged;

(xi)	suggested principal solutions and key alternatives (which quantity/size/kind of goods/facilities/ services); and

(xii)	the corresponding project delivery strategies, including draft procurement plans.

The report from the feasibility study sets out its findings and conclusions in a form aimed at facilitating review and decision making; cf. 2.8 below.

## 2.6	Costs and Benefits, Affordability, and Financing Options

The economic aspects are at the heart of public procurement. Value for money is an essential criterion for using public funds but requires careful review of all the benefits and costs associated with a project. To the extent reasonably possible, care should be taken to consider both direct and indirect benefits and costs, and to seek to quantify external effects. It is also essential to consider benefits and costs in the long term, and not only for the period of implementation of the project, be it for acquisition of goods, execution of works, or provision of services.

Although the economic analysis is described under a separate heading in this Chapter, it is often suitable to incorporate it in the feasibility study described under 2.4 above as a means of identifying the principal solutions and key alternatives to be suggested. Economic considerations may help narrow down the alternatives being examined and allow resources to be concentrated on reviewing the most promising ones.

It must be stressed that for most kinds of goods, works and services provided for more general use, questions of affordability and of the interplay between price and demand are essential for determining the right capacity, and thus the cost of putting this capacity into place and keeping it available. Supply of drinking water is a particularly eloquent example of this but the same phenomena occur also in many other circumstances.

For projects to be carried out over a period of several years, such as more important works or many types of advisory services, as well as for those requiring subsequent financing of operation, maintenance and the like, efforts should be made to ensure that corresponding financing is secured no later than at the time when the contract is concluded.

Among the economic aspects which would typically be covered at this stage are the following:

(i)	what are the benefits (also in non-monetary terms) of the various solutions feasible;

(ii)	what is their value (in monetary terms);

(iii)	what are the costs (both at market prices and in economic terms; consider exchange rate fluctuations, inflation as applicable) of the different elements: facilities, goods or services; their construction, supply or provision as well as their use, operation, maintenance, refurbishment, disposal, etc., as applicable;

(iv)	how are these costs and benefits distributed over time; how does their present value vary with various assumptions about interest rates, time horizons, time preferences, etc.;

(v)	which costs would be considered as affordable: what would people (not only users but also other beneficiaries and the taxpayer at large) be willing and able to pay for the goods, works or services (setting it against various scopes of supply, levels of service, etc.);

(vi)	how would demand be expected to vary as a function of the prices charged, the quality and quantity available, etc.; how would the supply capacity required from a plant or a network or a service facility and the corresponding fixed and variable costs interact with such demand; what would be the capacity, costs and prices at equilibrium; how well determined and how stable would this equilibrium be;

(vii)	as applicable, how could costs be recovered, how would products be priced, how would fees or charges be collected (e.g. in cases like resale of goods, cost recovery for municipal services etc. by user charges, or payment for advisory services by users; subsidies; taxes, etc.);

(viii)	should any users or other beneficiaries be treated differently for reasons of ability to pay or the like; if so, how should this be compensated;

(ix)	which (other) options would be available for financing the project (loans and grants from various sources; private sector participation, including public-private partnerships, private finance projects, works or service concessions, or “finance, build, operate and transfer” arrangements, etc.); how would these options interact with the other considerations above.

It is recognised that many of these issues are inherently difficult to resolve or would require large analytical resources. However, they should nevertheless be explicitly considered in the procurement planning process. Even if described only briefly and in very simple terms, the considerations and any underlying assumptions as well as the conclusions which are arrived at made should be documented.

## 2.7	Choice of Procurement Procedure

The choice of procurement procedure should be guided and determined by the complexity and nature of the contract whilst taking into account the need of efficiency and cost-effective procurement processes, including the optimal use of the competitive situation in the market.

The Directives permit the following procedures:

→	Open Procedure

→	Restricted Procedure

→	Negotiated Procedures (with or without a call for competition)

Below the EC thresholds, this guide recommends the use of a set of simplified procedures. National legislations may also lay down simplified procedures or impose the use of the same procedures as over the thresholds. The simplified recommended procedures are::

→	Simplified Open Procedure

→	Simplified Restrictive Procedure

→	Negotiated Procedures

→	Direct Procurement

Under the Directives, there is free choice between the open procedure and the restricted procedure. Both involve formal competitive tendering but the restricted procedure allows the contracting authority to manage the number of suitable candidates it will invite to tender.

The open procedure is a procedure in which any economic operator can tender and should be seen as the main procedure for the procurement of supplies and smaller works under EU financing, unless the scope and nature of the contract would justify the use of any of the other procedures available.

The restricted procedure which is a two-step procedure where the invitation to tenderer is preceded by the selection of the suitable candidates determined qualified to perform a possible contract with the contracting authority. The restricted procedure is specially designed to meet the special requirements involved in the procurement of larger construction works, civil engineering, supply and install projects, major specialised goods and equipment and service contracts. The scope, nature and complexity of the procurement involved should be determining factors for the use of the restricted procedure.

Negotiated procedures may only be used in case the conditions for their use are met.

## 2.8	Acquisition Decision

Having determined the needs, identified the parties concerned, considered the relevant regulations and standards applicable, studied the feasibility of various approaches and estimated their economic implications, and carried out appropriate consultations, the contracting authority should be in a position to decide which goods, works and services will be procured. It is important to formulate this decision in terms which are not unduly limitative or restrictive. In most cases, best value for money is obtained when suppliers, contractors and consultants have a certain freedom to propose the goods, works and services which best serve the needs identified and best meet the contracting authority’s requirements. In particular, specifications or designs must not be more detailed than appropriate in view of the project delivery strategy chosen; terms of reference would typically put more emphasis on the results to be achieved than on the precise activities to be carried out.

The time frame for implementation will be given.

The decision will typically indicate the expected costs and how they would be covered, set out budgetary obligations, identify sources and conditions of external financing, and determine (or set the basis for determining) prices, user fees or the like to be charged to users or beneficiaries.

Finally, the acquisition decision will set out the project delivery strategy selected. The first element of this is the contracting strategy: the ‘packaging’ of the procurement in different contracts to be concluded, the forms of contract to be used, and the basis for valuation and payment under the contract. It is complemented by considering the procurement procedures to be used. These largely depend on the value and nature of the contracts.

The items to be procured, the corresponding contracts and their expected costs together with the time frame for implementation are summed up in a procurement plan which may form the basis of a business case for authority to proceed.

## 2.9	Organisation of Tender Work

The organisation of the procurement work within the contracting authority is essential for the successful managing of the procurement operations, including the preparation and conduct of the tender proceedings.

A decision to move to the next stage of the acquisition process will imply the need to confirm which procedure to use and to develop the tender dossier including the technical specification, the tender documents, the selection and award criteria and the proposed contract terms.

The tender work must be organised as a function of the above. The work schedule should be based on the procurement plan, ensuring that suitable staff resources are made available as and when needed. Since the work load would mostly be uneven over time, and different skills would be required in different stages of preparation and implementation, the organisation should be flexible, both to prevent bottlenecks and to avoid sitting with underutilised capacity.

The contracting authority would normally have its own organisation and procedures already set up for purchasing goods and services and managing investment projects. For larger investments with external financing it is often advantageous to set up a special project organisation. It may include e.g. an evaluation committee and specialists on the procurement and disbursement procedures required by the financiers.

## 2.10	Specifications and Requirements

The purpose of technical specifications (for supply and works contracts) and statements of requirements (terms of reference for service contracts) is to give instructions and guidance to tenderers to inform their tenders and to serve as the supplier’s, contractor’s or service provider's mandate during project implementation. The terms of reference or technical specifications will be included in the tender documents and will become an annex of the eventual contract awarded as a result of the tender.

They should reflect correctly the needs of the contracting authority and the budget estimations made for the acquisition. Incorrect or unrealistic specifications are a common reason for many of the problems that later frequently occur during the tender and award process, such as the need for issuing amendments to the tender dossier, cancellation of tender proceedings, lodging of complaints and contract problems. The technical specifications will be included in the tender dossier and will become an annex of the eventual contract awarded as a result of the tender.

Furthermore, a set of precise and clear specifications is a prerequisite for tenderers to respond realistically and competitively to the requirements of the contracting authority. They must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, performance and other factors of relevance related to products and services to be procured.

Technical specifications must afford equal access for candidates and tenderers and not have the effect of creating unjustified obstacles to competitive tendering.

The thorough preparation of the terms of reference or technical specifications is extremely important for the ultimate success of the project. It is most likely to ensure that the project has been properly conceived, that the work is carried out on schedule and that resources will not be wasted. Therefore greater effort during project preparation will save time and money in the later stages of the project cycle.

Technical specifications must afford equal access for candidates and tenderers and must not have the effect of creating unjustified obstacles to competitive tendering. They define the characteristics required of a product, service or material or work with regard to the purpose for which they are intended by the contracting authority.

The terms of reference or technical specifications are prepared by the contracting authority. It is helpful to consult all parties involved in the proposed project in preparing terms of reference or technical specifications. This should improve both the quality of the project as well as the commitment of the contracting authority and end-users.

Once the terms of reference or technical specifications have been finalised, the corresponding tender procedure should be launched as soon as possible. The terms of reference or technical specifications contained in a tender dossier — the supposed basis for the project work-plan — must reflect the situation at the time of project start-up so as to avoid considerable effort having to be spent re-designing the project during the inception period.

The Directives provide that the technical specifications should defined by the contracting authorities by reference to national standards implementing European standards, or by reference to European technical approvals or by reference to common technical specifications.

Definitions

(1)	“Technical specifications” means the totality of the technical requirements contained in particular in the contract documents, defining the characteristics required of a service to be provided, a material or product to be supplied or works to be constructed, and thus permitting them to be described in a manner such that it fulfils the use for which it is intended by the contracting authority;

(2)	“Standard” means a technical specification approved by a recognized standardizing body for repeated and continuous application, compliance with which is in principle not compulsory;

(3)	“European standard” means a standard approved by the European Committee for Standardization (CEN) or by the European Committee for Electrotechnical Standardization (Cenelec) as ‘European standards (EN)’ or ‘Harmonization documents (HD)’ according to the common rules of these organizations;

(4)	“European technical approval” means a favourable technical assessment of the fitness for use of a product, based on fulfilment of the essential requirements for building works, by means of the inherent characteristics of the product and the defined conditions of application and use. The European approval shall be issued by an approval body designated for this purpose by the Member State;

(5)	“Common technical specification” means a technical specification laid down in accordance with a procedure recognized by the Member States to ensure uniform application in all Member States which has been published in the Official Journal.

Exceptions

where there are legally binding national technical rules which are compatible with the Treaty;

where the standards etc do not include any provision for establishing conformity or the technical means to do so do not exist;

where there would be a conflict with EC provisions on telecoms equipment, information technology or specific service or product areas;

where use of the standards etc would result in incompatibility with equipment in use, disproportionate costs or disproportionate technical difficulties;

for genuinely innovative projects.

The justification for invoking an exception must be given in the contract notice or the tender dossier.

Technical specifications must not refer to services, goods or works of a specific make or source, or process, in particular to trade marks, patents, types or a specific origin if that would favour certain service providers, suppliers, products or contractors. Such an indication is permitted, however, where it would otherwise be impossible to describe the subject of the contract with sufficient precision, but only if accompanied by the words “or equivalent”.

Non-discrimination

There is a general ban on technical specifications which mention goods of a specific make or source or of a particular process and which have the effect of favouring or eliminating certain enterprises or products. Among the specifications that can have such a discriminatory effect, and are therefore prohibited, the Directive mentions in particular the indication of trade marks, patents, types or a specific origin or production.

An exception to this general ban is allowed where the subject–matter of the contract cannot otherwise be described by specifications, which are sufficiently precise and intelligible to all concerned. Reliance on this derogation should not, however, have discriminatory effects; to that end, the Directive requires that such indications be accompanied by the words “or equivalent”. Contracting authorities relying on this or other derogations must always be able to provide evidence that they are necessary.

Principle of equivalence and mutual recognition

Contracting authorities must presume that products manufactured in accordance with the standards drawn up by the competent standards bodies conform to the essential requirements laid down in the directive concerned. They may not refuse products simply because they were not manufactured in accordance with such standards, if evidence is supplied that those products conform to the essential requirements established by Community legislative harmonization.

If there are no common technical rules or standards, a contracting authority cannot reject products from other Member States on the sole grounds that they comply with different technical rules or standards, without first checking whether they meet the requirements of the contract.

In accordance with the mutual recognition principle, it must consider on equal terms products from other Member States manufactured in accordance with technical rules or standards which afford the same degree of performance and protection of the legitimate interests concerned as products manufactured in conformity with the technical specifications stipulated in the contract documents.

## 2.11	Selection, Qualification and Suitability Criteria

The specifications and requirements set out the required characteristics of the goods, works or services to be procured. In the procurement process, it is also necessary to determine which tenderers may participate or which ones would be considered sufficiently well qualified, and to define the criteria against which tenders will be evaluated and the contract awarded.

The qualification criteria concern the financial standing of tenderers as well as their technical skills and resources and other elements which determine their capacity to deliver the goods, works or services. Tenderers must meet the minimum qualifications to provide the goods, works or services in question before their tenders can be considered.

When a selective procedure is to be used, participants will have to be selected in a transparent and non-discriminatory manner. The selection criteria are aimed at helping identify the candidates to be invited to tender.

The suitability of a candidate or a tenderer shall be assessed in accordance with the qualitative selection criteria laid down in the notices and documents issued in order to determine either (under the first phase of the restricted procedure and the negotiated procedure with prior call for competition) the candidates who will be invited to participate or (under the open procedure) whether a tenderer meets the contracting authorities minimum requirements and capable of performing a possible contract satisfactorily.

The contract notice and the tender documents shall state the criteria as well as the minimum qualification requirements that have to be met by the candidates and tenderers in order to be invited to submit a tenderer or under the open procedure to qualify for the award of contract. Furthermore, the contracting authorities are required to state in their contract notices, or invitations to tender, what evidence they require as to a candidate or tenderer´s personal position, economic and financial standing and technical capacity.

For the restricted procedure and the negotiated procedure with publication, the contracting authority is required to state the number of undertakings it intends to invite to participate or the range within which that number will fall. (No less than 5 in a restricted procedure, no less than 3 in the negotiated procedure with publication, if a sufficient number of suitable candidates is available. For genuine competition, 3 candidates are usually considered necessary.)

Under the open procedure, the contracting authority is required to consider the tenders from all the economic operators whose personal position is satisfactory and who meet the contracting authority’s minimum requirements of an economic and technical nature. Under the restricted procedure and the negotiated procedure with a call for competition, the contracting authority must select from the candidates who meet its minimum requirements those it will invite to tender or negotiate. In addition, it must do so objectively and on the basis of the evidence permitted (see below).

Economic and financial standing. The proof of an economic operator’s financial standing may, as a general rule, be furnished by:

statements from bank;

balance sheets, or extracts thereof, where published under national legislation;

evidence of relevant turnover over the last 3 years;

evidence that third party resources will be available;

alternative evidence if the undertaking is unable to provide the above;

an economic operator may, where appropriate and for a particular contract, rely on the capacities of other authorities, regardless of the legal links which it has with them and that, in that case, it must prove to the contracting authority that it will have at its disposal the resources necessary for the execution of the contract, for example by producing a statement from those authorities that that they will place the necessary resources at the disposal of the economic operator.

Technical capacity. The evidence of an economic operator’s technical capacity may be furnished by:

a list of recent contracts (3 years for principal deliveries of supplies, plus evidence of satisfactory performance;

a statement of the tools, plant and technical equipment available to the undertaking;

a statement of the firm’s average manpower and number of managerial staff over the past 3 years;

a statement of the technicians or technical bodies which the economic operator can call upon, whether or not under the undertaking’s control, especially those responsible for quality control;

a description of a supplier’s technical facilities and measures for ensuring quality and his study and research facilities;

where the supplies to be provided are complex, or exceptionally, they are required for a special purpose, a check carried out by the contracting authority or on its behalf by a competent official body in the undertaking’s home country, on the technical capacities of the service-provider and, if necessary, his study and research facilities and quality control measures;

samples, descriptions and/or photographs, the authenticity of which must be certified if the contracting authority so requests;

certificates drawn up by official quality control institutes or recognised agencies attesting the conformity of the specified products to specifications or standards;

the ability of undertakings may be evaluated in particular with regard to their skills, efficiency, experience and reliability for contracts involving installation of supplies.

## 2.12	The Award Criteria

Contract award criteria are used when evaluating tenders in order to rank them by merit with a view to identifying the most favourable one. The award criteria used for this purpose may be:

a)	the economically most advantageous tender, taking into account e.g. quality, technical merit, functional and environmental characteristics, service, delivery dates, price, etc.; or

b)	the lowest price (under the condition that the tender is otherwise compliant).

It is very important to select award criteria which match the specifications and requirements and correspond to the nature and purpose of the goods, works or services to be procured. Typically, quality and technical merit are of dominating importance for intellectual (consulting) services. It may also be an important criterion for works and equipment. For routine goods, where quality, delivery time and other factors are less significant, “lowest price” may be adequate.

The selection, qualification and award criteria must be determined and made known to (prospective) tenderers in advance of the respective procurement proceedings. This is typically done by including such information in notices and in the tender documents.

Where the criterion is most economically advantageous tender, in addition to price, the following factors, as examples, may be considered, as applicable:

delivery and completion date;

running costs;

cost-effectiveness;

quality;

economical, aesthetic and functional characteristics;

technical merit;

after-sales service; and

technical assistance.

The contracting authority must specify the relative weighting it gives to each of the award criteria in the contract notice or the contract documents. The weighting can be expressed as a range with an appropriate spread and that, if weighting is not possible for demonstrable reasons, the criteria are to be listed in descending order of importance. The contracts to be awarded on the basis of the criteria laid down by the contracting authority. Preferably, factors other than price to be used should be quantifiable.

## 2.13	Preparation of the Tender Documents

The tender documents are the focal point in the tendering process and shall furnish all information necessary for a prospective tenderer to prepare a responsive tender for the supplies to be provided. While the detail and complexity of these documents may vary with the size and nature of the contract, as further set out in the following Chapters, they generally should include:

(a)	Invitation to Tender;

(b)	Instructions to Tenderers;

(c)	General and Special Conditions of Contract;

(d)	Technical Specifications;

(e)	Tender Form;

(f)	Contract Form;

(g)	Appendices (model financial offers, forms for guarantees, etc., as applicable).

The tender documents shall be drafted so as to permit and encourage the widest possible competition. They shall clearly define the scope of supplies and associated services to be supplied, the rights and obligations of the contracting authority and of suppliers, and the conditions to be met in order for a tender to be declared responsive, and they shall set out fair and non-discriminatory criteria for selecting the winning tender.

Guiding principles for the design of the tender documents.

It rests on the contracting authority:

to prepare a thoroughly drawn up tender dossier by using the appropriate model tender documents attached to this guide, which allow optimal competition and make it possible, generally, to make an award decision without prior negotiations;

to ensure that all legal formalities in connection with the tender proceedings will be met; announcement of tender, submission and opening of tenders, presentation of award criteria and recording of the process; and

to include technical, commercial, environmental and other requirements that correctly will balance and optimally reflect the character and size of the contract.

In particular, the following areas are of importance in the preparation of the tender documents:

Based on the size and duration of the contract determine the qualification or selection criteria for participation in the tender which shall be disclosed in the contract notice and tender documents, when applicable;

Determine how qualifications shall be evidenced by tenderers without imposing unnecessary formal conditions which could affect negatively the participation;

Decide on the appropriate packaging of the tender and whether to allow the tendering for lots;

Decide whether groups or joint ventures will required to take a specific legal form for performance of the contract;

Decide on the award criteria, and their relative weighting or if necessary their descending order of importance for listing in the contract notice or tender documents;

Decide on instruments for the invitations to participate or for tenders in addition to the publication of a contract notice in the OJEU, such as the government website or procurement bulletin of the member state, national and local newspapers;

Determine the appropriate time limits for the preparation and submission of tenders, which shall respect the minimum time limits, but sufficiently extended, when so required, in order to correctly reflect the size and complexity of the tender;

Determine the length of the tender validity period, which should be set to enable an effective and correct tender evaluation, including the award and conclusion of contract, but not as long that the time length may affect prices and costs negatively. Normally the validity period would fall within the range of 60-90 days;

Consider the need for a pre-bid conference, which could be necessary in the case of complex technical specifications or contract conditions;

Decide on the need for requesting tender and performance securities. This should normally be avoided since it hinders participation and has a negative effect on competition. The use of tender securities, however, could be justified for large and complex supply or works contracts, where a withdrawal would be very costly for the contracting authority;

Determine the appropriate contract model taking into account the size, type and duration of the contract.

Section 3. 	Tender proceedings

## 3.1	Organisation of Tender Proceedings

The Directives do not contain any specific provisions on the organisation of tender proceedings except to require tenders to be opened after the deadline, to make provision for confidentiality and, for electronic tenders, to require the use of systems and equipment that are generally available. It is entirely a national concern to elaborate tender proceedings and practices which vary considerably. The use of tender committees for the opening and evaluation of tenders is common practice in the new Member States and candidate countries, as required by national legislation, although with differences in the functions and mandates given to the tender committees.

Whatever the role and mandate assigned to a tender committee in a national context, there are some general concerns in relation to the organisation of the procurement proceedings that should be observed, namely:

The planning and preparation of tender processes is often decisive to the quality and successful outcome of the tender proceedings and should therefore be organised in a manner that correctly reflects the needs of specialised procurement competence, procedurally, technically and commercially. Subject to the size of the contracting authority, the annual procurement volume and the nature of contracts envisaged, there is often a need to establish a specialist procurement body that can operate as an internal service unit providing a range of qualified procurement services to the end-user departments of the contracting authority;

For large projects running over a long period, in particular in the case of Community financing, the creation of specialised project implementation units is also recommended;

For the purpose of accountability, there must be clarity on the responsibilities and the decision-making powers, including delegation policy, within the line organisation of the contracting authority in terms of authorisation to make an award decision, to sign the contract and to authorise payments under the contract.

For the purposes of this guide, the following principles apply:

- A tender committee should only have the mandate to issue a recommendation as to the award of a contract. The authorised officer of the contracting authority should make the formal decision and be held accountable for it;

- A tender committee may be created either on an ad-hoc or permanent basis. In the latter case, the committee should be obliged to appoint the specialists needed for a fair and competent technical and commercial evaluation of the tenders;

- Contracting authorities should only be required to establish tender committees for significant contracts such as those governed over the thresholds. It more appropriate for the relevant units of the line organisation of the contracting entities to conduct the evaluation and award of low-value contracts (for example below the EC thresholds);

- The persons responsible for the preparation of the tender dossier, including technical specifications, instructions to tenderers, the evaluation and award criteria, and the general and special conditions of the contract, should be appointed members of the tender committee.

- In a context where the use of this guide is mandatory under pre accession financing, with ex ante control, the composition of the tender committee may need to be submitted to the Commission for approval, depending on the terms of the Financial Agreement.

Contracting authorities should apply the following general rules for the formation and operation of tender committees. Individual differences between the various areas of procurement will be addressed in the respective Chapters in the Operational Guidelines for goods, works and service contracts.

The Evaluation Committee

Composition

Where an evaluation committee is used, the members should be appointed by the contracting authority on a personal basis. The membership should comprise, including an observer, a non-voting Chairman, a non-voting Secretary and a minimum of 3 (three) voting members.. Each member should demonstrate a working proficiency of the language in which the tenders are submitted. The voting members must possess the technical and administrative capacities necessary to give an informed opinion on the tenders.

The evaluation committee members should attend all meetings. Any absence should be recorded and explained in the Tender Evaluation Report. All voting members of the evaluation committee should have equal voting rights. The names and functions of all those involved in the evaluation process must be recorded in the Tender Evaluation Report.

Impartiality and Confidentiality

All members of the evaluation committee, including the observer, must sign a Declaration of Impartiality and Confidentiality (see Annex A4). Any tender committee member or observer who has a potential conflict of interest due to a link with any tenderer must declare it and immediately withdraw from the Tender committee. He/she will be excluded from participating further in any capacity in the evaluation meetings.

No information about the examination, clarification, evaluation or comparison of tenders or decisions about the contract award can be disclosed before the conclusion of the contract by the contracting authority and the successful tenderer. Any attempt by a tenderer to influence the process in any way (whether by initiating contact with members of the tender committee or otherwise) will result in the immediate exclusion of its tender from further consideration:

Apart from any tender opening session, the proceedings of the tender committee are conducted in camera and are confidential.

In order to maintain the confidentiality of the proceedings, participation in the tender committee meetings should strictly limited to the members of the tender committee, including the observer.

The tenders should not leave the room/building in which the committee meetings take place before the conclusion of the work of the tender committee. They should be kept in a safe place when not in use.

Responsibilities of the Evaluation Committee members

The Chairman is responsible for co-ordinating the evaluation process and for ensuring its impartiality and transparency. The voting members of the evaluation committee have collective responsibility for the recommendations made by the Committee.

The Secretary to the Committee is responsible for carrying out all administrative tasks connected with the evaluation procedure. These will include:

circulating and collecting the Declarations of Impartiality and Confidentiality;

keeping the minutes of all meetings of the tender committee and the relevant records and documents;

registering attendance at meetings and compiling the Tender Evaluation Report and its supporting annexes.

Timetable

The evaluation committee should be formed early enough to ensure the availability of the designated members during the period necessary to prepare and conduct the evaluation process. The tender evaluation should start and be completed as soon as possible. The duration of the evaluation process should be agreed between the tender committee and the contracting authority. The evaluation process should take as long as necessary having regard to the need to notify the successful tenderer within the tender validity period specified in the tender dossier.

## 3.2	Preparation of Tender Dossiers

The tender dossier holds a key position in the tendering process and must provide all the information necessary for a prospective tenderer to prepare a responsive tender. While the detail and complexity of the documents may vary with the size and nature of the contract, they generally should include:

a)	The invitation to tender;

b)	Instructions to tenderers;

c)	General and Special Conditions of Contract;

d)	Terms of Reference/Technical Specifications.

The tender dossier needs to be drafted so as to permit and encourage effective competition. The documents need to define as clearly as possible the scope of the works, goods or services to be procured, the minimum standards to be met by candidates and tenderers, the rights and obligations of the purchaser and the supplier, contractor or service provider, and any conditions to be met in order for a tender to be declared compliant, that is to say substantially responsive to the tender dossier.

If there needs to be a clarification meeting or site visit to clarify the tender dossier, including the scope of work and technical requirements, this should be specified in the instructions to tenderers, together with details of the arrangements.

## 3.3	Tender Validity Period

The period of validity of the tenders should be specified in the tender dossier and be sufficient to enable the contracting authority to complete the evaluation of tenders and conclude a contract with the successful tenderer. In exceptional cases, before the period of validity expires, the contracting authority may ask the tenderers to extend the period, for a specific number of days.

## 3.4	Tender Guarantees

A tender guarantee, in the amount specified in the tender documents, affords the contracting authority reasonable protection against irresponsible tenders and may be acceptable for high value contracts in certain circumstances. But a tender guarantee should not be set so high as to discourage tenderers and the amount should normally fall within the range of 1-5 per cent of the estimated contract price.

Since a request for tender guarantees is an obstacle for all tenderers, particularly for small and medium enterprises (SME), it should be used with moderation. It represents financial costs as well as being an administrative burden for all participating firms. A tender guarantee may be appropriate for works contracts and for complex supply contracts of significant value.

Tender guarantees should not be required for routine service contracts, framework agreements or low-value contracts.

## 3.5	The Use of the Two-envelope System

The two-envelope system, under which technical and financial proposals are submitted in different envelopes to be opened at separate times, has the effect of separating quality and price. It is more appropriate for some public procurement, as for example consultancy services.

## 3.6	Submissions and Receipt of Tenders and Requests to Participate

Tenders must reach the contracting authority at the address and, at the very latest, the date and time indicated in the tender dossier. The period for submission must be sufficient to guarantee the quality of tenders and so permit truly competitive tendering.

Experience shows that too short a period prevents candidates from tendering or causes them to submit incomplete or ill-prepared tenders. The deadline for submissions must fall on a working day.

Tenders should always be submitted by letter or by hand, unless the contracting authority has the facilities to accept communication by electronic means in accordance with the provisions of the Directive 97/52 et seq. The tools to be used for communicating by electronic means, as well as their technical characteristics, must be non-discriminatory, generally available and interoperable with the information and communication technology products in general use.

Requests to participate in procedures for the award of public contracts may be made by e-mail or by any other means as stated by the contracting authority in the contract notice. Under national legislation, confirmation in writing may be required where necessary for the purposes of legal proof.

Where a tender is submitted by post or delivered by hand, the following rules should apply:

The tenderer should seal the original and each copy of the tender in separate envelopes, duly marking them as ORIGINAL and COPY. The envelopes should then be sealed in an outer envelope;

The inner and outer envelopes should be addressed to the purchaser and bear the procurement references indicated in the tender document and with a statement “Not to be opened before the tender-opening”;

The tenderers should be advised by the tender dossier, that an incorrectly sealed and marked tender may run the risk of misplacement or premature opening, for which the purchaser cannot be held responsible;

The inner envelope should also indicate the name and address of the tenderer to enable the tender to be returned unopened in case it is declared “late”;

The tender must be signed by an authorised person according to the instructions stated in the tender dossier.

On receiving tenders, the contracting authority must register them and provide a receipt for those delivered by hand. The envelopes containing the tenders must remain sealed and be kept in a safe place until they are opened.

The outer envelopes of tenders should be numbered in order of receipt (whether or not they are received before the deadline for submission of tenders).

## 3.7	Tender Opening Procedure

The purpose of the tender-opening session is to check that the tenders are complete, that the tender guarantee, whenever required, has been provided, that the documents have been duly signed and that the tenders are generally in order.

The receipt and opening of tenders needs to be done in a manner that ensures the regularity of the proceedings. The tender opening session may be done by a public opening or by a non-public opening.

Public opening of tenders is recommended by the European Commission under Community funding for all supply and works contracts governed by the Directives under the application of the open or restricted procedures, except for tenders submitted by electronic means where special procedures may be used.

Non-public opening of tenders at a formal meeting is acceptable, particularly for (i) consultant services contracts, including other services, and in general (ii) for low value contracts, which normally implies contracts below the EC thresholds or as otherwise determined by the contracting authority or national legislation. The opening should be conducted by a tender committee or alternatively by a panel of at least two persons appointed by the contracting authority.

Where the tender opening is public, the minutes of the tender opening should be sent to the participants promptly after the opening of the tenders. Where appropriate, the minutes might also be published on the website of the contracting authority. The following are usually announced at a public tender-opening session: the names of the tenderers, the unevaluated tender prices, the provision of any requisite tender guarantee and fulfilment of any other formality or condition that the contracting authority thinks appropriate.

A Tender Opening Report should be prepared for all tenders, irrespective of value. It should comprise a summary of the tenders submitted and the minutes of the tender opening session. A simplified version may be used for low-value contracts. The Tender Opening Report should state:

the date, time and place of the session;

the persons present;

the names of the tenderers who have responded within the deadline;

whether the originals of the tenders were duly signed, and whether the tenders were sent in the requisite number of copies.

The specific rules and procedures for tender openings that may apply in conjunction with the procurement of supplies, services and works, respectively, may be elaborated in the operational Sections.

## 3.8	Clarification of Tenders

To assist in the examination, evaluation, comparison and qualification of the tenders, the Contracting Authority may, at its discretion, ask any tenderer for a clarification of its tender. Any clarification submitted by a tenderer in respect to its tender and that is not in response to a request by the Contracting Authority shall not be considered. The request for clarification and the response shall be in writing, except for the conduct of interviews in conjunction with the evaluation of tenders for consultant services contracts, when so permitted by the tender dossier.

No change in the prices or substance of the tender shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Contracting Authority in the evaluation of the tenders.

The Contracting Authority may waive any minor informality, non-conformity or irregularity, provided that such waiver does not prejudice or affect the relative ranking of any tenderer.

The Contracting Authority may request that the tenderer submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities or omissions in the tender related to documentation requirements.   Such omission shall not be related to any aspect of the price of the tender. Failure of the tenderer to comply with the request may result in the rejection of its tender.

Once the technical evaluation has been completed, the Contracting Authority checks that the financial offers contain no arithmetical errors. Arithmetical errors which can be corrected without prejudice to the tenderer must be corrected and notified to the tenderer concerned. Otherwise the tenderer must be given the opportunity to correct the error.

If the tenderer does not accept the correction of errors, its tender shall be disqualified.

## 3.9	Suspension and Cancellation of Tender Proceedings

Suspension

In exceptional and duly justified cases, tender procedures may be published with a conditionality clause. This may apply where a tender procedure is launched before a financing decision is issued or a financing agreement is signed between the European Commission and the beneficiary country; the award of the contract is therefore subject to the conclusion of the financing agreement and the provision of funding.

Because of its implications, the existence of a suspension clause must be explicitly mentioned in the procurement notice. The tender procedure will invariably be annulled if the Commission's decision-making procedure is not completed or the financing agreement is not signed.

Cancellation of award procedures

The contracting authority may, before the contract is signed, abandon the procurement or cancel the award procedure without the candidates or tenderers being entitled to claim any compensation. If a contract award procedure is cancelled, all tenderers must be notified as soon as possible, with confirmation in writing if requested together with the reasons for the cancellation.

Cancellation may occur where:

- the tender procedure has been unsuccessful, i.e., no qualitatively or financially worthwhile tender has been received or there is no response at all;

- the economic or technical data of the project have been fundamentally altered;

- exceptional circumstances or force majeure render normal performance of the contract impossible;

- all technically compliant tenders exceed the financial resources available;

- there have been irregularities in the procedure, in particular where these have prevented fair competition.

After cancelling a tender procedure, the Contracting Authority may decide:

- to open negotiations in the absence of tenders or suitable tenders under an open or restricted procedure, provided the terms of the contract are not substantially altered and on condition that a report is sent to the Commission if requested;

- not to award the contract;

- to launch a new tender procedure: either an open or a restricted procedure, or a negotiated with a call for competition in the event of cancellation justified by irregular or unacceptable tenders under an open or restricted procedure, provided the terms of the contract are not substantially altered and following a further contract notice unless all the compliant tenderers in the original procedure are included.

Whatever the case, the final decision is taken by the contracting authority (if necessary with the prior agreement of the Commission in the case of contracts awarded under the ex-ante system). If the contracting authority has reserved the right to cancel without reason it will not be liable for any damages, including, without limitation, damages for loss of profits in any way connected with the cancellation of the tender. The publication of a contract notice does not commit the contracting authority to implement the programme or project announced.

## 3.10	Modification of Contracts

Concluded contracts may need to be modified during their duration if the circumstances affecting implementation have changed since the initial contract was signed. Where the Directives apply, there is provision for additional supplies, works or services in closely defined circumstances. Contract modifications may need to be formalised through an addendum to the contract, but under no circumstances may exceed 50 per cent of the original contract value. Such an addendum must be signed by both the contracting parties, and where Community financing is involved under a decentralised ex-ante system, such addenda may need to be approved and endorsed by the Commission.

The following general principles must always be respected:

A request for contract modifications should not be accepted unless such request is properly substantiated. The Contracting Authority must examine the reasons given and reject requests which have little or no substantiation.

Contracts can only be modified within the lifetime of the contract; modifications cannot be made retroactively.

The purpose of the addendum must be closely connected with the nature of the items covered by the initial contract.

Major changes, such as a fundamental alteration of the specifications, cannot be made by means of an addendum.

The addendum must not alter the competition conditions prevailing at the time the contract was awarded.

Unit rates or prices must be identical to those in the initial contract, unless the initial contract stipulates otherwise (i.e., there is a price-revision clause).

Any modification extending the performance period of the contract must be such that implementation and final payments can be completed before the expiry of the financing agreement under which the initial contract was financed.

Any modifications that require additional funding must have been foreseen in the specifications of the initial contract and can only be agreed before the expiry of the financing agreement under which the initial contract was financed. The additional funding must come from the same budget line as that used for the initial contract.

Under no circumstances can the contracting authority increase the budget of the initial contract beyond that covered in the specifications of the initial tender and subsequent contract.

Section 4.	Consultant Services Contracts

## 4.1	Introduction

Technical and economic support in the course of cooperation policy involves recourse to outside know-how on the basis of service contracts, most of them for studies or technical assistance.

Study contracts include studies for the identification and preparation of projects, feasibility studies, economic and market studies, technical studies, evaluations and audits.

Study contracts generally specify an outcome, ie, the service provider must provide a given product: the technical and operational means by which it achieves the specified outcome are irrelevant. These are, therefore, lump-sum contracts and the service provider will be paid only if the specified outcome is achieved.

Technical assistance contracts are used where a service provider is called on to play an advisory role, to manage or supervise a project, or to provide the experts specified in the contract. Technical assistance contracts often only specify the means, i.e., the service provider is responsible for performing the tasks entrusted to it in the terms of reference and ensuring the quality of the services provided. Payment for these contracts is dictated by the resources and services actually provided. The service provider does, however, have a duty of care under the contract: it must warn the Contracting Authority in good time of anything that might affect the proper execution of the project.

Some service contracts may, however, combine both types, specifying both the means and the outcome.

The Contracting Authority, which is always specified in the contract notice, is the authority as defined in the glossary of terms (Annex A01) empowered to conclude the contract.

Service contracts are concluded directly by the Contracting Authority designated in a financing memorandum, ie, the government or an entity of the beneficiary country with which the European Commission establishes the financing memorandum. The Contracting Authority will select candidates and draw up shortlists and is responsible for issuing invitations to tender, receiving tenders, chairing tender-examination sessions, deciding on the results of tender procedures and signing the contracts with the prior approval of the European Commission. The Contracting Authority must submit Prior Indicative Notices, contract notices and award notices to the OJEU for publication, using standard forms and the EU reference nomenclature applicable to public contracts (CPV).

"Service provider" describes any natural or legal person, public entity or group thereof offering services in the market. A service provider who has applied to take part in a restricted procedure or a negotiated procedure is termed a "candidate"; a service provider who has submitted a tender is termed a "tenderer".

Services contracts other than consultancy services should also follow provisions compatible with the EC directives.

## 4.2	Award Procedures

### 4.2.1	Contracts above the EU Threshold

4.2.1.1	Choice of Procedure

All service contracts at or above the EU threshold may be awarded by an open procedure or by a restricted procedure following publication of a contract notice as laid down in Section 1.

The open procedure is defined in the directives as a procedure in which any economic operator can tender. It should be recalled, however, that contracting authorities can reject tenderers who do not meet their minimum standards and that only EU economic operators, or equivalent under an agreement with the EU, have rights under Community law.

The restricted procedure is defined as a procedure in which any economic operator can ask to participate but only those invited to do so by the contracting authority can submit a tender.

The negotiated procedure with or without a prior call for competition may only be used in exceptional circumstances as stated below. The Contracting Authority must seek prior approval from the European Commission to use the negotiated procedure.

4.2.1.2	Negotiated Procedure

Contracting Authorities may use the negotiated procedure with prior publication of a contract notice in the following exceptional cases:

(a)	In the event of irregular tenders or tenders which are unacceptable under national provisions compatible with the Directive under an open or restricted procedure, provided the original terms of the contract are not substantially altered.

(b)	In exceptional cases where the nature of the services or the risks attaching thereto do not permit prior overall pricing.

(c)	In the case of services, inter alia financial services and intellectual services such as services involving the design of works, insofar as the nature of the services to be provided is such that contract specifications cannot be established with sufficient precision to permit the award of the contract by selection of the best tender according to the rules governing open or restricted procedures.

Contracting authorities may award public contracts by a negotiated procedure without prior publication of a contract notice in the following exceptional cases:

(a)	when no tenders or no appropriate tenders or no applications have been submitted in response to an open procedure or a restricted procedure, provided that the initial conditions of contract are not substantially altered and on condition that a report is sent to the Commission if it so requests;

In such cases, after cancelling the award procedure, the Contracting Authority may negotiate with one or more tenderers of its choice, from among those that took part in the tender procedure, provided that the initial conditions of the tender procedure are not substantially altered and that the principle of equal treatment is observed.

(b)	when, for technical or artistic reasons, or for reasons connected with the protection of exclusive rights, the contract may be awarded only to a particular service provider;

(c)	insofar as is strictly necessary when, for reasons of extreme urgency brought about by events unforeseeable by the contracting authority in question, the time-limit for the open, restricted or negotiated procedures with publication of a contract notice cannot be complied with. The circumstances invoked to justify extreme urgency must not in any event be attributable to the contracting authority;

(d)	when the contract concerned follows a design contest and must, under the applicable rules, be awarded to the successful candidate or to one of the successful candidates, in the latter case, all successful candidates must be invited to participate in the negotiations;

(e)	for additional services not included in the project initially considered or in the original contract but which have, through unforeseen circumstances, become necessary for the performance of the services described therein, on condition that the award is made to the economic operator performing such services:

when such additional services cannot be technically or economically separated from the original contract without major inconvenience to the contracting authorities, or

when such services, although separable from the performance of the original contract, are strictly necessary for its completion.

However, the aggregate value of contracts awarded for additional services may not exceed 50% of the amount of the original contract;

(f)	for new services consisting in the repetition of similar services entrusted to the economic operator to whom the same contracting authorities awarded an original contract, provided that such services are in conformity with a basic project for which the original contract was awarded according to the open or restricted procedure. As soon as the first project is put up for tender, the possible use of this procedure shall be disclosed and the total estimated cost of subsequent services shall be taken into consideration by the contracting authorities.

It should be noted that the Directive does not apply where a contracting authority awards a service contract to another contracting authority on the basis of an exclusive right — see Article 6 of Directive 92/50 EC.

Where the negotiated procedure is used with or without a call for competition, the Contracting Authority must prepare a Negotiation Report justifying the manner in which the negotiations were conducted and the basis for the contract award decision resulting from these negotiations. The procedures given in Sections 1 must be followed by analogy, with the Negotiation Report being included in the contract dossier.

### 4.2.2	Contracts under the EU Threshold

Contracts of a value under the EU threshold may be awarded using a simplified procedure.

## 4.3	Open or Restricted Procedure for Contracts above the EU Threshold

### 4.3.1	Publicity

In order to ensure the widest possible publicity and the requisite transparency, every EU funded contract under a pre accession instrument shall be included in a Prior Indicative Notice (PIN) as well as a contract notice.

The contracting authority must also dispatch a contract notice to OJEU for all service contracts above the EU threshold.

4.3.1.1. Publication of prior indicative notices

In addition to increasing the prospect of achieving better value from increased competition, dispatch of a full PIN to the OJEU may enable the contracting authority to take advantage of shorter minimum timescales for the receipt of tenders. A full PIN is one which includes as much of the information required for a contract notice as is available when the PIN is dispatched.

The PIN should set out the estimated total value of contracts, by service category, which the contracting authority intends to award during a budgetary year where the total estimated value of such contracts is equal to or greater than €750 000. It should be sent to the office for official publications of the European Union (OJEU) as early as possible in the budgetary year (see template in Annex B 01), where possible in electronic form and sufficiently in advance before the intended date of publication (the OJEU shall publish the notices not later than 12 days after their dispatch).

The publication of PINs does not bind the Contracting Authority to finance the contracts proposed, and service providers are not expected to submit application forms at this stage.

4.3.1.2	Publication of Contract Notices

In addition to any PIN, all service contracts at or above the EU threshold must also be the subject of a contract notice published in the Official Journal of the European Union.. Where possible the contract notice should be dispatched electronically and sufficiently in advance before the intended date of publication (the OJEU shall publish the notices not later than 12 days after their dispatch).

The European Commission is responsible for publication in the Official Journal of the European Union while, if the contract notice is also published locally, the Contracting Authority must arrange local publication directly. If the contract notice is also published locally, it must not be published before dispatch to the OJEU, it must not contain information other than that contained in the OJEU notice and must say when the OJEU notice was dispatched.

The contract notice must state clearly, precisely and completely what the subject of the contract is and who the Contracting Authority is. It is strongly recommended that it specifies the maximum budget available for the intended operation and the forecast timetable of activities. It must provide would-be service providers with the information they need to determine their capacity to fulfil the contract in question. It must also indicate the range within which the number of service providers which they intend to invite will fall (See template in Annex B03)

| ( | The selection criteria identified in the procurement notice must be: |
| --- | --- |
|  | □ Clearly formulated, without any ambiguity |
|  | □ Easy to verify on the basis of the information submitted using the standard application form (see Annex B04) |
|  | □ Devised to allow a clear YES/NO assessment to be made as to whether or not the candidate satisfies a particular selection criterion |
|  | The criteria specified in the annexes to this guide are given by way of illustration and should be adapted to the nature, cost and complexity of the contract. |

| ( | Candidates are required to use the standard application form (see template in Annex B04: |
| --- | --- |
|  | Its format and instructions must be strictly observed. |
|  | □ Any application which does not observe these provisions will be automatically eliminated. |
|  | □ Any additional documentation (brochure, letter, etc.) sent with an application will not be taken into consideration. |

The time allowed for candidates to submit their applications must be sufficient to permit proper competition. The minimum deadline for submitting applications is 37 days from the date of dispatch of the contract notice to the Official Journal of the European Union. The actual deadline will be determined by the contract's size and complexity.

### 4.3.2	Establishment of Shortlists

The short-listing of candidates may be carried out by the Contracting Authority or by an Evaluation Committee appointed by the Contracting Authority to act on its behalf. If so, the Committee should comprise a non-voting Chairman, a non-voting Secretary and a minimum number of 3 (three) voting members possessing the technical and administrative capacities necessary to give an informed opinion on the applications. Each member must be able to demonstrate a working proficiency of the language in which the applications are submitted. All members of the Evaluation Committee, including the observer(s), are obliged to sign a Declaration of Impartiality and Confidentiality (see Annex A04).

Would-be service providers (individually or as part of a consortium) must include with their applications the information required by the published notice and the standard application form (see Annex B04) so that their capacity to fulfil contracts of the type in question can be assessed.

The selection procedure involves:

1.	establishing a long list (see template in Annex B05) summarising all the applications received;

2.	eliminating candidates who are ineligible (see Section 1) or fall into one of the situations described in Section 1;

3.	checking that the candidates' financial situation (financial and economic standing) is sound, as backed up, for example, by balance sheets and turnover for the previous three years (see section 2.11);

4.	verifying the candidates' technical and professional capabilities, for instance by reviewing their average annual staffing levels, the size and professional experience of their management and the main services supplied in the field in question in recent years (see section 2.11).

| ( | The selection must be carried out by applying the selection criteria specified in the contract notice without any modification. |
| --- | --- |

After examination of the responses to the contract notice, the service providers meeting the minimum selection requirements will be short-listed.

| ( | The shortlist should contain a minimum of five candidates. Every contract notice must specify the range of candidates. |
| --- | --- |

If the number of eligible candidates meeting the selection criteria is less than the minimum of five, the Contracting Authority may continue the tender procedure if the real number of candidates is sufficient to ensure genuine competition.

If the number of eligible candidates meeting the selection criteria is greater than the maximum indicated in the contract notice, the relative strengths and weaknesses of the applications of these candidates must be examined to identify the eight most suitable applications, in accordance with the defined selection criteria, for the tender procedure. The results of this examination must be duly justified in the Shortlist Report. This should produce a final shortlist of at most 8 candidates.

| ( | The short-listing process and the final shortlist itself must be fully documented in a Shortlist Report (see template in Annex B06). This and all the application forms received must be retained. |
| --- | --- |

The Shortlist Report and the tender dossier to be sent to short-listed candidates must be submitted to the European Commission. The European Commission retains the right to reject the shortlist. Once a shortlist has been approved by the Contracting Authority and the European Commission, short-listed service providers or consortia are not allowed to form alliances with any other firms or to subcontract to each other for the contract in question.

The Contracting Authority may allow subcontracting with entities other than those on the shortlist provided that the sub-contractor complies with the eligibility conditions set out in Sections 1 and that subcontracting does not account for an excessive proportion of the tender. The tender dossier must stipulate what the proportion is.

All Candidates will be informed simultaneously in writing by the Contracting Authority promptly upon the decision, (see Annex B07). Candidates who are selected will receive a letter of invitation to tender and the tender dossier (see template in Annex B08).

PROCEDURE FOR ESTABLISHING SHORTLISTS

PUBLISH PRIOR INDICATIVE NOTICE (PIN) May be sent to the OJEU, where possible in electronic form and at least 12 days before the intended date of publication to allow translation. Forewarns interested parties of a forthcoming contract notices and may justify shorter deadlines.

To justify shorter deadlines for submission of tenders, a full PIN must be published at least 52 days and not more than a year before the contract notice.

PUBLISH CONTRACT NOTICE Must be sent to the OJEU, where possible in electronic form and at least 12 days before the intended date of publication

Under the restricted procedure, candidates must be given at least 37 days from dispatch of the contract notice to submit standard application forms

EVALUATION COMMITTEE MEETS TO:

1) ESTABLISH LONG LIST Summarises all candidates

2) ELIMINATE ALL CANDIDATES WHICH MUST BE EXCLUDED Apply the grounds for exclusion in Section 1

3) ELIMINATE ALL INELIGIBLE CANDIDATES Apply the eligibility criteria in Section 1

4) IDENTIFY ALL ELIGIBLE CANDIDATES MEETING THE SELECTION CRITERIA If more than the maximum indicated in the contract notice, identify the most suitable If less than 5, continue only if satisfied there is genuine competition

5) PREPARE SHORTLIST REPORT Record the entire short-listing process

6) SHORTLIST ACCORDING TO THE RANGE OF CANDIDATES Send invitation to tender and tender dossier to short-listed candidates Send letters simultaneously to unsuccessful candidates.

### 4.3.3	Drafting and Contents of the Tender Dossier

It is vital that the tender dossier be carefully drafted not only for the proper execution of the contract but also for the sound functioning of the award procedure.

These documents must contain all the provisions and information that candidates invited to tender need to present their tenders: the procedures to follow, the documents to provide, cases of non-compliance, award criteria and their weightings, stipulations regarding subcontracting, etc. It may be desirable for representatives of the final beneficiaries to participate in the tender preparation at an early stage. See Section 2.10.

The Contracting Authority is responsible for drawing up these documents.

The Contracting Authority must submit the tender dossier to the European Commission for approval prior to issue.

The Contracting Authority will send only the short-listed candidates a letter of invitation to tender (see template in Annex B08) accompanied by the tender dossier comprising the following documents:

TENDER DOSSIER CONTENT

| ① | INSTRUCTIONS TO TENDERERS |
| --- | --- |
|  | which must indicate: |
|  | □ the type of contract (i.e., service) |
|  | □ the tender evaluation criteria (and any sub-criteria) and their weightings |
|  | □ the possibility of interviews and the timetable for them |
|  | □ whether variants are authorised |
|  | □ whether subcontracting intentions are to be disclosed |
|  | □ the maximum budget available for the contract |
|  | □ the currency of the tender |
|  | □ the sworn statement to be provided by the tenderers |
|  | See Annex B08 for template. |

| ② | DRAFT CONTRACT AND ANNEXES |
| --- | --- |
|  | See standard format in Annex B09. This includes: |
|  | □ The specific contract conditions which amplify, supplement or derogate from the general conditions, and where they conflict, override them. |
|  | □ The Terms of Reference for the project (which will become an annex of the eventual contract), with a forecast timetable for the contract and forecast dates from which the key experts must be available. See Section 2.10 |
|  | □ An overall structure for the Organisation and Methodology to be provided by the tenderer and which will become an annex of the eventual contract. |
|  | □ A standard format for the summary and CVs of key staff, to be included as an annex of the eventual contract. |
|  | □ The format of the budget (for completion by the tenderer) which will become an annex of the eventual contract. |
|  | □ The General Conditions for service contracts, to be included as an annex of the eventual contract. Changes to the General Conditions are forbidden. |
|  | □ The format for a guarantee from a bank or a similar institution to provide a guarantee for the pre-financing payments. |
|  | □ Any additional contractual information such as special tax arrangements for contracts funded by the European Community. |
|  | The tender dossier must clearly state whether or not the tender must be made with firm, non-revisable prices. If not, the tender dossier must set down the conditions and/or formulae for revision of prices in the course of the contract. The Contracting Authority must then take particular account of: |
|  | (a) the nature of the contract and the economic situation in which the contract is implemented; |
|  | (b) the nature and duration of the tasks and of the contract; |
|  | (c) its financial interests. |
|  | A guarantee will be required to cover any pre-financing payment exceeding €150 000. It will be released as and when the pre-financing payment is deducted from interim payments or payments of balances made to the service provider in accordance with the terms of the contract. |

| ③ | TENDER SUBMISSION FORMAT |
| --- | --- |
|  | The format in which the tender should be submitted. See Annex B09d for template. If this format is not respected, the tender must be rejected. |

### 4.3.4	Award Criteria

Consultancy services contracts are recommended to be awarded to the most economically advantageous tender. To identify such a tender the technical quality and price of the tender may be used as criteria. For contracts funded under pre accession instruments the standard relative weighting of technical and financial characteristics is 80:20.

The technical criteria allow the quality of technical offers to be assessed; it may be divided into several sub criteria, among which the two main types are the methodology and the specific competences of the experts proposed. The methodology must be examined in the light of the terms of reference, for example as regards the approach proposed to fulfil the requirements, the optimum use of the technical and professional resources available in the beneficiary country, the work schedule, the appropriateness of the resources to the tasks, the support proposed for experts in the field etc. Specific competences may be awarded points for such elements as very high qualifications related to the tender, geographical connections with other experts, particular motivation in the requirements of the tender, etc.

Each criterion is allotted a number of points out of 100 distributed between the different sub-criteria. Their respective weightings depend on the nature of the services required and are determined on a case-by-case basis in the tender dossier. For study contracts, the methodology would typically be given a higher weight relative to the CVs than for technical assistance contracts.

The points must be related as closely as possible to the terms of reference describing the services to be provided and refer to parameters that are easy to identify in the tenders and, if possible, quantifiable.

The tender dossier must contain full details of the technical evaluation grid, with its criteria and sub-criteria and their weightings.

### 4.3.5	Additional Information before the Deadline for Submission of Tenders

The tender dossier should be clear enough to avoid candidates invited to tender from having to request additional information during the procedure. If the Contracting Authority, either on its own initiative or in response to the request of a short-listed candidate, provides additional information on the tender dossier, it must send such information in writing to all other short-listed candidates at the same time.

Tenderers may submit questions in writing up to 16 days before the deadline for submission of tenders. The Contracting Authority must reply to all tenderers' questions at least 6 days before the deadline for receipt of tenders.

### 4.3.6	Deadline for Submission of Tenders

Tenders must reach the Contracting Authority at the address and no later than at the date and time shown in the invitation to tender. The period for submission must be sufficient to guarantee the quality of tenders and so permit truly competitive tendering. Experience shows that too short a period prevents candidates from tendering or causes them to submit incomplete or ill-prepared tenders. The deadline for submissions must be at the close of business of a working day in the beneficiary country.

The minimum period between the dispatch of the letter of invitation to tender by the Contracting Authority and the deadline for receipt of tenders is 40 days(less following a full PIN). However, in exceptional cases, this period may be shortened subject to the requirements of the Directive and with prior authorisation from the European Commission.

### 4.3.7	Period of Validity

Tenderers are bound by their tenders for the period specified in the letter of invitation to tender. This period must be sufficient to allow the Contracting Authority to examine tenders, approve the contract award proposal, notify the successful tenderer and conclude the contract. The period of validity of tenders is fixed at 90 days from the deadline for the submission of tenders.

In exceptional cases, before the period of validity expires, the Contracting Authority may ask the tenderers to extend the period for a specific number of days, which may not exceed 40.

The successful tenderer must maintain its tender for a further 60 days from the date of notification of award.

### 4.3.8	Submission of Tenders

Tenders must be submitted preferably in accordance with the double envelope system, i.e., in an outer parcel or envelope containing two separate, sealed envelopes, one bearing the words "Envelope A — technical offer" and the other "Envelope B — financial offer". All parts of the tender other than the financial offer must be submitted in Envelope A.

Any infringement of these rules (e.g., unsealed envelopes or references to price in the technical offer) is to be considered a breach of the rules, and may lead to rejection of the tender.

This system enables the technical offer and the financial offer to be evaluated successively and separately: it ensures that the technical quality of a tender is considered independently of the price.

The outer envelope must bear:

(a)	the address for submission of tenders indicated in the tender dossier;

(b)	the reference of the tender procedure to which the tenderer is responding;

(c)	where applicable, the numbers of the lots being tendered for;

(d)	the words "Not to be opened before the tender-opening session" written in the language of the tender dossier and in the local language;

(e)	the name of the tenderer.

### 4.3.9	The Evaluation Committee

4.3.9.1	Composition

Tenders may be opened and evaluated by an Evaluation Committee, or depending on national practice a panel, appointed by the Contracting Authority. An Evaluation Committee should comprise a non-voting Chairman, a non-voting Secretary and a minimum number of 3 (three) voting members as well as an observer, when so is requested. Every member must be able to demonstrate a working proficiency of the language in which the tenders are submitted. The voting members must possess the technical and administrative capacities necessary to give an informed opinion on the tenders. The same principles apply to a panel.

The Evaluation Committee (i.e., the Chairman, the Secretary and the voting members) must be nominated on a personal basis by the Contracting Authority. The composition of the Evaluation Committee must be submitted for approval to the European Commission. As a general rule, the European Commission nominates an observer to follow all or part of the proceedings of the Evaluation Committee. Prior approval must be sought from the European Commission for the participation of other observers.

The Evaluation Committee members should attend all meetings. Any absence must be recorded and explained in the Evaluation Report.

All voting members of the evaluation committee have equal voting rights. The names and functions of all those involved in the evaluation process must be recorded in the evaluation report.

4.3.9.2	Impartiality and Confidentiality

All members of the Evaluation Committee and any observers must sign a Declaration of Impartiality and Confidentiality (see Annex A04). Any Evaluation Committee member or observer who has a potential conflict of interest due to a link with any tenderer must declare it and immediately withdraw from the Evaluation Committee. He will be excluded from participating further in any capacity in the evaluation meetings.

Any Evaluation Committee member who withdraws from the Evaluation Committee for whatever reason must be replaced (following the standard procedure for appointing members of the Evaluation Committee, as explained in Section 3.1) and the evaluation process must be restarted. Any assessment by a voting member withdrawing from the Committee at whatever stage of the evaluation has to be disregarded.

| ( | Subject to requirements for the prompt notification of award decisions and for de-briefing within 15 days of request, no information about the examination, clarification, evaluation or comparison of tenders or decisions about the contract award can be disclosed before the signature of the contract by the Contracting Authority and the successful tenderer. Any attempt by a tenderer to influence the process in any way (whether by initiating contact with members of the Evaluation Committee or otherwise) will result in the immediate exclusion of its tender from further consideration. |
| --- | --- |

The proceedings of the Evaluation Committee, from the opening of tenders to the conclusion of the work of the Evaluation Committee, are conducted in camera and are confidential.

In order to maintain the confidentiality of the proceedings, participation in the Evaluation Committee meetings is limited to the members of the Evaluation Committee designated by the Contracting Authority and any authorised observers.

The tenders should not leave the room/building in which the committee meetings take place before the conclusion of the work of the Evaluation Committee. They should be kept in a safe place when not in use.

4.3.9.3	Responsibilities of the Evaluation Committee Members

The Chairman is responsible for co-ordinating the evaluation process in accordance with the procedures in this Guide and for ensuring its impartiality and transparency. The voting members of the Evaluation Committee have collective responsibility for the recommendations made by the Committee.

The Secretary to the Committee is responsible for carrying out all administrative tasks connected with the evaluation procedure. These will include:

circulating and collecting the Declarations of Impartiality and Confidentiality;

keeping the minutes of all meetings of the Evaluation Committee and the relevant records and documents; and

registering attendance at meetings and compiling the Evaluation Report and its supporting annexes.

Any request for clarification requiring communication with the tenderers during the evaluation process must be conducted in writing (by fax or letter or, where permitted, by electronic means) and signed by both the Chairman and the Secretary of the Evaluation Committee. Copies of any such communication must be annexed to the Evaluation Report.

If a tender infringes the formal requirements, the Evaluation Committee may use its discretion to decide whether or not it should still be considered during the rest of the evaluation process. Whatever the Evaluation Committee decides, this must be fully recorded and justified in the Evaluation Report.

4.3.9.4	Timetable

The Evaluation Committee should be formed early enough to ensure the availability of the designated members (and any observer nominated by the European Commission, in the case of decentralised ex-ante control) during the period necessary to prepare and conduct the evaluation process. The tender evaluation should be completed as soon as possible.

The duration of the evaluation process should be agreed between members of the Evaluation Committee and the Contracting Authority. The evaluation process must be completed in time to allow the successful tenderer to be notified by the Contracting Authority (after all necessary approvals) within the tender validity period (ie. 90 days) specified in the tender dossier.

### 4.3.10	Stages in the Evaluation Process

4.3.10.1	Receipt and Registration of Tenders

On receiving tenders, the Contracting Authority must register them and provide a receipt for those delivered by hand. The envelopes containing the tenders must remain sealed and be kept in a safe place until they are opened.

The outer envelopes of tenders must be numbered in order of receipt (whether or not they are received before the deadline for submission of tenders).

4.3.10.2	Tender Opening Session

Tender opening will be conducted in a non-public session.

Part 1: Preparatory phase

First meeting of Evaluation Committee:

to be held before starting the actual evaluation;

the tender dossier should have been circulated in advance to the members of the Evaluation Committee.

The Chairman presents the purpose of the tender procedure in general terms.

The Chairman reminds the Committee of the award criteria and weightings specified in the tender dossier, stating that these must be respected without modification. (The selection criteria used in the short-listing of candidates should not be used during the tender evaluation).

The Chairman explains the procedures to be followed by the Evaluation Committee.

Before the tenders are opened, the Chairman of the Committee checks that all members are familiar with the technical evaluation grid set out in the tender dossier to make sure that the tenders will be evaluated by the different members of the Committee in a consistent manner. See Annex B9c3 for the format of an evaluation grid.

The Chairman reminds the Committee of the Contracting Authority’s minimum technical requirements, of the criteria for technical evaluation (80 points), that the financial evaluation will be carried out later as per the tender dossier, and that the weightings given to the technical and financial evaluations will be 0.80 and 0.20 respectively. Other weighting that might have been duly authorised by the EC should be explained if necessary.

Part 2: Compliance with formal requirements

See tender opening checklist in Annex B10.

The following tasks are carried out by the Chairman and Secretary:

Examine and state the condition of outer envelopes before opening them in order of receipt, announcing the name of the tenderer and whether separate envelopes have been used for technical and financial offers. Only tenders contained in envelopes received by the date and time indicated in the tender dossier are considered for evaluation.

Require all members of the Evaluation Committee and any observer(s) to read and sign a Declaration of Impartiality and Confidentiality (see Annex A04).

Open the inner envelope containing the technical offer and mark the tender envelope number on each copy of the technical offer. The front page of each copy of the technical offer must be initialled by the Chairman and the Secretary.

The Chairman and the Secretary must initial the inner envelope containing the financial offer across the seal, marking the tender envelope number on the envelope. This is not opened and must be locked away in a safe place until the financial evaluation takes place, after completion of the technical evaluation.

The Committee must decide whether or not tenders comply with the formal requirements at this stage (i.e., following the opening of the outer envelope and the opening of the technical offer). The Summary of tenders received, which is attached to the Tender Opening Report (see Annex B11) must be used to record the compliance of each of the tenders with the formal requirements. Non-compliant tenders may be rejected. The evaluation committee may decide to ask for missing documents or formal corrections. This decision has to be applied equally to all tenders.

Part 3: Administrative compliance

The Committee checks the compliance of tenders with the instructions given in the tender dossier. The evaluation committee may decide to ask for missing documents or formal corrections. This decision has to be applied equally to all tenders.

Copies of the technical offers are distributed to the Committee members. The originals are locked away for safe keeping.

Each technical offer is examined for compliance with the tender dossier, in particular that:

the documentation is complete;

the language required by the tender dossier has been used;

a declaration of intent, accepting the terms of reference and general conditions, has been signed by the tenderer (i.e., leader and all consortium partners, in the case of a consortium);

each of the key personnel proposed have signed a statement of availability and exclusivity for this tender (see Annex B09);

for consortia: the confirmation of association and designation of a lead company has been signed by all consortium members;

for tenderers intending to subcontract tasks (if permitted by the tender dossier): the tenderer has included a statement regarding the content and extent of subcontracting envisaged, which must be within the limit stated in the tender dossier, and the identity of the sub-contractor.

With the agreement of the other Evaluation Committee members, the Chairman may communicate in writing with tenderers whose submissions require clarification. The evaluation committee may decide to ask for missing documents or formal corrections. This decision has to be applied equally to all tenderers.

| ( | The Chairman must check that no member of the Evaluation Committee has a potential conflict of interest with any of the tenderers (on the basis of the shortlist, the tenders received, consortium members and any identified sub-contractor). Any Evaluation Committee member or observer who has a potential conflict of interest due to a link with any tenderer must declare it and immediately withdraw from the Evaluation Committee. He will be excluded from participating further in any capacity in the evaluation meetings. Any Evaluation Committee member who withdraws from the Evaluation Committee for whatever reason must be replaced (following the standard procedure for appointing members of the Evaluation Committee, as explained in Section 3.1) and the evaluation process must be restarted. |
| --- | --- |

The table included in the Tender Opening Report (see Annex B11) must be used to record the administrative compliance of each of the tenders.

| ( | The Tender Opening Report, which comprises the summary of tenders received and the minutes of the tender opening session, must be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee. The Tender Opening Report must state: □ the date, time and place of the session; □ the persons present; □ the names of the tenderers who have replied within the deadline; □ whether tenders were submitted using the double-envelope system; □ whether the originals were duly signed, and whether technical offers were sent in the requisite number of copies; □ whether any requests for clarification were sent by the Chairman, including copies of the correspondence; □ the names of any tenderers whose tenders were found to be non-compliant at the opening session and the requirement(s) with which their tenders failed to comply; □ the names of any tenderers who withdrew their tenders. |
| --- | --- |

4.3.10.3	Evaluation of Technical Offers

The Committee then examines the technical offers, the financial offers remaining sealed. The Committee members receive copies of the technical offers. When evaluating technical offers, each member awards each offer a score out of a maximum 100 points in accordance with the technical evaluation grid (setting out the technical criteria, sub-criteria and weightings) laid down in the tender dossier (see Section 3.2). Under no circumstances may the Committee or its members change the technical evaluation grid communicated to the tenderers in the tender dossier.

In practice, it is recommended that tenders be scored for a given criterion one after another, rather than scoring each tender for all criteria before moving on to the next. Where the content of a tender is incomplete or deviates substantially from one or more of the technical award criteria laid down in the tender dossier, the tender must be automatically rejected (without being given a score).

| ( | Nationality of experts and sub-contractors: The Evaluation Committee must check at this stage that the nationalities of any experts and sub-contractors identified in the technical offers satisfy the nationality rule in Section 1.3. If the service provider is required by the terms of reference to provide supplies, the Evaluation Committee must verify that the proposed supplies satisfy the Rule of Origin in Section 1.3. |
| --- | --- |

If the tender dossier expressly permits variants, such variants are scored separately.

| ( | Each voting member of the Committee completes an evaluation grid (see Annex B12) to record his assessment of each technical offer in order to establish a general appreciation of strengths and weaknesses of the individual technical offers. |
| --- | --- |

On completion of the technical evaluation, the points awarded by each member are compared. Besides the numerical score, a member must explain the reasons for his choice and defend his scores before the Committee.

The Committee discusses each technical offer and each member awards it a final score. The Committee members may modify their individual evaluation grids as a result of the general discussion on the merits of each offer.

Once discussed, each Evaluation Committee member finalises his evaluation grid on each of the technical offers and signs it before handing it over to the Secretary of the Evaluation Committee. The Secretary must then compile a summary of the comments of the Committee members as part of the Evaluation Report.

| ( | In the case of major discrepancies, a full justification has to be provided by dissenting members during a meeting of the Evaluation Committee. |
| --- | --- |

The example in Annex B12 shows the format of such a summary as part of the Evaluation Report and indicates the level of detail expected. The Secretary calculates the aggregate final score, which is the arithmetical average of the individual final scores.

If interviews were provided for in the tender dossier, the Committee may, after writing up its provisional conclusions and before definitively concluding its evaluation of the technical offers, decide to interview the key members of the team of experts proposed in technically compliant tenders (ie, those which meet the contracting authority’s minimum technical requirements of an average score of 80 points or more in the technical evaluation). In this case the experts are interviewed by the Committee, preferably collectively in the case of a team, at intervals close enough to permit comparison. Interviews must follow a standard format agreed beforehand by the Committee and applied to all experts or teams called to interview.

Tenderers must be given at least 10 days' advance notice of the date and time of the interview. If a tenderer is prevented from attending an interview by force majeure, a mutually convenient alternative appointment is arranged with the tenderer.

On completion of these interviews, the Evaluation Committee, without modifying either the composition or the weighting of the criteria laid down in the technical evaluation grid, decides whether it is necessary to adjust the scores of the experts who have been interviewed. Any adjustments must be substantiated.

This procedure entails considerable costs both for tenderers and the Contracting Authority and should therefore be used with restraint. It must be recorded in the Evaluation Report, which may lead to revision of the initial technical evaluation of the tender. The indicative timetable for these interviews must be given in the tender dossier.

Once the Committee has established each technical offer's average score (the mathematical average of the final scores awarded by each voting member), any tender falling short of the minimum technical requirements of an average technical score of 80 points or more is automatically rejected.

If no tender achieves the technical threshold, the tender procedure is either cancelled or, if justified, turned into a negotiated procedure.

The Committee considers only tenders that have met the technical threshold of 80 points. Of these tenders, the best technical offer is then awarded 100 points. The others receive points calculated using the following formula:

Technical score = (final score of the technical offer in question/final score of the best technical offer) x 100.

| Specimen Tender Evaluation Summary Part 1: Technical Evaluation |
| --- |
|  | Maximum possible score | Tenderer 1 | Tenderer 2 | Tenderer 3 |
| Evaluator A | 100 | 55 | 88 | 84 |
| Evaluator B | 100 | 60 | 84 | 82 |
| Evaluator C | 100 | 59 | 82 | 90 |
| Total | 300 | 174 | 254 | 256 |
| Average score (mathematical average) |  | 174/3 = 58.00 | 254/3 = 84.67 | 256/3 = 85.33 |
| Technical score (actual final score / highest final score) |  | ELIMINATED* | 84.67/85.33 x 100 = 99.22 | 100.00 |
| * Only tenderers with average scores of at least 80 points qualify for the financial evaluation |

The Secretary must record the names of the firms and the results in the Evaluation Report. At this stage, the Chairman may give the Committee members the opportunity to comment, to table objections or to query dissenting opinions. The Chairman should then state for the record the names of those firms which have passed the technical threshold of 80 points and will proceed for financial evaluation.

| ( | Note that all technical offers must be retained by the Contracting Authority, whether or not they achieve this threshold. |
| --- | --- |

4.3.10.4	Evaluation of Financial Offers

Upon completion of the technical evaluation, the envelopes containing the financial offers for tenders which were not eliminated during the technical evaluation are opened and all copies of these financial offers are initialled by Chairman and Secretary of the Evaluation Committee.

The Evaluation Committee has to ensure that the financial offer satisfies all formal requirements. A financial offer not meeting these requirements may be rejected. Any rejection on these grounds will have to be fully justified in the Evaluation Report.

The envelopes containing the financial offers of rejected tenderers must be retained by the Contracting Authority with other documents for the tender. They must remain unopened.

The Evaluation Committee checks that the financial offers contain no arithmetical errors. Any arithmetical errors are corrected without prejudice to the tenderer. Substantial arithmetical errors shall be communicated to the tenderer for its acceptance. If no approval is obtained, such tender shall be rejected.

The total contract value comprises the fees (including employment-related overheads) and the provision for actual expenditure which is specified in the tender dossier. This total contract value is compared with the maximum budget available for the contract.

| ( | Tenders exceeding the maximum budget allocated for the contract may be eliminated. (In the absence of acceptable tenders the Contracting Authority may need to cancel the procedure and start again or move to a negotiated procedure in accordance with Section 3.9 above.) |
| --- | --- |

The Evaluation Committee then proceeds with the financial comparison of the fees (including employment-related overheads) between the different financial offers. The provision for actual expenditure is excluded from the comparison of the financial offers as it was specified in the tender dossier.

The tender with the lowest total fees receives 100 points. The others are awarded points by means of the following formula:

Financial score = (lowest total fees / total fees of the tender being considered) x 100.

| ( | When evaluating financial offers, the Evaluation Committee compares only the total fees. |
| --- | --- |

| Specimen Tender Evaluation Summary Part 2: Financial Evaluation* |
| --- |
|  | Maximum possible score | Tenderer 1 | Tenderer 2 | Tenderer 3 |
| Total fees |  | Eliminated following technical evaluation* | € 951 322 | € 1 060 452 |
| Financial score (lowest total fees/actual total fees X 100) |  |  | 100.00 | 951 322/ 1 060 452 x 100 = 89.71 |
| * Only tenderers with average scores of at least 80 points in the technical evaluation qualify for the financial evaluation. |

4.3.10.5	Conclusions of the Evaluation Committee

The most economically advantageous tender is established by weighing technical quality against price on an 80/20 basis. This is done by multiplying:

the scores awarded to the technical offers by 0.80;

the scores awarded to the financial offers by 0.20.

This weighting is used in principle and may be only modified before launching the tender after proper authorisation of the European Commission in duly justified cases.

| Specimen Tender Evaluation Summary Part 3: Composite Evaluation |
| --- |
|  | Maximum possible score | Tenderer 1 | Tenderer 2 | Tenderer 3 |
| Technical score X 0.80 |  | Eliminated following technical evaluation | 99.22 X 0.80 = 79.38 | 100.00 X 0.80 = 80.00 |
| Financial score X 0.20 |  |  | 100.00 X 0.20 = 20.00 | 89.71 X 0.20 = 17.94 |
| Overall score |  |  | 79.38 + 0.20 = 99.38 | 80.00 + 17.94 = 97.94 |
| Final ranking |  |  | 1 | 2 |
| * Only tenderers with average scores of at least 80 points qualify for the financial evaluation. |

The resulting, weighted technical and financial scores are then added together and the contract is awarded to the tender achieving the highest overall score. It is essential to make the calculations strictly according to the above instructions.

| Specimen Tender Evaluation Summary |
| --- |
|  | Maximum possible score | Tenderer 1 | Tenderer 2 | Tenderer 3 |
| Technical Evaluation |
| Evaluator A | 100 | 55 | 88 | 84 |
| Evaluator B | 100 | 60 | 84 | 82 |
| Evaluator C | 100 | 59 | 82 | 90 |
| Total | 300 | 174 | 254 | 256 |
| Average score |  | 58.00 | 84.67 | 85.33 |
| Technical score |  | Eliminated* | 99.22 | 100.00 |
| Financial Evaluation |
| Total fees |  | Eliminated following technical evaluation* | € 951 322 | € 1 060 452 |
| Financial score |  |  | 100.00 | 89.71 |
| Composite Evaluation |
| Technical score X 0.80 |  | Eliminated following technical evaluation | 99.22 X 0.80 = 79.38 | 100.00 X 0.80 = 80.67 |
| Financial score X 0.20 |  |  | 100.00 X 0.20 = 20.00 | 89.71 X 0.20 = 17.94 |
| Overall score |  |  | 79.38 + 0.20 = 99.38 | 80.00 + 17.94 = 97.94 |
| Final ranking |  |  | 1 | 2 |
| * Only tenderers with average scores of at least 80 points in the technical evaluation qualify for the financial evaluation. |

| ( | As a result of its deliberations, the Evaluation Committee may make any of the following recommendations: □ Award the contract to the tenderer which has submitted a tender: – which complies with the formal requirements and the eligibility rules; – whose total budget is within the maximum budget available for the project; – which meets the minimum requirements of the technical proposal as specified in the tender dossier; and – which is the most economically advantageous tender (satisfying all of the above conditions). □ Cancel the tender procedure in exceptional circumstances, such as: – None of the tenders satisfies the award criteria of the tender procedure; – No tenders achieved the minimum threshold during the technical evaluation; – the total price (comprising both the fees and the provision) of all tenders received exceed the maximum amount available for the contract. |
| --- | --- |

The entire procedure (technical and financial evaluation) is recorded in an Evaluation Report (see template in Annex B12) to be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee. This must submitted to the Contracting Authority, which must decide whether or not to accept its recommendations.

The Contracting Authority must then submit the Evaluation Report together with its recommendation to the European Commission for approval. If there is an award proposal and the European Commission has not already received the original tender of the recommended tenderer and copies of the other tenders, these must be submitted.

At the same time, for any award proposal, a contract dossier including a proposed contract must be prepared on the basis of the recommended tender. It must be submitted to the European Commission for endorsement (agreement to finance the proposed contract).

If the European Commission does not accept the recommendation of the Evaluation Committee and the Contracting Authority, it must write to the Contracting Authority stating the reasons for its decision. The European Commission may also suggest how the Contracting Authority should proceed and give the conditions under which the Authority might endorse a proposed contract on the basis of the tender procedure.

If the European Commission approves the recommendation of the Evaluation Committee, the Contracting Authority will either commence awarding the contract or cancel the tender, as recommended by the Evaluation Committee.

The Evaluation Report is drawn up, dated and kept for future reference. It must contain at least the following:

(a)	the name and address of the Contracting Authority, and the subject and value of the contract or framework contract;

(b)	the names of the candidates or tenderers rejected and the reasons for their rejection;

(c)	the names of the candidates or tenderers to be examined and the reasons for their selection;

(d)	the names of the candidates or service provider proposed and the reasons for that choice and, if known, the proportion of the contract or framework agreement which the service provider intends to subcontract to third parties.

The Contracting Authority will then take its decision giving at least the following:

(a)	its name and address, and the subject and value of the contract or framework agreement;

(b)	the names of the candidates or tenderers rejected and the reasons for their rejection;

(c)	the names of the candidates or tenderers to be examined and the reasons for their selection;

(d)	the names of the candidates or service provider selected and the reasons for that choice by reference to the selection and award criteria announced in advance and, if known, the proportion of the contract or framework agreement which the service provider intends to subcontract to third parties;

(e)	in the case of negotiated procedures, the circumstances referred to in these rules which justify their use;

(f)	where appropriate, the reasons why the Contracting Authority has decided not to award a contract.

The entire evaluation procedure, including notification of the successful tenderer, must be completed while the tenders are still valid. It is important to bear in mind that the successful tenderer might be unable to maintain its tender (for example, because one or more of the key experts are no longer available) if the evaluation procedure takes too long.

| ( | The entire tender procedure is confidential from the drawing-up of the shortlist to the signature of the contract by both parties. The Evaluation Committee's decisions are collective and its deliberations must remain secret. The Committee members and any observers are bound to secrecy. |
| --- | --- |

The Evaluation Report, in particular, is for official use only and may be divulged neither to tenderers nor to any party outside the authorised services of the Contracting Authority, the European Commission and the supervisory authorities (e.g., the European Court of Auditors). It may be given to a competent court under an open court case.

4.3.10.6	Contract Preparation

If the Evaluation Committee recommends the award of a contract to a particular tenderer and the Contracting Authority approves the Evaluation Report, the Contracting Authority must use the standard contract format (see Annex B09) to prepare the proposed contract. All the components of the proposed contract should be available from either the tender dossier or the tender submitted by the recommended tenderer. Only the Special Conditions should need to be completed.

A contract dossier must be prepared using the following structure:

a) Explanatory note using the format in Annex A6 b) Copy of the financing agreement authorising the project c) Copy of the tender announcements (contract forecast, procurement notice and shortlist), Shortlist Report, Tender Opening Report, Evaluation Report, and any other relevant information d) Three copies of the proposed contract, which is based on the standard service contract template (see Annex B09): □ Special conditions (to be completed by the Contracting Authority); □ General conditions for service contracts (standard version in tender dossier); □ Terms of reference (from the tender dossier); □ Organisation and methodology (from the recommended tender); □ List of key experts and their CVs (from the recommended tender); □ Budget breakdown (from the recommended tender); □ Forms and other relevant documents (from the tender dossier and including the financial identification form, financial guarantee template, audit certificate template, as well as, for example, the formats for progress reports and financial reports to be used by the service provider).

| ( | The standard contract annexes for the General conditions and Forms and other relevant documents (see Annex B09) must be reproduced without modification in every service contract. The Special conditions must be completed by the Contracting Authority. |
| --- | --- |

### 4.3.11	Cancelling the Tender Procedure

The Contracting Authority may decide to cancel the tender procedure at any stage, but particularly in the light of the Evaluation Report, if:

the tender procedure has been unsuccessful, i.e., no suitable tender has been received or there is no response at all;

the economic or technical data of the project have been fundamentally altered;

exceptional circumstances or force majeure render normal performance of the contract impossible;

all technically compliant tenders exceed the financial resources available;

there have been irregularities in the procedure, in particular where these have prevented fair competition.

In the event of cancellation of any tender procedure, tenderers must be notified of the cancellation by the Contracting Authority. Such tenderers shall not be entitled to compensation. When the tender procedure is cancelled before the outer envelope of any tender has been opened, the unopened and sealed envelopes must be returned to the tenderers.

### 4.3.12	Award of the Contract

4.3.12.1	Notifying the Successful Tenderer

Before the period of validity of tenders expires, the Contracting Authority notifies the successful tenderer in writing that its tender has been successful (see format of letter in Annex B?), as well simultaneously in writing informing the unsuccessful tenderers.

This notification to the successful tenderer implies that the validity of the successful tender is automatically extended for a period of 60 days from the date of notification of award of the contract. Unless there is challenge of the award decision by any of the unsuccessful tenderers within 15 days from the date of notification, the Contracting Authority sends the contract to the tenderer for signature.

Where a contract is awarded under a financing agreement which had not been concluded at the time the tender procedure was launched, the Contracting Authority must not notify the successful tenderer before the financing memorandum has been concluded.

4.3.12.2	Contract Signature

In preparing the contract for signature, the Contracting Authority must proceed as follows:

1)	Use the contract dossier prepared following the recommendation of the Evaluation Committee.

2)	Sign all copies of the contract.

3)	Send the three signed copies of the contract to the successful tenderer, who must countersign them within 15 days of receipt (and, in any case, before the expiry of the tender validity period) and return two copies to the Contracting Authority together with the advance guarantee required in the contract. If the successful tenderer fails to do this within the specified deadline or indicates at any stage that it is not willing or able to sign the contract, the tenderer cannot be awarded the contract and forfeits its tender guarantee if such is required in the tender dossier. The contract preparation process must be restarted from step 1 with a new contract dossier prepared using the tender which has achieved the next highest score (provided that that tender passed the technical threshold and is within the maximum budget available for the contract).

4)	On receipt of the two signed copies from the contractor, the Contracting Authority sends one to the financial service in charge of payments and the other copy is sent to the European Commission. A copy of the signed contract must be sent to the Project Manager.

| ( | The Contracting Authority and the Service provider must note on the contract the date on which they sign it. The contract takes effect on the date of the later signature. An addendum cannot cover earlier services or enter into force before this date. |
| --- | --- |

4.3.12.3	Publicising the Award of the Contract

As indicated above, the Contracting Authority is required to inform the tenderers of decisions reached concerning the award of the contract, including the grounds for any decision not to award a contract for which there has been competitive tendering or to recommence the procedure.

Once the contract has been awarded, the Contracting Authority must within 48 days prepare a service contract award notice (using the template in Annex B14) and send it to the OJEU for publication. In addition, the Contracting Authority must record all statistical information concerning the contract award procedure including the contract value, the names of the other tenderers and the successful tenderer.

| ( | The Contracting Authority is responsible for preparing the service contract award notice and for submitting it in electronic form to OJEU for publication. The award notice must be sent to OJEU within 48 days from the date of award. |
| --- | --- |

### 4.3.13	Provision and Replacement of Experts

Where the tender procedure involves the provision of technical assistance staff, the service provider is bound to provide the staff specified in the tender. This specification may take various forms.

Whatever the form, the key staff (head of project, long-term experts, project administrator, accountant, etc.) to be provided by the service provider must be identified and named in the contract.

Should a company and/or proposed experts deliberately conceal the fact that all or some of the team proposed in their tender are unavailable from the date specified in the tender dossier for the start of the assignment, they may be excluded from the tender procedure by the Committee.

Should the Contracting Authority learn that such facts have been concealed after the contract has been awarded, it may decide (with the prior approval of the European Commission) to cancel the contract and either recommence the tender procedure or award the contract to the tender ranked second by the Evaluation Committee (provided that that tender achieved the threshold of 80 points in the technical evaluation and is within the maximum budget available for the contract). Such behaviour may lead to a tenderer's exclusion from other contracts funded by the European Community.

However, the contract must not only identify the key staff to be provided but specify the qualifications and experience required of them. This is important if the service provider has to replace staff after the contract has been signed and concluded. This situation may arise before performance of the contract has even begun or while it is in progress.

In both cases, the contractor must first obtain the Contracting Authority's written approval by substantiating its request for replacement. The Contracting Authority has 30 days from the date of receipt of the request in which to seek the approval of the European Commission and reply.

The service provider must, on its own initiative, propose a replacement where:

(a)	a member of staff dies, falls seriously ill or suffers an accident;

(b)	it becomes necessary to replace a member of staff for any other reasons beyond the service provider's control (e.g., resignation etc.).

In the course of performance, the Contracting Authority may also submit a substantiated written request for a replacement where it considers a member of staff incompetent or unsuitable for the purposes of the contract.

Where a member of staff has to be replaced, the replacement must possess at least equivalent qualifications and experience and his remuneration may in no circumstances exceed that of the expert replaced. Where the service provider is unable to provide a replacement possessing equivalent qualifications and/or experience, the Contracting Authority may either terminate the contract, if it feels that its performance is jeopardised, or, if it feels that this is not the case, accept the replacement, in which case the latter's fees are to be negotiated downwards to reflect the proper level of remuneration.

Any additional expenses resulting from the replacement of staff are borne by the service provider. Where an expert is not replaced immediately and some time elapses before the new expert takes up his functions, the Contracting Authority may ask the service provider to assign a temporary expert to the project pending the new expert's arrival or to take other steps to bridge the gap. Whatever the case may be, the Contracting Authority will make no payment for the period of absence of the expert or his replacement (whether temporary or permanent).

## 4.4	Procedures for the Award of Contracts under the EU Threshold

### 4.4.1	Framework Agreements

For short-term, technical assistance contracts with a performance period (i.e., duration of actual services to be provided) of under 12 months, the Contracting Authority may use a Framework Agreement concluded with one or more service providers following a normal restricted or open procedure. The duration of such contracts may not exceed four years, save in exceptional cases justified in particular by the subject of the framework agreement. Contracting Authorities may not make undue use of framework agreement or use them in such a way that the purpose or effect is to prevent, restrict or distort competition. For sectors which are not covered by the Framework Agreement a simplified procedure must be used with a local call for competition.

The Framework Agreement offers access to technical assistance in a much shorter period than the simplified procedures which are the only alternative for this type of contract.

### 4.4.2	Simplified Restricted Procedure

If the Contracting Authority does not wish to use a framework agreement or its use is unsuccessful (e.g., the technical expertise required is not available in the Framework Agreement), the Contracting Authority may award a contract below the EU threshold in accordance with the relevant national legislation or by a simplified restricted procedure, involving a local call for competition and at least three service providers of its choice.

| ( | Note that the simplified restricted procedure requires more time than the procedure to initiate an assignment under the Framework Agreement. |
| --- | --- |

A local call for competition with the purpose of establishing a list of qualified candidates for a certain category of consultant services, from which the Contracting Authority may invite tenders in writing, may be conducted in the following manner:

1)	The publishing of a simplified prior indicative notice once a year with a formal invitation to qualify for certain categories of service contracts falling below the EU threshold. The template in Annex B3 gives the minimum information which must be included in a local advertisement.

2)	Alternatively, in case a certain service category was not covered by the indicative notice above or the number of suitable candidates available is insufficient, the publishing of a specific contract notice with an invitation to qualify. The minimum time limit for submission of applications is 21 days. The template in Annex B3 gives the minimum information which must be included in a local advertisement.

3)	Both types of notices may be published on the website of the Contracting Authority and/or in the official Procurement Bulletin issued by the government, or in another appropriate media.

4)	The list of pre-selected firms shall be established on fair and objective grounds. The appropriate financial and professional background of the candidates should be described in the contract notice. A service provider should also have the right to apply directly to the Contracting Authority at any time.

5)	The candidates should use the application form (see Annex B4bis), which may be submitted by e-mail, fax or by ordinary mail.

The Contracting Authority should invite at least 3 (three) suitable candidates from the list of qualified firms drawing inter alia on responses. The chosen candidates are sent a letter of invitation to tender accompanied by a tender dossier.

Tenders must reach the Contracting Authority at the address and by no later than the date and time shown in the invitation to tender. The chosen candidates must be allowed at least 21 days from the dispatch of the letter of invitation to tender in which to submit their tenders.

Tenders must be sent in two envelopes, one containing the technical offer and the other the financial offer.

Tenders may be opened and evaluated by a committee possessing the requisite technical and administrative capacities. The members of the committee must sign a Declaration of Impartiality and Confidentiality (see Annex A04). After evaluating the tenders, the committee identifies the most economically advantageous tender on the basis of technical quality and price, as described for international tender.

The Contracting Authority may as well require documentary evidence only from the successful tenderer at the stage of awarding rather than to all bidders at the stage of selection.

| ( | The Contracting Authority is entitled to award a contract in the absence of 3 compliant tenders, provided there is at least one fully compliant tender with a technical proposal and financial proposal acceptable to the Contracting Authority. |
| --- | --- |

| ( | The Contracting Authority may award service contracts of a value of €5 000 or less on the basis of a single tender. |
| --- | --- |

| ( | Note that projects must not be split artificially to circumvent the procurement thresholds. |
| --- | --- |

## 4.5	Modifying Service Contracts

Service contracts may need to be modified during their duration if the circumstances affecting project implementation have changed since the initial contract was signed. Contract modifications must be formalised through an addendum to the contract. Such an addendum must be signed by the contracting parties, unless they are explicitly allowed under the conditions of the contract.

Changes of address, changes of bank account, and changes of auditor may simply be notified in writing by the service provider to the Contracting Authority, although this does not affect the right of the Contracting Authority to oppose the service provider's choice of bank account or auditor.

### 4.5.1	General Principles

The following general principles must always be respected:

A service provider's requests for contract modifications should not automatically be accepted by the Contracting Authority. There must be justified reasons for modifying a contract. The Contracting Authority must examine the reasons given and reject requests which have little or no substantiation.

Contracts can only be modified within the lifetime of the contract; modifications cannot be made retroactively.

The purpose of the addendum must be closely connected with the nature of the project covered by the initial contract.

Major changes, such as a fundamental alteration of the Terms of Reference, cannot be made by means of an addendum.

The addendum must not alter the competition conditions prevailing at the time the contract was awarded.

Unit prices, particularly fee rates, must be identical to those in the initial contract, unless the initial contract stipulates otherwise (i.e., there is a price-revision clause).

Any modification extending the period of execution of the tasks must be such that implementation and final payments can be completed before the expiry of the Financing agreement under which the initial contract was financed.

Any modifications which require additional funding must have been foreseen in the Terms of Reference of the initial contract and can only be agreed before the expiry of the financing agreement under which the initial contract was financed. The additional funding must come from the same budget line as that used for the initial contract.

| ( | Under no circumstances can modifications be made to contracts such that the budget of the complementary services exceeds 50% of the budget of the initial contract. |
| --- | --- |

| ( | Requests for contract modifications to service contracts must be made (by one contracting party to the other) allowing at least 30 days for the addendum to be signed before the end of the period of execution of the initial contract. |
| --- | --- |

### 4.5.2	Preparing an Addendum

In preparing an addendum, the Contracting Authority must proceed as follows:

1)	Use the standard template for an addendum (see Annex A7):

| ( | All references in the proposed addendum to article numbers and/or annexes to be modified must correspond to those in the initial contract. |
| --- | --- |

Any addendum modifying the budget must include a replacement budget showing how the full budget breakdown of the initial contract has been modified by this addendum (and any previous addenda). The following column headings should be used:

| Budget Item | Initial contract budget | Addendum 1 | (Addendum 2…) | Revised budget |
| --- | --- | --- | --- | --- |

| ( | If the budget is modified by the proposed addendum, the payment schedule must also be modified accordingly, taking into account any payments already made in the course of the contract. The payment schedule must not be modified unless either the budget is being modified or the contract is being extended. |
| --- | --- |

2)	Prepare a dossier comprising the following items:

a) Explanatory note (see template in Annex A6) providing a technical and financial justification for making the modifications in the proposed addendum b) Copy of the service provider's request for (or agreement to) the proposed modifications c) Copy of the financing agreement authorising the project d) Copy of the initial contract and any subsequent addenda e) Copy of the initial tender announcements (contract forecast, procurement notice and shortlist), Shortlist Report, Tender Opening Report, Evaluation Report, and any other relevant information f) Three copies of the proposed addendum, which is based on the standard addendum template (see Annex A7) and includes any revised annexes.

4)	Send the three signed copies of the addendum to the service provider, who must countersign them within 30 days of receipt and return three copies to the Contracting Authority together with any financial guarantee required in the addendum.

5)	On receipt of the two signed copies from the contractor, the Contracting Authority sends one to the financial service in charge of payments and the other to the European Commission. A copy of the signed addendum must be sent to the Project Manager.

| ( | The Contracting Authority and the Service provider must note on the addendum the date on which they sign it. The addendum takes effect on the date of the later signature. An addendum cannot cover earlier services or enter into force before this date. |
| --- | --- |

Section 5	Supply contracts

5.1	Introduction

Supply contracts cover the purchase, leasing, rental or hire purchase, with or without option to buy, of products. The contract may, as an incidental matter, include sitting and installation operations necessary to prepare products to be used. Supply contracts may also include the provision of maintenance services provided that the total value of those services does not exceed the value of the products themselves. It may include training on the use of equipment under the same conditions.

"Supplier" describes any natural or legal person, public entity or group thereof who offers supplies in the market. A supplier who has submitted a tender is known as a "tenderer".

The Contracting Authority, which is always specified in the contract notice, is the authority as defined in the glossary of terms (Annex A01) empowered to conclude the contract. Supply contracts are concluded by the Contracting Authority designated in a financing agreement, i.e., the government or an entity of the beneficiary country with legal personality with which the European Commission establishes the financing agreement.

The Contracting Authority must submit the tender dossiers to the European Commission for approval prior to issue. The Contracting Authority must submit procurement notices and award notices to the European Commission for publication.

On the basis of decisions thus approved and in close consultation with the European Commission, the Contracting Authority is responsible for launching tender procedures, receiving tenders, chairing tender-examination sessions and deciding on the results of tender procedures. The Contracting Authority submits the results of the tender examination and the contract award proposal to the European Commission for approval. Once it has received approval, it signs the contracts and notifies the European Commission accordingly. As a general rule, the European Commission will be represented when tenders are opened and evaluated and must always be formally invited.

## 5.2	Procurement Procedures

### 5.2.1	Contracts above the Threshold of the Directive

5.2.1.1	Open Procedure

The method recommended for awarding supply contracts funded under pre accession instruments is an open procedure following publication of a contract notice.

5.2.1.2	Restricted Procedure

When it is more appropriate to the characteristics of the contract to use a restricted procedure, this procedure shall be used following publication of a contract notice. Section 4.3.1 will apply mutatis mutandis.

5.2.1.3	Negotiated Procedure

Supply contracts may be awarded by a negotiated procedure with prior publication of a contract notice in the following exceptional circumstances:

(a)	in the event of irregular tenders or tenders which are unacceptable under national provisions compatible with the Directive, in response to an open or restricted procedure insofar as the original terms of the contract are not substantially altered.

(b)	when the nature of the supplies or the risks attaching thereto do not permit prior overall pricing.

Supply contracts may be awarded by a negotiated procedure without prior publication of a contract notice in the following exceptional circumstances:

(a)	Where an open or restricted procedure has been unsuccessful, that is where no tenders or no applications have been submitted, provided the original terms of the contract are not substantially altered and the principle of equal treatment is observed.

(b)	When for technical or artistic reasons, or for reasons connected with the protection of exclusive rights, the contract may only be awarded to a particular supplier.

(c)	Insofar as strictly necessary when, for reasons of extreme urgency brought about by events which the Contracting Authorities could not have foreseen and which can in no way be attributed to them, the time-limit for the open, restricted or negotiated procedure with publication of a contract notice cannot be met.

Operations carried out in crisis situations as referred to in Article 168(2) of the Implementing Rules are considered to satisfy the test of extreme urgency.

(d)	For additional deliveries by the original supplier intended either as a partial replacement of normal supplies or installations or as the extension of existing supplies or installations, where a change of supplier would oblige the Contracting Authority to acquire equipment having different technical characteristics which would result in either incompatibility or disproportionate technical difficulties in operation and maintenance; the length of such contracts as well as that of recurrent contracts may not, as a general rule, exceed three years.

The Contracting Authority must seek prior approval from the European Commission to use the negotiated procedure.

Where the Contracting Authority uses a negotiated procedure with or without publication of a contract notice, it must prepare a report justifying the manner in which the negotiations were conducted and the basis for the contract award decision resulting from these negotiations. The procedures described in Section 1 must be followed by analogy, with the Report being included in the contract dossier.

### 5.2.2	Contracts under the EU Threshold

Contracts below the EU threshold may be awarded by a local open procedure, involving a local call for competition (see 5.4). The national legislation may provide for the same provisions as for contracts over the thresholds or lay down simplified procedures.

## 5.3	Procedures for Contracts above the EU Threshold

### 5.3.1	Publicity

In order to ensure the widest possible publicity, every contract funded under Community pre accession instruments shall be the subject of a Prior Indicative Notice (PIN) as well as a contract notice.

In addition to increasing the prospect of achieving better value from increased competition, dispatch of a PIN to the OJEU will enable the contracting authority to take advantage of shorter minimum timescales for the receipt of tenders.

The model forms in Annex C for PINs, contract notices and award notices are based on the standard forms which are mandatory for contracts above the threshold and should be completed using the EU reference nomenclature applicable to public contracts (CPV).

5.3.1.1 Publication of PINs

The PIN should set out the estimated total value of contracts, by product area, which the contracting authority intends to award during a budgetary year where the total value of such contracts is equal to or greater than €750 000. It should be sent to the Office for Official Publications of the European Union (OJEU) as early as possible in the budgetary year, (see template in Annex C01), where possible in electronic form.

The publication of a PIN does not bind the contracting authority to finance the contracts proposed and suppliers are not expected to submit applications at this stage.

5.3.1.2	Publication of Contract Notices

In addition to any PIN, all supply contracts above the EU threshold must also be the subject of a contract notice published in the Official Journal of the European Union. Where possible, the contract notice should be dispatched in electronic form.

The European Commission is responsible for publication in the Official Journal of the European Union, while, if the procurement notice is also published locally, the Contracting Authority must arrange local publication directly. If the contract notice is also published locally, it must not be published before dispatch to the OJEU, it must not contain information other than that contained in the OJEU notice and must say when the OJEU notice was dispatched.

The contract notice must identify clearly, precisely, and completely what the subject of the contract is and who the Contracting Authority is. It must provide would-be suppliers with the information they need to determine their capacity to fulfil the contract in question. (See template in Annex C02)

The tender dossier for the contract in question is sent to suppliers requesting it by the Contracting Authority.

### 5.3.2	Drafting and Contents of the Tender Dossier

It is vital that tender documents be carefully drafted not only for the proper execution of the contract but also for the sound functioning of the award procedure.

These documents must contain all the provisions and information that tenderers need to present their tenders: the procedures to follow, the documents to provide, cases of non-compliance, award criteria, etc. It may be desirable for representatives of the final beneficiaries to participate in the tender preparation at an early stage (See Section 2.10 for preparing Technical Specifications).

Technical specifications must afford equal access for candidates and tenderers and not have the effect of creating unjustified obstacles to competitive tendering. They define the characteristics required of a product, service or material or work with regard to the purpose for which they are intended by the Contracting Authority, such as quality levels, environmental performance levels, design for all requirements (including accessibility for disabled persons) and conformity assessment, performance, use of the product, safety or dimensions, including requirements relevant to the product as regards the name under which the product is sold, terminology, symbols, testing and test methods, packaging, marking and labelling, user instructions, production processes and methods and conformity assessment procedures.

Given the technical complexity of many supply contracts, the preparation of the tender dossier - particularly the Technical Specifications - may require the assistance of one or more external technical specialist(s) who must be recruited by the Contracting Authority with the prior approval of the European Commission. Each such specialist must sign a Declaration of Objectivity and Confidentiality (see Annex A3).

As with Terms of Reference for service contracts, particular attention must be paid to the preparation of the Technical Specifications for the supplies tendered. These are the key to successful procurement and a sound supply contract and project.

The Technical Specifications indicate — where applicable, lot by lot — the exact nature and performance characteristics of the supplies. Where applicable, they also specify delivery conditions and installation, training and after-sales service.

It is essential that the performance characteristics correspond to the intended purpose. If there needs to be a clarification meeting or site visit to clarify technical requirements at the site where supplies are to be installed, this should be specified in the instructions to tenderers, together with details of the arrangements.

The purpose of the Technical Specifications is to define the required supplies precisely. The minimum quality standards, defined by the Technical Specifications, will enable the Contracting Authority or its evaluation committee to determine which tenders are technically compliant.

Where the criterion for award is that of the most economically advantageous tender, contracting authorities may authorise tenderers to submit variants. Contract notices must indicate whether or not tenderers may submit tenders for 'variant solutions': variants will not be authorised without this indication. The Contracting Authority must clearly state in the tender dossier the minimum specifications to be respected by the variants and any specific requirements for their presentation. Where variants are allowed by the tender dossier, the Contracting Authority may take them into account when:

they are submitted in accordance with any specific requirements for the submission of variants; and

they meet the technical specifications required by the tender dossier, attaining at least the minimum quality and performance required.

| ( | Unless justified by the subject-matter of the contract, technical specifications shall not refer to a specific make or source, or a particular process, or to trade marks, patents, types or a specific origin or production with the effect of favouring or eliminating certain undertakings or certain products. Such reference shall be permitted on an exceptional basis, where a sufficiently precise and intelligible description of the subject-matter of the contract by other means is not possible; then such reference shall be accompanied by the words "or equivalent". |
| --- | --- |

The Contracting Authority must submit the tender dossier to the European Commission for approval prior to issue.

The tender dossier must contain the following documents:

TENDER DOSSIER CONTENT

| ① | INSTRUCTIONS TO TENDERERS |
| --- | --- |
|  | which must indicate: |
|  | □ The type of contract (i.e., supply). |
|  | □ The selection and award criteria and the rules for applying them. |
|  | □ The grid to be used to evaluate the tenders. Given the wide variety of supplies and their technical nature, the grid must be individually developed for each tender in a YES/NO format to allow clear assessment whether or not the offer responds to the Technical Specifications. If necessary, the relative weighting of the award criteria must then be established as the basis for assessing which tender is the most economically advantageous. |
|  | □ Whether variants are authorised. |
|  | □ Whether subcontracting intentions are to be disclosed. |
|  | □ The currency of the tender. |
|  | □ The format to be used by a bank or similar institution to provide a tender guarantee (1 per cent of the bid value) |
|  | See Annex C04 for template. |

| ② | DRAFT CONTRACT AND ANNEXES |
| --- | --- |
|  | See standard format in Annex C04. This includes: |
|  | □ The specific contract conditions which amplify, supplement or derogate from the general conditions, and where they conflict, override them. |
|  | □ The technical annexes, containing any plans and the Technical Specifications, as well as a provisional timetable for performance. |
|  | □ The format of the budget (for completion by the tenderer). |
|  | □ The General Conditions for supply contracts, to be included as an annex of the eventual contract. Changes to the General Conditions are forbidden. |
|  | □ The formats to be used by a bank or similar institution to provide guarantees for: |
|  | – payment of advances, and |
|  | – performance (10 per cent of the contract value) |
|  | □ Any additional contractual information such as special tax arrangements for contracts funded by the European Community. |
|  | The tender documents must clearly state whether a firm, non-revisable price must be quoted. If that is not the case, they must lay down the conditions and/or formulas for revision of prices during the lifetime of the contract. In such cases the Contracting Authority must take particular account of: |
|  | (a) the object of the procurement procedure and the economic situation in which it is taking place; |
|  | (b) the type of tasks and contract and their duration; |
|  | (c) its financial interests. |
|  | A guarantee is required in return for the payment of pre-financing exceeding €150 000. It will be released as and when the pre-financing is deducted from interim payments or payments of balances made to the contractor in accordance with the terms of the contract. |

| ③ | TENDER SUBMISSION FORMAT |
| --- | --- |
|  | The format in which the tender should be submitted. See Annex C04 for template. The standard content comprises the tender dossier and the actual tender of the tenderer. The technical and financial offers must both be submitted in a single, sealed envelope or packet. The technical offer must satisfy the Technical Specifications in all respects. The financial offer must be presented in the standard format to facilitate comparison of the financial offers. If this format is not respected, the tender will be rejected. |

### 5.3.3	Selection Criteria

The selection criteria concern the tenderer's capacity to execute similar contracts. They are used in admitting tenderers under the open procedure and in selecting participants in others.

The selection procedure involves:

1.	eliminating candidates who are ineligible (see Section 1.3] or fall into one of the situations described in Section 1.7;

2.	checking that the candidates' financial situation (financial and economic standing) is sound, as backed up, as a general rule, by appropriate statements from banks; by balance sheets or extracts from the balance-sheets, where publication of the balance-sheet is required under the law of the country in which the economic operator is established;  or by turnover for a maximum of previous three financial years available, depending on the date on which the undertaking was set up or the economic operator started trading, as far as the information on these turnovers is available (see Volume I, Sections 2.11);

3.	verifying the candidates' technical and professional capabilities, for example by looking at their main supplies provided in the field in question in recent years; a description of the technical facilities and measures used for ensuring quality and their study and research facilities; samples, descriptions and/or photographs of products, the authenticity of which must be certified if the contracting authority so requests; or certificates drawn up by official quality control institutes or agencies of recognised competence attesting the conformity of products clearly identified by references to specifications or standards (see Section 2.10).

The selection criteria specified in the annexes to this guide are given by way of illustration and should be adapted to the nature, cost and complexity of the contract.

If, for any valid reason, the tenderer or candidate is unable to provide the references required by the Contracting Authority, he may prove his economic and financial capacity by any other means which the Contracting Authority considers appropriate. Where the services or products to be supplied are complex or, exceptionally, are required for a special purpose, evidence of technical and professional capacity may be secured by means of a check carried out by the contracting authority or on its behalf by a competent official body of the country in which the supplier is established, subject to that body's agreement. Such checks shall concern the supplier's technical capacity and production capacity and, if necessary, its study and research facilities and quality control measures.

The criteria should be precise, non-discriminatory and not prejudicial to fair competition. All criteria specified in the tender dossier must be applied as such and cannot in any case be modified during the procedure. The technical evaluation will be based on the evaluation grid published in the tender dossier, which must not be modified in any way during the evaluation process. Given the wide variety of supplies and their technical nature, the grid must be individually developed for each tender in a YES/NO format to allow clear assessment whether or not the offer responds to the technical requirements of the tender dossier. See example in Annex C04.

5.3.4 	Award criteria

The criteria on which the contracting authorities base the award of public contracts are either:

(a)	when the award is made to the tender most economically advantageous from the point of view of the contracting authority, various criteria linked to the subject-matter of the public contract in question, for example, quality, price, technical merit, aesthetic and functional characteristics, environmental characteristics, running costs, cost-effectiveness, after-sales service and technical assistance, delivery date and delivery period or period of completion, or

(b)	the lowest price only.

When the award is made to the most economically advantageous tender, the contracting authority must specify in the contract notice or in the contract documents the relative weighting which it gives to each of the criteria chosen to determine the most economically advantageous tender.

### 5.3.4	Additional Information during the Procedure

The tender dossier should be clear enough to avoid tenderers having to request additional information during the tender procedure. If the Contracting Authority, either on its own initiative or in response to a request from a tenderer, provides additional information on the tender dossier, it must send such information in writing to all other tenderers at the same time.

The deadline for the submission of tenders may be extended to allow tenderers to take account of the changes.

| ( | If the tender has a particularly complex technical content, the Contracting Authority may organise a clarification meeting or site visit. This meeting must be announced in the tender dossier and must take place at least 21 days before the expiry of the deadline. All costs of attending such a meeting must be met by the tenderers. Visits by individual companies during the tender period cannot be permitted unless clarification meetings and/or site visits have been specifically scheduled for all tenderers. |
| --- | --- |

Provided that it has been requested in good time, additional information relating to the specifications and any supporting documents shall be supplied by the contracting authorities or competent departments not later than six days before the deadline fixed for the receipt of tenders.

### 5.3.5	Deadline for the Submission of Tenders

Tenders must reach the Contracting Authority at the address and, at the very latest, the date and time indicated in the tender dossier. The period for submission must be sufficient to guarantee the quality of tenders and so permit truly competitive tendering.

Experience shows that too short a period prevents candidates from tendering or causes them to submit incomplete or ill-prepared tenders. The deadline for submissions must fall on a working day in the beneficiary country and be combined with the tender-opening session where applicable.

Under the open procedure, the minimum time-limit for the receipt of tenders is 52 days from the date on which the contract notice was sent to the OJEU. Where a PIN has been published, that minimum deadline may be reduced to 36 days from the date on which the contract notice was sent. However, in exceptional cases, a shorter deadline of not less than 22 days may be allowed. The shortened time-limits are permitted, provided that the PIN has included all the information required for the contract notice in Annex C02, insofar as that information is available at the time the notice is published and that the prior information notice was sent for publication between 52 days and 12 months before the date on which the contract notice was sent.

3.	In the case of restricted procedures, negotiated procedures with publication of a contract notice:

(a)	the minimum time-limit for receipt of requests to participate is 37 days from the date on which the contract notice is sent;

(b)	in the case of restricted procedures, the minimum time-limit for the receipt of tenders is 40 days from the date on which the invitation is sent. 4. Where a PIN has been published, that minimum deadline may be reduced to 36 days from the date on which the invitation to tender was sent in restricted procedures. However, in exceptional cases, a shorter deadline of not less than 22 days may be allowed and with the prior authorisation of the European Commission. The shortened time-limits are permitted, provided that the PIN has included all the information required for the contract notice in Annex C02, insofar as that information is available at the time the notice is published and that the prior information notice was sent for publication between 52 days and 12 months before the date on which the contract notice was sent.

### 5.3.6	Period of Validity

Tenderers are bound by their tenders for the period specified in the tender dossier. This period must be sufficient to allow the Contracting Authority to examine the tenders, take the contract award decision, notify the successful tenderer and conclude the contract. The period of validity of tenders is fixed at 90 days from the deadline for the submission of tenders.

In exceptional cases, before the period of validity expires, the Contracting Authority may ask the tenderers to extend the period for a specific number of days, which may not exceed 40.

The successful tenderer must maintain its tender for a further 60 days from the date of notification of award.

### 5.3.7	Submission of Tenders

Each technical and financial offer must be placed in a single sealed envelope, itself placed in a package or outer envelope. The inner envelope must bear:

(a)	the address indicated in the tender documents for the submission of tenders;

(b)	the reference to the call for tenders to which the tenderer is responding;

(c)	where appropriate, the numbers of the lots for which a tender is being submitted;

(d)	the words "Not to be opened before the tender-opening session" written in the language of the tender dossier and in the local language;

(e)	the name of the tenderer.

### 5.3.8	The Evaluation Committee

5.3.8.1	Composition

Tenders are to be opened and evaluated in accordance with national legislation, compatible with the Directive. This might involve a formal Evaluation Committee or panel appointed by the contracting authority. Where tenders are opened and evaluated by an Evaluation Committee appointed by the Contracting Authority, the Committee should comprise a non-voting Chairman, a non-voting Secretary and a minimum of 3 voting members. Every member must be able to demonstrate a working proficiency in the language in which the tenders are submitted. The voting members must possess the technical and administrative capacities necessary to give an informed opinion on the tenders.

The Evaluation Committee (i.e., the Chairman, the Secretary and the other voting members) must be nominated on a personal basis by the Contracting Authority. The composition of the Evaluation Committee must be submitted for approval to the European Commission. The European Commission may nominate an observer to follow all or part of the proceedings of the Evaluation Committee. The observer may be an independent expert. Prior approval must be sought from the European Commission for the participation of other observers.

The same principles should apply to a panel appointed by the Contracting Authority.

The Evaluation Committee members should attend all meetings. Any absence must be recorded and explained in the Evaluation Report.

All voting members of the Evaluation Committee have equal voting rights. The names and functions of all those involved in the evaluation process must be recorded in the Evaluation Report.

5.3.8.2	Impartiality and Confidentiality

All members of the Evaluation Committee and any observers must sign a Declaration of Impartiality and Confidentiality (see Annex A04). Any Evaluation Committee member or observer who has a potential conflict of interest due to a link with any tenderer must declare it and immediately withdraw from the Evaluation Committee. He will be excluded from participating further in any capacity in the evaluation meetings.

Any Evaluation Committee member who withdraws from the Evaluation Committee for whatever reason must be replaced (following the standard procedure for appointing members of the Evaluation Committee, as explained in Section 3.1) and the evaluation process must be restarted.

Any assessment by a voting member withdrawing from the Committee at whatever stage of the evaluation has to be disregarded.

| ( | Subject to requirements for the prompt notification of award decisions and for de-briefing within 15 days of request, no information about the examination, clarification, evaluation or comparison of tenders or decisions about the contract award can be disclosed before the signature of the contract by the Contracting Authority and the successful tenderer. Any attempt by a tenderer to influence the process in any way (whether by initiating contact with members of the Evaluation Committee or otherwise) will result in the immediate exclusion of its tender from further consideration. |
| --- | --- |

Apart from the tender opening session, the proceedings of the Evaluation Committee are conducted in camera and are confidential.

In order to maintain the confidentiality of the proceedings, participation in the Evaluation Committee meetings is strictly limited to the members of the Evaluation Committee designated by the Contracting Authority and any authorised observers.

The tenders should not leave the room/building in which the committee meetings take place before the conclusion of the work of the Evaluation Committee. They should be kept in a safe place when not in use.

5.3.8.3	Responsibilities of the Evaluation Committee Members

The Chairman is responsible for co-ordinating the evaluation process and for ensuring its impartiality and transparency. The voting members of the Evaluation Committee have collective responsibility for decisions taken by the Committee and its recommendation on the award of the contract.

The Secretary to the Committee is responsible for carrying out all administrative tasks connected with the evaluation procedure. These will include:

circulating and collecting the Declarations of Impartiality and Confidentiality;

keeping the minutes of all meetings of the Evaluation Committee and the relevant records and documents;

registering attendance at meetings and compiling the Evaluation Report and its supporting annexes.

Any request for clarification requiring communication with the tenderers during the evaluation process must be conducted in writing (by fax or letter or, where permitted, by electronic means) and signed by both the Chairman and the Secretary of the Evaluation Committee. Copies of any such communication must be annexed to the Evaluation Report.

If a tender infringes the formal requirements, the Evaluation Committee may use its discretion to decide whether or not it should still be considered during the rest of the evaluation process. Whatever the Evaluation Committee decides, this must be fully recorded and justified in the Evaluation Report.

5.3.8.4	Timetable

The Evaluation Committee should be formed early enough to ensure the availability of the designated members during the period necessary to prepare and conduct the evaluation process. The tender evaluation should be completed as soon as possible.

The duration of the evaluation process should be agreed between members of the Evaluation Committee and the Contracting Authority. The evaluation process must be completed in time to allow the successful tenderer to be notified by the Contracting Authority (after all necessary approvals) within the tender validity period (i.e., 90 days) specified in the tender dossier.

### 5.3.9	Stages in the Evaluation Process

5.3.9.1	Receipt and Registration of Tenders

On receiving tenders, the Contracting Authority must register them and provide a receipt for those delivered by hand. The envelopes containing the tenders must remain sealed and be kept in a safe place until they are opened.

The outer envelopes of tenders must be numbered in order of receipt (whether or not they are received before the deadline for submission of tenders).

5.3.9.2	Preparatory Meeting

First meeting of Evaluation Committee:

to be held before the tender opening session;

the tender dossier should have been distributed in advance to the members of the Evaluation Committee.

The Chairman presents the purpose of the tender procedure in general terms.

The Chairman reminds the Evaluation Committee of the selection and award criteria specified in the tender dossier, stating that these must be respected without modification.

The Chairman explains the procedures to be followed by the Evaluation Committee.

Before the tenders are opened, the Chairman of the Committee checks that all members are familiar with the evaluation criteria set out in the tender dossier to make sure that the tenders will be evaluated by the different members of the Committee in a consistent manner. The Chairman must then ensure that the voting members are familiar with the relative weighting of the award criteria and the means to apply them.

5.3.9.3	Tender Opening Session

The purpose of the tender-opening session is to check that the tenders are complete, that the requisite tender guarantee has been provided, that the documents have been duly signed and that the tenders are generally in order.

| ( | The tender opening session may be a formal, public process. The Evaluation Committee opens the tenders in public at the place and time fixed in the tender dossier. The following are announced at the tender-opening session: the names of the tenderers, the tender prices, the provision of the requisite tender guarantee and any other formality which the Contracting Authority thinks appropriate. |
| --- | --- |

The European Commission must be informed of the tender opening session. It may be represented as an observer at the tender-opening session and receive a copy of each tender.

Representatives of the tenderers may attend a public opening session if such a session is held. The minutes of this meeting must be recorded separately and may be made available to the tenderers on request.

All members of the Evaluation Committee and any observers are required to read and sign a Declaration of Impartiality and Confidentiality (see Annex A4).

See tender opening checklist in Annex C5 for the detailed formalities to be carried out by the Chairman with the assistance of the Secretary, as summarised below.

The following tasks are carried out by the Chairman and Secretary:

Examine and state the condition of outer envelopes before opening them in order of receipt, announcing the name of the tenderer. Only tenders in envelopes received by the date and time indicated in the tender dossier are considered for evaluation.

Initial the front page of each document and all pages of the financial offer.

The Committee must decide whether or not tenders comply with the formal requirements. The Summary of tenders received, which is attached to the Tender Opening Report (see Annex C06) must be used to record the compliance of each of the tenders with the formal requirements. The tenders not considered for further evaluation must be kept by the Contracting Authority, together with the other tenders — the associated guarantees may be returned to the tenderers on request.

| ( | The Tender Opening Report, which comprises the Summary of tenders submitted and the minutes of the tender opening session, must be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee. It may be made available to the tenderers upon request. The Tender Opening Report must state: □ the date, time and place of the session; □ the persons present; □ the names of the tenderers who have replied within the deadline; □ whether the originals of the tenders were duly signed, and whether technical offers were sent in the requisite number of copies; □ the names of any tenderers whose tenders were found to be non-compliant at the opening session and the requirement(s) with which their tenders failed to comply; □ the names of any tenderers who withdrew their tenders; □ any declarations made by the tenderers. |
| --- | --- |

5.3.9.4	Evaluation of Technical Offers

It is obligatory that the Evaluation Committee uses the evaluation grid published in the tender dossier.

Part 1: Administrative compliance

Before conducting a detailed evaluation of the tenders, the Contracting Authority checks that they comply with the essential requirements of the tender dossier.

A tender is deemed to comply if it satisfies all the conditions, procedures and specifications in the tender dossier without substantially departing from or attaching restrictions to them. Substantial departures or restrictions are those which affect the scope, quality or performance of the contract, differ widely from the terms of the tender dossier, limit the rights of the Contracting Authority or the tenderer's obligations under the contract or distort competition for tenderers whose tenders do comply.

Tenders which do not substantially comply with the tender dossier may be rejected by the Contracting Authority and may not subsequently be made to comply by undergoing corrections or having discrepancies or restrictions removed. The evaluation committee may decide to ask for missing documents or formal corrections. This decision has to be applied equally to all tenders.

Copies of the technical offers are distributed to the Committee members. The originals are locked away for safe keeping.

Each technical offer is examined for compliance with the tender dossier, in particular that:

the documentation is complete;

the language required by the tender dossier has been used;

the tenderer has initialled the front page of both the Technical Specifications and General Conditions;

for consortia: the confirmation of association and designation of a lead company has been signed by all consortium members;

for tenderers intending to subcontract tasks: the tenderer has included a statement regarding the content and extent of subcontracting envisaged and, if known, the names of the proposed sub-contractors.

With the agreement of the other Evaluation Committee members, the Chairman may communicate in writing with tenderers whose submissions require clarification, offering them the possibility to respond within an acceptable time limit. The evaluation committee may decide to ask for missing documents or formal corrections. This decision has to be applied equally to all tenderers.

| ( | The Chairman must check that no member of the Evaluation Committee has a potential conflict of interest with any of the tenderers (on the basis of the shortlist, the tenders received, consortium members and any identified subcontractor). Any Evaluation Committee member or observer who has a potential conflict of interest due to a link with any tenderer must declare it and immediately withdraw from the Evaluation Committee. He will be excluded from participating further in any capacity in the evaluation meetings. Any Evaluation Committee member who withdraws from the Evaluation Committee for whatever reason must be replaced (following the standard procedure for appointing members of the Evaluation Committee, as explained in Section 3.1) and the evaluation process must be restarted. |
| --- | --- |

The administrative compliance of each of the tenders must be recorded in the Evaluation Report (see Annex C7).

Part 2: Technical compliance of tenders

The detailed evaluation of the tenders takes place after checking that the tenders satisfy the formal requirements of tender submission. The criteria to be applied are those published in the tender dossier and, accordingly, the evaluation grid included in the tender dossier must be used. Under no circumstances may the Committee or its members change the evaluation grid communicated to the tenderers in the tender dossier.

The purpose of this evaluation is to assess whether or not the competing tenders meet the minimum technical requirements and eligibility criteria. As part of the technical evaluation, the Evaluation Committee analyses the commercial aspects, and, where applicable, the training component of the tenders to determine whether they satisfy the requirements set in the tender dossier. The results are recorded in a YES/NO grid for all elements specified in the tender dossier. No scoring method should be used. If the tender is divided into lots, the evaluation should be carried out lot-by-lot.

| ( | Rule of origin: All tenders must satisfy the rule that the goods to be supplied originate in EU Member States and/or the countries and territories of the regions covered and/or allowed by the Regulation or other instruments governing the programme under which the contract is being financed. Evidence to this effect is asked for in the instructions to tenderers. The tenderer must provide a declaration that the goods tendered comply with the origin requirement and specify the respective country of origin. In case of any doubt as to the origin of goods, additional information must be requested. Should doubts persist, the advice of the European Commission should be sought. The tenderer will be required to provide, prior to the signature of the contract, proof of origin in the form of a Certificate of Origin or other official documentation as prima facie evidence. Where the provision of a Certificate of Origin is not possible (in many countries these are only issued against presentation to the Chamber of Commerce of commercial invoices), the tenderer can in these cases submit its own declaration. The official Certificates of Origin must then be submitted with the first invoice. Failing this, the Contracting Authority cannot release any funds to the contractor. The rule of origin applies to all items tendered and supplied. Therefore, it is insufficient that only a certain percentage of the goods tendered and supplied or a certain percentage of the total tender and contract value comply with this requirement. To establish origin, one must determine where the product in question has been obtained or produced. A product cannot originate in a country in which no production process has taken place. On the other hand, the country of production is not necessarily the country of origin but only when the relevant provisions of Regulation (EEC) 2913/92 and its implementing regulation are fulfilled. Furthermore, the country of origin is not necessarily the country from which the goods have been shipped and supplied. Where there is only one country of production, the origin of the finished product is easily established. However, in cases where more than one country is involved in the production of goods it is necessary to determine which of those countries confers origin on the finished goods. The country of origin is deemed to be the country in which the goods have undergone their last, economically justified, substantial transformation and the provisions of Article 24 of the Community Customs Code must therefore be applied on a case by case basis to those goods. If the last substantial transformation has not taken place in a Member State of the European Union or one of the eligible recipient countries, the goods cannot be tendered for the project. The supplier must certify that the goods tendered comply with the origin requirement specifying the country or countries of origin. When tendering for systems comprising more than one item, the origin of each item in the system must be specified. If requested to do so, the supplier must provide any additional information and/or a certificate of origin in support of the origin claimed in the tender. |
| --- | --- |

| ( | Tenders which clearly fail to satisfy the rule of origin must be rejected. |
| --- | --- |

| ( | Nationality of experts and subcontractors: The Evaluation Committee must check at this stage that the nationalities of any experts and/or subcontractors identified in the technical offers satisfy the nationality rule in section. |
| --- | --- |

Having evaluated the tenders, the Evaluation Committee rules on the technical compliance of each tender, classifying it as technically compliant or not technically compliant. Where contracts include after-sales service and/or training, the technical quality of such services is also assessed during the technical evaluation. If the tenderer submitted a permitted variant solution in accordance with any specific rules for the submission of variants, the variant tender should be evaluated.

Part 3: Technical ranking/rating/grading of tenders.

Unless lowest price is the sole criterion, all compliant tenders and variant tenders then need to be evaluated against the criteria and compared for determining which is the most economically advantageous (cf. 4.3.10.3).

5.3.9.5	Evaluation of Financial Offers

Once the technical evaluation has been completed, the Committee checks that the financial offers contain no arithmetical errors. Arithmetical errors which can be corrected without prejudice to the tenderer must be corrected and notified to the tenderer concerned. Otherwise the tenderer must be given the opportunity to correct the error.

If the tender procedure contains several lots, financial offers are compared for each lot. The financial evaluation will have to identify the best financial offer for each lot.

If, for a given contract, tenders appear to be abnormally low, the Contracting Authority or its evaluation committee must, before rejecting such tenders on that ground alone, request in writing details of the constituent elements of the tender which it considers relevant and verify those constituent elements, after due hearing of the parties, taking account of the explanations received.

The Contracting Authority may, in particular, take into consideration explanations relating to:

(a)	the economy of the manufacturing process, of the provision of services or of the construction method;

(b)	the technical solutions chosen or the exceptionally favourable conditions available to the tenderer;

(c)	the originality of the tender.

The justification for rejecting or accepting an abnormally low offer must be recorded in the evaluation report and the contracting authority must notify the European Commission of its decision.

5.3.9.6	Choice of Tender

5.3.9.6.1	Simple Supply Contracts

Lowest price will often be the sole criterion for awarding simple supply contracts. All non-compliant tenders having already been eliminated, the contract is awarded to the tenderer submitting the lowest priced, compliant tender.

If the selected tender exceeds the maximum budget available for the contract, the provisions of Section 3.3.10 apply.

5.3.9.6.2	Supply Contracts Involving Ancillary Services

Where a supply contract includes ancillary services (such as after sales services and/or training) which represent a significant proportion of the contract value, the technical evaluation can take into account the quality of such services on a YES/NO basis. All non compliant tenders having been eliminated, the contract is awarded to the tenderer offering the lowest price for both equipment and ancillary services together.

5.3.9.6.3	Particularly Complex Supplies

For particularly complex supplies or supplies concerning products with particular security/production/implementation constraints,  the contract will most often be awarded to the most economically advantageous tender from the point of view of the contracting authority, on the basis of various criteria linked to the subject-matter of the public contract in question, for example, quality, price, technical merit, aesthetic and functional characteristics, environmental characteristics, running costs, cost-effectiveness, after-sales service and technical assistance, delivery date and delivery period or period of completion.

The European Commission must give its prior approval to the use of this approach and will provide technical support to the Contracting Authority on a case-by-case basis.

5.3.9.7	Conclusions of the Evaluation Committee

| ( | As a result of its deliberations, the Evaluation Committee may make any of the following recommendations: □ Award the contract to the tenderer which has submitted a tender: – which complies with the formal requirements and the eligibility rules; – whose total budget is within the maximum budget available for the project; – which meets the minimum technical requirements specified in the tender dossier; and – which offers the best value for money satisfying all of the above conditions. □ Cancel the tender procedure in exceptional circumstances, such as: – None of the tenders satisfies the selection/award criteria of the tender procedure; □ All tenders received exceed the maximum budget available for the contract. |
| --- | --- |

The entire procedure (technical and financial evaluation) is recorded in an Evaluation Report (see template in Annex C7) to be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee. This must be submitted to the Contracting Authority, which must decide whether or not to accept the Committee's recommendations.

The Contracting Authority must then submit the Evaluation Report together with its recommendation to the European Commission for approval. If there is an award proposal and the European Commission has not already received the original tender of the recommended tenderer and copies of the other tenders, these must be submitted.

At the same time, for any award proposal, a contract dossier including a proposed contract must be prepared on the basis of the recommended tender. It must be submitted to the European Commission for endorsement (agreement to finance the proposed contract).

If the European Commission does not accept the recommendation of the Evaluation Committee and the Contracting Authority, it must write to the Contracting Authority stating the reasons for its decision. The European Commission may also suggest how the Contracting Authority should proceed and give the conditions under which the European Commission may endorse a proposed contract on the basis of the tender procedure.

If the European Commission approves the recommendation of the Evaluation Committee, the Contracting Authority will either commence awarding the contract or cancel the tender, as recommended by the Evaluation Committee.

The report is drawn up, dated and kept for future reference. That written record must contain at least the following:

(a)	the name and address of the Contracting Authority, and the subject and value of the contract or framework agreement;

(b)	the names of the candidates or tenderers rejected and the reasons for their rejection;

(c)	the names of the candidates or tenderers to be examined and the reasons for their selection;

(d)	the names of the candidates or contractor proposed and the reasons for that choice and, if known, the proportion of the contract which the contractor intends to subcontract to third parties.

The Contracting Authority will then take its decision giving at least the following:

(a)	its name and address, and the subject and value of the contract or framework contract;

(b)	the names of the candidates or tenderers rejected and the reasons for their rejection;

(c)	the names of the candidates or tenderers to be examined and the reasons for their selection;

(d)	the names of the candidates or contractor selected and the reasons for that choice by reference to the selection and award criteria announced in advance and, if known, the proportion of the contract or the framework contract which the contractor intends to subcontract to third parties;

(e)	in the case of negotiated procedures, the circumstances referred to in these rules which justify their use;

(f)	where appropriate, the reasons why the Contracting Authority has decided not to award a contract.

The entire evaluation procedure, including notification of the successful tenderer, must be completed while the tenders are still valid. It is important to bear in mind that the successful tenderer might be unable to maintain its tender if the evaluation procedure takes too long.

| ( | The entire tender procedure is confidential from the end of the tender opening session to the signature of the contract by both parties. The Evaluation Committee's decisions are collective and its deliberations must remain secret. The Evaluation Committee members and any observers are bound to secrecy. |
| --- | --- |

The Evaluation Report, in particular, is for official use only and may be divulged neither to tenderers nor to any party outside the authorised services of the Contracting Authority, the European Commission and the supervisory authorities (e.g., the Court of Auditors). It may be given to a competent court under an open court case.

5.3.9.8	Contract Preparation

If the Evaluation Committee recommends the award of a contract to a particular tenderer and the Contracting Authority approves the Evaluation Report, the Contracting Authority must use the standard contract format (see Annex C04) to prepare the proposed contract. All the components of the proposed contract should be available from either the tender dossier or the tender submitted by the recommended tenderer. Only the Special conditions should need to be completed.

A contract dossier must be prepared using the following structure:

a) Explanatory note using the format in Annex A6 b) Copy of the financing agreement authorising the project. c) Copy of the tender announcements (PIN, if any, and contract notice), Site Visit Report, Tender Opening Report, Evaluation Report, and any other relevant information. d) Three copies of the proposed contract, which is based on the standard service contract template (see Annex C04): □ Special conditions (to be completed by the Contracting Authority); □ General conditions for supply contracts (standard version in the tender dossier); □ Technical specifications (from the tender dossier); □ Budget (from the recommended tender); □ Miscellaneous (from the tender dossier and including, for example, tax and customs arrangements, financial guarantee format, and the standard invoice format to be used by the contractor).

| ( | The standard contract annexes for the General conditions and Miscellaneous Information (see Annex C04) must be reproduced without modification in every supply contract. The Special conditions must be completed by the Contracting Authority |
| --- | --- |

### 5.3.10	Cancelling the Tender Procedure

The Contracting Authority may decide to cancel the tender procedure at any stage, but particularly in the light of the Evaluation Report, if:

the tender procedure has been unsuccessful, i.e., no acceptable tender has been received or there is no response at all;

the economic or technical data of the project have been fundamentally altered;

exceptional circumstances or force majeure render normal performance of the contract impossible;

all technically compliant tenders exceed the financial resources available;

there have been irregularities in the procedure, in particular where these have prevented fair competition.

The responsibility for cancelling a tender procedure lies with the Contracting Authority, with the prior approval of the European Commission.

In the event of cancellation of any tender procedure, tenderers must be notified of the cancellation by the Contracting Authority. Such tenderers are not entitled to compensation. They will be entitled to the immediate release of their tender guarantee. When the tender procedure is cancelled before the outer envelope of any tender has been opened, the unopened and sealed envelopes must be returned to the tenderers.

### 5.3.11	Award of the Contract

5.3.11.1	Notifying the Successful Tenderer

After the Contracting Authority and the European Commission have given their formal approval and before the period of validity of tenders expires, the Contracting Authority notifies the successful tenderer in writing that its tender has been successful, as well simultaneously in writing informing the unsuccessful tenderers (see format of letter in Annex C8). It draws attention to any arithmetical errors which were corrected during the evaluation process.

Before the period of validity of tenders expires, the Contracting Authority notifies the successful tenderer in writing that its tender This notification to the successful tenderer implies that the validity of the successful tender is automatically extended for a period of 60 days from the date of notification of award of the contract. Unless there is challenge of the award decision by any of the unsuccessful tenderers within 15 days from the date of notification, the Contracting Authority sends the contract to the tenderer for signature.

Where a contract is awarded under a financing memorandum which had not been concluded at the time the tender procedure was launched, the Contracting Authority must not notify the successful tenderer before the financing memorandum has been concluded.

5.3.11.2	Contract Signature

In preparing the contract for signature, the Contracting Authority must proceed as follows:

1)	Use the contract dossier prepared following acceptance of the recommendation of the Evaluation Committee.

2)	Sign all copies of the contract.

3)	Send all three signed copies of the contract to the successful tenderer, who must countersign them within 30 days of receipt (and, in any case, before the expiry of the tender validity period) and return two copies to the Contracting Authority together with the advance guarantee required in the contract. If the successful tenderer fails to do this within the specified deadline or indicates at any stage that it is not willing or able to sign the contract, the tenderer cannot be awarded the contract and forfeits its tender guarantee. The contract preparation process must be restarted from step 1 with a new contract dossier prepared using the tender which has the next lowest price or which is the next most advantageous tender (provided that that tender is technically compliant and is within the maximum budget available for the contract).

4)	On receipt of the two signed copies from the successful tenderer, the Contracting Authority sends one to the financial service in charge of payments and the second copy is sent to the European Commission. A copy of the signed contract must be sent to the Project Manager.

| ( | The Contracting Authority and the Contractor must note on the contract the date on which they sign it. Subject to any conditions imposed, the contract takes effect on the date of the later signature. A contract cannot cover earlier supplies/services or enter into force before this date. |
| --- | --- |

5.3.11.3	Publicising the award of the contract

As indicated above, the Contracting Authority informs candidates and tenderers of decisions reached concerning the award of the contract as soon as possible, including the grounds for any decision not to award a contract for which there has been competitive tendering or to recommence the procedure.

Once the contract has been awarded, the Contracting Authority must within 48 days prepare a contract award notice (using the template in Annex C09) and send it, where possible in electronic form, to the Official Journal of the European Union for publication. In addition, the Contracting Authority must record all statistical information concerning the contract award procedure including the contract value, the names of the other tenderers and the successful tenderer.

| ( | The Contracting Authority is responsible for preparing the supply contract award notice and for submitting it in electronic form to OJEU for publication The award notice must be sent within 48 days from the date of award. |
| --- | --- |

## 5.4	Local open tender for Contracts under the EU Threshold

In this case, the procurement notice is published only in the beneficiary country. It may be published on the website of the Contracting Authority and/or in the official Procurement Bulletin issued by the government, or in another appropriate media. As the cost of publishing the full procurement notice in the local media may be prohibitive, the template in Annex C3 gives the minimum information which must be included in a local advertisement. However, the full procurement notice must be available from the address referred to in the advertisement, together with the tender dossier. This publication is under the responsibility of the beneficiary country.

Note that a local open tender procedure must provide other eligible contractors with the same opportunities as local firms. No conditions seeking to restrict the participation of other eligible contractors are allowed (e.g., obliging such firms to be registered in the beneficiary country or to have won contracts there in the past).

In this procedure, there must be a minimum of 30 days between the date of publication of the procurement notice in the local press and the deadline for receipt of tenders.

|  | ( | The measures applicable to an international open procedure, as described previously, apply by analogy to the local open procedure. The Contracting Authority may require a tender guarantee. It may as well require documentary evidence only from the successful tenderer at the stage of awarding rather than to all bidders at the stage of selection. There’s no contract award notice but each tenderer has to be informed as per international tender. |
| --- | --- | --- |

|  | ( | The Contracting Authority may award supply contracts of a value of €5,000 or less on the basis of a single tender. Note that projects must not be split artificially to circumvent the procurement thresholds. |
| --- | --- | --- |

## 5.5	Modifying Supply Contracts

Supply contracts may need to be modified during their duration if the circumstances affecting project implementation have changed since the initial contract was signed. Contract modifications must be formalised through an addendum to the contract. Such an addendum must be signed by the contracting parties unless they are explicitly allowed under the conditions of the contract.

Changes of address, changes of bank account and changes of auditor may simply be notified in writing by the supplier to the Contracting Authority, although this does not affect the right of the Contracting Authority to oppose the supplier's choice of bank account or auditor.

### 5.5.1	General Principles

The following general principles must always be respected:

A supplier's requests for contract modifications should not automatically be accepted by the Contracting Authority. Such requests must be properly substantiated. The Contracting Authority must examine the reasons given and reject requests which have little or no substantiation.

Contracts can only be modified within the lifetime of the contract; modifications cannot be made retroactively.

The purpose of the addendum must be closely connected with the nature of the project covered by the initial contract.

Major changes, such as a fundamental alteration of the Technical Specifications, cannot be made by means of an addendum.

The addendum must not alter the competition conditions prevailing at the time the contract was awarded.

Unit prices must be identical to those in the initial contract, unless the initial contract stipulates otherwise (i.e., there is a price-revision clause).

Any modification extending the performance period of the contract must be such that implementation and final payments can be completed before the expiry of the financing agreement under which the initial contract was financed.

Any modifications which require additional funding must have been foreseen in the Technical Specifications of the initial contract and can only be agreed before the expiry of the financing agreement under which the initial contract was financed. The additional funding must come from the same budget line as that used for the initial contract.

| ( | Under no circumstances can the Contracting Authority increase the budget of the initial contract or agree to/arrange for the purchase of equipment that was not covered in the Technical Specifications of the initial tender and subsequent contract. The only exception to this rule is for additional deliveries by the original supplier intended either as a partial replacement of supplies or installations included in the original contract, or as an extension of existing supplies or installations where a change of supplier would oblige the Contracting Authority to acquire equipment having different technical characteristics which would result in either incompatibility or disproportionate technical difficulties in operation and maintenance. The length of such contracts as well as that of recurrent contracts may not, as a general rule, exceed three years. |
| --- | --- |

| ( | Requests for contract modifications to supply contracts must be made (by one contracting party to the other) allowing at least 30 days for the addendum to be signed before the end of the period of execution of the initial contract. |
| --- | --- |

### 5.5.2	Preparing an Addendum

In preparing the addendum, the Contracting Authority must proceed as follows:

1)	Use the standard template for an addendum (see Annex A07)

| ( | All references in the proposed addendum to article numbers and/or annexes to be modified must correspond to those in the initial contract. |
| --- | --- |

Any addendum modifying the budget must include a replacement budget showing how the full budget breakdown of the initial contract has been modified by this addendum (and any previous addenda). The following column headings should be used:

| Budget Item | Initial contract budget | Addendum 1 | (Addendum 2…) | Revised budget |
| --- | --- | --- | --- | --- |

| ( | If the budget is modified by the proposed addendum, the payment schedule must also be modified accordingly, taking into account any payments already made in the course of the contract. The payment schedule must not be modified unless either the budget is being modified or the contract is being extended. |
| --- | --- |

2)	Prepare a dossier comprising the following items:

a) Explanatory note (see template in Annex A06) providing a technical and financial justification for making the modifications in the proposed addendum b) Copy of the contractor’s request for (or agreement to) the proposed modifications c) Copy of the financing agreement authorising the project d) Copy of the initial contract and any subsequent addenda e) Copy of the tender announcements (contract forecast and contract notice), Site Visit Report, Tender Opening Report, Evaluation Report and any other relevant information f) Three copies of the proposed addendum, which is based on the standard addendum template (see Annex A07) and includes any revised annexes.

3) Sign all copies of the addendum and send the addendum dossier to the European Commission for approval and endorsement.

4)	Send the three signed copies of the addendum to the contractor, who must countersign them within 30 days of receipt and return two copies to the Contracting Authority together with any financial guarantee required in the addendum.

5)	On receipt of the two signed copies from the successful tenderer, the Contracting Authority send one to the financial service in charge of payments and the second copy is sent to the European Commission. A copy of the signed addendum must be sent to the Project Manager.

| ( | The Contracting Authority and the Contractor must note on the addendum the date on which they sign it. The addendum takes effect on the date of the later signature. An addendum cannot cover earlier supplies/services or enter into force before this date. |
| --- | --- |

section 6.	Works contracts

## 6.1	Introduction

Works contracts cover either the execution, or both the execution and design, of works or the realisation, by whatever means, of a work corresponding to the requirements specified by the Contracting Authority. A 'work' means the outcome of building or civil engineering works taken as a whole that is sufficient of itself to fulfil an economic or technical function.

Works contracts are contracts concluded between a Contracting Authority and a contractor for the execution of works or a work

"Contractor" describes any natural or legal person, public entity or group of such persons, who offers works on the market. A contractor who has sought an invitation to take part in a restricted or negotiated procedure is known as a “candidate” and one who has submitted a tender is known as a "tenderer".

The Contracting Authority, which is always specified in the contract notice, is the authority as defined in the glossary of terms (Annex A01) empowered to conclude the contract.

Works contracts are concluded by the Contracting Authority designated in a financing agreement, i.e., the government or an entity of the beneficiary country with legal personality with which the European Commission establishes the financing agreement.

The Contracting Authority submits the tender dossiers to the European Commission for approval prior to issue. The Contracting Authority must submit procurement notices and award notices to the European Commission for publication.

On the basis of decisions thus approved and in close consultation with the European Commission, the Contracting Authority is responsible for launching tender procedures, receiving tenders, chairing tender-examination sessions and deciding on the results of tender procedures. The Contracting Authority submits the results of the tender examination and the contract award proposal to the European Commission for approval. Once it has received approval, it signs the contracts and notifies the European Commission accordingly. As a general rule, the European Commission will be represented when tenders are opened and evaluated and must always be invited.

## 6.2	Procurement Procedures

### 6.2.1	Contracts above the Threshold of the Directive

6..2.1.1	Choice of Procedure

All works contracts at or above the EU threshold may be awarded by an open procedure or by a restricted procedure following publication of a contract notice as laid down in Section 1.

The open procedure is defined in the directives as a procedure in which any economic operator can tender. It should be recalled, however, that contracting authorities can reject tenderers who do not meet their minimum standards and that only EU economic operators, or equivalent under an agreement with the EU, have rights under Community law.

The restricted procedure is defined as a procedure in which any economic operator can ask to participate but only those invited to do so by the contracting authority can submit a tender.

The negotiated procedure with or without a prior call for competition may only be used in exceptional circumstances as stated below.

6.2.1.2	Negotiated Procedure

(a)	Works contracts may be awarded by a negotiated procedure with prior publication of a contract notice in the following exceptional circumstances:

in the event of irregular tenders or tenders which are unacceptable under national provisions compatible with the Directive, in response to an open or restricted procedure insofar as the original terms of the contract are not substantially altered;

in exceptional cases, when the nature of the works or the risks attaching thereto do not permit prior overall pricing;

for works which are performed solely for purposes of research, testing or development and not with the aim of ensuring profitability or recovering research and development costs.

(b)	Works contracts may be awarded by a negotiated procedure without prior publication of a contract notice in the exceptional circumstances permitted under the Directive:

where no tender or no appropriate tenders have been submitted in response to an open or a restricted procedure, provided the original terms of the contract are not substantially altered and the principle of equal treatment is observed.

when for technical or artistic reasons, or for reasons connected with the protection of exclusive rights, the contract may be awarded only to a particular contractor;

insofar as is strictly necessary when, for reasons of extreme urgency brought about by events which the contracting authority could not have foreseen and which can in no way be attributed to it the time-limit for the open, restricted or negotiated procedure with publication of a contract notice cannot be met.

(Operations carried out in crisis situations as referred to in Article 168(2) of the implementing rules are considered to satisfy the test of extreme urgency.)

for additional works not included in the project initially considered or the original contract which have, through unforeseen circumstances, become necessary for carrying out the works described therein and which are to be awarded to the contractor already carrying out the work:

▫	where such works cannot be technically or economically separated from the original contract without major inconvenience to the contracting authority; or

▫	where such works, although separable from the performance of the original contract, are strictly necessary to its completion; and

▫	where, in either case, the aggregate value of contracts awarded for additional works does not exceed 50 per cent of the value of the original contract;

for new works consisting in the repetition of similar works entrusted to the contractor to whom the contracting authority awarded an original contract according to the open or restricted procedure, provided the works conform to a basic project for which the original contract was awarded.

The use of this procedure must be disclosed when the first project is put up for tender and the total estimated value must be taken into account. The procedure can only be used during the three years after the original contract is signed.

In not requiring a call for competition, these derogations from the fundamental principles of transparency and competitive procurement must be construed narrowly.

The Contracting Authority must seek prior approval from the European Commission to use the negotiated procedure.

Where the contracting authority uses a negotiated procedure with or without publication of a contract notice, the contracting authority must prepare a report justifying the manner in which the negotiations were conducted and the basis for the contract award decision resulting from these negotiations. The procedures given in Section 1 must be followed by analogy, with the Negotiation Report being included in the contract dossier.

### 6.2.2	Contracts below the EU Threshold

Contracts below the EU threshold may be awarded by a local open procedure, involving a local call for competition (see 6.5). The national legislation may provide for the same provisions as for contracts over the thresholds or lay down simplified procedures.

## 6.3	Procedures for Contracts above the EU Threshold

### 6.3.1	Publicity

In order to ensure the widest possible publicity and increase competition, every contract award procedure above the EU threshold shall be introduced in a Prior Indicative Notice (PIN). In addition, dispatch of a full PIN to the OJEU may enable the contracting authority to take advantage of shorter minimum timescale for the receipt of tenders. A full PIN is one which includes as much of the information required for a contract notice as is available when the PIN is dispatched.

The model forms in Annex for PINs as well as those for contract notices and award notices are based on the standard forms which are mandatory for contracts above the threshold and should be completed using the EU reference nomenclature applicable to public contracts (CPV).

6.3.1.1	Publication of Contract Forecasts

The PIN, or contract forecast, should be dispatched to the OJEU, using the template in Annex D01, as soon as possible after the decision approving the programme for acquiring the works.

The contract forecasts must give a brief indication of the subject and content of the contracts concerned. Given that they are forecasts, publication does not bind the Contracting Authority to finance the contracts proposed and prospective contractors are not expected to submit tenders at this stage. . Where possible they should be submitted in electronic form and at least 12 days before the desired date of publication. If reduced minimum timescales are sought, the PIN must be published at least 52 days and not more than one year before the corresponding contract notice.

The contract forecasts are published in the Official Journal of the European Union

6.3.1.2	Publication of Contract Notices

In addition to contract forecasts (PINs), all works contracts which meet the EU threshold must also be the subject of a contract notice published in the Official Journal of the European Union (OJEU).

The European Commission is responsible for publication in the Official Journal of the European Union. When the procurement notice is also published locally, the Contracting Authority must arrange publication directly.

Contract notices for publication in the OJEU must be submitted to the relevant services of the European Commission using the template in Annex D02. Where possible they should be submitted in electronic form and sufficiently in advance before the intended date of publication (the OJEU shall publish the notices not later than 12 days after their dispatch).

The contract notice must identify clearly, precisely, and completely what the subject of the contract is and who the Contracting Authority is. If the contract notice is also published locally, it must not be published before dispatch of the OJEU notice, it must not contain more information than the OJEU notice and must say when the OJEU notice was dispatched.

Under the open procedure, the Contracting Authority must send tender dossiers to would-be tenderers. Because of their size and printing costs, tender dossiers for works contracts are usually sent out for a fixed fee. If a contractor is responsible for compiling the tender dossier and/or sending it out, the contractor in question must sign a Declaration of Objectivity and Confidentiality (see Annex A3).

### 6.3.2	Drafting and Contents of the Tender Dossier

It is vital that tender documents are drafted carefully, not only for the proper execution of the contract but also for the sound functioning of the award procedure. These documents must contain all the information that tenderers need to present their tenders: the procedures to follow, the documents to provide, cases of non-compliance, award criteria, etc. It may be desirable for representatives of the final beneficiaries to participate in the tender preparation at an early stage. See Section 2.10 for guidelines on preparing Technical Specifications.

Technical specifications must afford equal access for candidates and tenderers and not have the effect of creating unjustified obstacles to competitive tendering. They define the characteristics required of a product, service or material or work with regard to the purpose for which they are intended by the Contracting Authority. Those characteristics shall include

(a)	levels of quality, performance, safety or dimensions, including the requirements applicable to the material, the product or to the supply as regards quality assurance, terminology, symbols, testing and test methods, packaging, marking and labelling;

(d)	rules relating to design and costing, the test, inspection and acceptances for works and methods or techniques of construction and all other technical conditions prescribed by thr contracting authority, under general or specific regulations, in relation of finished works and to the materials or parts which they involve.

Given the technical complexity of many works contracts, the preparation of the tender dossier - particularly the Technical Specifications - may require the assistance of one or more external technical specialist(s) who must be recruited by the Contracting Authority with the prior approval of the European Commission. Each such specialist must sign a Declaration of Objectivity and Confidentiality (see Annex A03).

Particular attention must be paid to the preparation of the Technical Specifications for the works tendered. These are the key to successful procurement and a sound works contract and project. The Technical Specifications indicate — where applicable, lot by lot — the exact nature and performance characteristics of the works. Where applicable, they also specify delivery conditions and installation, training and after-sales service.

It is essential that the performance characteristics correspond to the intended purpose. If there needs to be a clarification meeting or site visit to clarify technical requirements at the site where the works are to be carried out, this should be specified in the instructions to tenderers, together with details of the arrangements.

The purpose of the Technical Specifications is to define the required works precisely. The minimum quality standards, defined by the Technical Specifications, will enable the contracting authority or its evaluation committee to determine which tenders are technically compliant.

Contract notices must indicate whether or not tenderers may submit tenders for 'variant solutions'. Where variants are allowed by the tender dossier, the Contracting Authority may take them into account when:

they are submitted in accordance with any specific requirements for the submission of variants; and

they meet the technical specifications required by the tender dossier, attaining at least the minimum quality and performance required.

The Contracting Authority must clearly state in the tender dossier the minimum specifications to be respected by the variants and any specific requirements for their presentation.

| ( | Unless warranted by the nature of the contract, Technical Specifications mentioning or describing products of a given brand or origin and thereby favouring or excluding certain products are prohibited. However, where products cannot be described in a sufficiently clear or intelligible manner, they may be named as long as they are followed by the words "or equivalent". In all cases the Contracting Authority must be prepared to consider tenders which the tenderers can prove offer equivalent functionality. |
| --- | --- |

The Contracting Authority must submit the tender dossier to the European Commission for approval prior to issue.

The tender dossier must contain the following documents:

TENDER DOSSIER CONTENT

| ① | INSTRUCTIONS TO TENDERERS |
| --- | --- |
|  | which must indicate: |
|  | □ The type of contract (i.e., Works either Construction or Design-Build). The Contracting Authority chooses Annex D4 or D4bis accordingly. |
|  | □ The selection and award criteria and the rules for applying them. |
|  | □ The grid to be used to assess the conformity of tenders. Given the wide variety of works and their technical nature, the grid must be individually developed for each tender in a YES/NO format to allow clear assessment whether or not the offer responds to the Technical Specifications. |
|  | □ The relative weighting of the award criteria must then be established as the basis for assessing which tender is the most economically advantageous. |
|  | □ Whether variants are authorised. |
|  | □ Whether subcontracting intentions are to be disclosed. |
|  | □ The currency of the tender. |
|  | □ The format to be used by a bank or similar institution to provide a tender guarantee (1 per cent of the bid value) |
|  | See Annex D 04 or D04bis for template. |

| ② | DRAFT CONTRACT AND ANNEXES |
| --- | --- |
|  | See standard format in Annex D04/D04bis. This includes: |
|  | □ The specific contract conditions which amplify, supplement or derogate from the general conditions, and where they conflict, override them. |
|  | □ The technical annexes, containing any plans and the Technical Specifications, as well as a provisional timetable for performance. |
|  | □ The format of the bill of quantities/budget (for completion by the tenderer). |
|  | □ The General Conditions for works contracts, to be included as an annex of the eventual contract. Changes to the General Conditions are forbidden unless such changes are provided for by the specific contract conditions. |
|  | □ The formats to be used by a bank or similar institution to provide guarantees for: |
|  | – payment of advances, and |
|  | – performance (10 per cent of the contract value) |
|  | □ Any additional contractual information such as special tax arrangements for contracts funded by the European Community. |
|  | The tender documents must clearly state whether a firm, non-revisable price must be quoted. If that is not the case, they must lay down the conditions and/or formulas for revision of prices during the lifetime of the contract. In such cases the Contracting Authority must take particular account of: |
|  | (a) the object of the procurement procedure and the economic situation in which it is taking place; |
|  | (b) the type of tasks and contract and their duration; |
|  | (c) its financial interests. |
|  | A guarantee is required in return for the payment of pre-financing exceeding €150 000. It will be released as and when the pre-financing is deducted from interim payments or payments of balances made to the contractor in accordance with the terms of the contract. |

| ③ | TENDER SUBMISSION FORMAT |
| --- | --- |
|  | The format in which the tender should be submitted. See Annex D04/D04bis for template. The technical and financial offers must both be submitted in a single, sealed envelope or packet. The technical offer must satisfy the Technical Specifications in all respects. The financial offer must be presented in the standard format to facilitate comparison of the financial offers. If this format is not respected, the tender will be rejected. |

### 6.3.3	Selection and Award Criteria

6.3.3.1	Selection Criteria

The selection criteria concern the tenderer's capacity to execute similar contracts, with particular reference to works executed in recent years. They are used in admitting tenderers under the open procedure and in admitting candidates and selecting which to invite to participate in other procedures.

The selection procedure involves:

1)	eliminating candidates who are ineligible (see Section 1.3) or are excluded from public procurement contracts;

2)	checking that the candidates' financial situation (financial and economic standing) is sound, as backed up, for example, by balance sheets and turnover for the previous three years (see Section 2.11);

3)	verifying the candidates' technical and professional capabilities, for example by looking at their average annual staffing levels, the size and professional experience of their management and the more important works carried out over the past five years (see Section 2.11).

The selection criteria specified in the annexes to this guide are given by way of illustration and should be adapted to the nature, cost and complexity of the contract.

If, for some exceptional reason which the Contracting Authority considers justified, the tenderer or candidate is unable to provide the references required by the Contracting Authority, it may prove its economic and financial capacity by any other means which the Contracting Authority considers appropriate. Where the works, services or products to be supplied are complex or, exceptionally, are required for a special purpose, evidence of technical and professional capacity may be secured by means of a check carried out by the contracting authority or on its behalf by a competent official body of the country in which the contractor is established, subject to that body's agreement. Such checks shall concern the contractor’s technical capacity and production capacity and, if necessary, its study and research facilities and quality control measures.

6.3.3.2	Award Criteria

The award criteria should be precise, non-discriminatory and not prejudicial to fair competition. All criteria specified in the tender dossier must be applied as such and cannot in any case be modified during the procedure.

The technical evaluation will start with an assessment of the conformity of the offer with the technical specifications based on the grid published in the tender dossier, which must not be modified in any way during the evaluation process. Given the wide variety of works and their technical nature, these must be individually developed for each tender in a YES/NO format to allow clear assessment whether or not the offer responds to the technical requirements of the tender dossier.

The criteria on which the contracting authorities shall base the award of works contracts shall be:

(a) either the lowest price only; 
(b) or, when the award is made to the most economically advantageous tender, various criteria according to the contract: e. g. price, running costs.

See Annex D04/D04bis.

### 6.3.4	Additional Information during the Procedure

The tender dossier should be clear enough to avoid tenderers having to request additional information during the tender procedure. If the Contracting Authority, either on its own initiative or in response to a request from a tenderer, provides additional information on the tender dossier, it must send such information in writing to all other tenderers at the same time.

If it proves impossible to identify potential tenderers in the case of an open tender procedure, a notice setting out any changes to the tender dossier may be published, taking into account that contract notices should be submitted for publication sufficiently in advance before the intended date of publication (the OJEU shall publish the notices not later than 12 days after their dispatch). The deadline for the submission of tenders may be extended to allow tenderers to take account of the changes. As a last resort, the contracting authority may need to cancel the procedure.

| ( | If the tender has a particularly complex technical content, the Contracting Authority may organise a clarification meeting or site visit. This meeting must be announced in the tender dossier and must take place at least 16 days before the expiry of the deadline. All costs of attending such a meeting must be met by the tenderers. Visits by individual companies during the tender period cannot be permitted unless clarification meetings and/or site visits have been specifically scheduled for all tenderers. |
| --- | --- |

Tenderers may submit questions in writing. The Contracting Authority must reply to all tenderers' questions at least 6 days before the deadline for receipt of tenders.

### 6.3.5	Deadline for the Submission of Tenders

Tenders must reach the Contracting Authority at the address and, at the very latest, at the date and time indicated in the tender dossier. The period for submission must be sufficient to guarantee the quality of tenders and so permit truly competitive tendering. Experience shows that too short a period prevents candidates from tendering or causes them to submit incomplete or ill-prepared tenders. The deadline for submissions must fall on a working day in the beneficiary country and be combined with the tender-opening session where applicable.

### 6.3.6	Period of Validity

Tenderers are bound by their tenders for the period specified in the tender dossier. This period must be sufficient to allow the Contracting Authority to examine the tenders, take the contract award decision, notify the tenderers and conclude the contract. The period of validity of tenders is fixed at 90 days from the deadline for the submission of tenders.

In exceptional cases, before the period of validity expires, the Contracting Authority may ask the tenderers to extend the period for a specific number of days, which may not exceed 40.

The successful tenderer must maintain its tender for a further 60 days from the date of notification of award.

### 6.3.7	Submission of Tenders

Each technical and financial offer must be placed in a single sealed envelope, itself placed in a package or outer envelope. The inner envelope must bear:

(a)	the address indicated in the tender documents for the submission of tenders;

(b)	the reference to the call for tenders to which the tenderer is responding;

(c)	where appropriate, the numbers of the lots for which a tender is being submitted;

(d)	the words "Not to be opened before the tender-opening session" written in the language of the tender dossier and in the local language;

(e)	the name of the tenderer.

### 6.3.8	The Evaluation Committee

6.3.8.1	Composition

Tenders are to be opened and evaluated in accordance with national legislation, compatible with the Directive. This might involve a formal Evaluation Committee or panel appointed by the contracting authority. Where tenders are opened and evaluated by an Evaluation Committee appointed by the Contracting Authority, the Committee should comprise a non-voting Chairman, a non-voting Secretary and a minimum of five voting members. Every member must have a working proficiency in the language in which the tenders are submitted. The voting members must possess the technical and administrative capacities necessary to give an informed opinion on the tenders.

The Evaluation Committee (i.e., the Chairman, the Secretary and the other voting members) must be nominated on a personal basis by the Contracting Authority. The composition of the Evaluation Committee must be submitted for approval to the European Commission. The European Commission may nominate an observer to follow all or part of the proceedings of the Evaluation Committee. The observer may be an independent expert. Prior approval must be sought from the European Commission for the participation of other observers.

The Evaluation Committee members should attend all meetings. Any absence must be recorded and explained in the Evaluation Report. All voting members of the Evaluation Committee have equal voting rights. The names and functions of all those involved in the evaluation process must be recorded in the Evaluation Report.

6.3.8.2	Impartiality and Confidentiality

Any Evaluation Committee member or observer who has a potential conflict of interest due to a link with any tenderer must declare it and immediately withdraw from the Evaluation Committee. He will be excluded from participating further in any capacity in the evaluation meetings.

Any Evaluation Committee member who withdraws from the Evaluation Committee for whatever reason must be replaced (following the standard procedure for appointing members of the Evaluation Committee, as explained in section 3.1) and the evaluation process must be restarted. Any assessment by a voting member withdrawing from the Committee at whatever stage of the evaluation has to be disregarded.

| ( | Save to the extent that the contracting authority will be required by the directive and national legislation to notify its award decisions and to provide de-briefing on request, no information about the examination, clarification, evaluation or comparison of tenders or decisions about the contract award can be disclosed before the signature of the contract by the Contracting Authority and the successful tenderer. Any attempt by a tenderer to influence the process in any way (whether by initiating contact with members of the Evaluation Committee or otherwise) will result in the immediate exclusion of its tender from further consideration. |
| --- | --- |

Apart from the tender opening session, the proceedings of the Evaluation Committee are conducted in camera and are confidential.

In order to maintain the confidentiality of the proceedings, participation in the Evaluation Committee meetings is strictly limited to the members of the Evaluation Committee designated by the Contracting Authority and any authorised observers.

The tenders should not leave the room/building in which the committee meetings take place before the conclusion of the work of the Evaluation Committee. They should be kept in a safe place when not in use.

6.3.8.3	Responsibilities of the Evaluation Committee Members

The Chairman is responsible for co-ordinating the evaluation process and for ensuring its impartiality and transparency. The voting members of the Evaluation Committee have collective responsibility for decisions taken by the Committee and its recommendation on the award of the contract.

The Secretary to the Committee is responsible for carrying out all administrative tasks connected with the evaluation procedure. These will include:

circulating and collecting the Declarations of Impartiality and Confidentiality;

keeping the minutes of all meetings of the Evaluation Committee and the relevant records and documents;

registering attendance at meetings and compiling the Evaluation Report and its supporting annexes.

Any request for clarification requiring communication with the tenderers during the evaluation process must be conducted in writing (by fax, letter or, where permitted, by electronic means) and signed by both the Chairman and the Secretary of the Evaluation Committee. Copies of any such communication must be annexed to the Evaluation Report.

If a tender infringes the formal requirements, the Evaluation Committee may use its discretion to decide whether or not it should still be considered during the rest of the evaluation process. Whatever the Evaluation Committee decides, this must be fully recorded and justified in the Evaluation Report.

6.3.8.4	Timetable

The Evaluation Committee should be formed early enough to ensure the availability of the designated members during the period necessary to prepare and conduct the evaluation process. The tender evaluation should be completed as soon as possible.

The duration of the evaluation process should be agreed between members of the Evaluation Committee and the Contracting Authority. The evaluation process must be completed in time to allow the successful tenderer to be notified by the Contracting Authority (after all necessary approvals) within the tender validity period (i.e., 90 days) specified in the tender dossier.

### 6.3.9	Stages in the Evaluation Process

6.3.9.1	Receipt and Registration of Tenders

On receiving tenders, the Contracting Authority must register them and provide a receipt for those delivered by hand. The envelopes containing the tenders must remain sealed and be kept in a safe place until they are opened.

The outer envelopes of tenders must be numbered in order of receipt (whether or not they are received before the deadline for submission of tenders).

6.3.9.2	Preparatory Meeting

First meeting of Evaluation Committee:

to be held before the tender opening session

the tender dossier should have been distributed in advance to the members of the Evaluation Committee.

The Chairman presents the purpose of the tender procedure in general terms.

The Chairman reminds the Evaluation Committee of the selection and award criteria specified in the tender dossier, stating that these must be respected without modification.

The Chairman explains the procedures to be followed by the Evaluation Committee.

Before the tenders are opened, the Chairman of the Committee checks that all members are familiar with the grid set out in the tender dossier to make sure that the conformity of tenders to technical requirements will be evaluated by the different members of the Committee in a consistent manner. See Annex D04 for the format of an evaluation grid. The Chairman must then ensure that the voting members are familiar with the relative weighting of the award criteria and the means to apply them.

6.3.9.3	Tender Opening Session

The purpose of the tender-opening session is to check that the tenders are complete, that the requisite tender guarantee has been provided, that the documents have been duly signed and that the tenders are generally in order.

| ( | The tender opening session may be a formal, public process. The Evaluation Committee opens the tenders in public at the place and time fixed in the tender dossier. The following are announced at the tender-opening session: the names of the tenderers, the tender prices, the provision of the requisite tender guarantee and any other formality which the Contracting Authority thinks appropriate. |
| --- | --- |

Representatives of the tenderers may attend a public opening session. The minutes of this meeting must be recorded separately and may be made available to the tenderers on request.

The European Commission must be informed of the tender opening session. It may be represented as an observer at the tender-opening session and receive a copy of each tender.

All members of the Evaluation Committee and any observers are required to read and sign a Declaration of Impartiality and Confidentiality (see Annex A4).

See tender opening checklist in Annex D05 for the detailed formalities to be carried out by the Chairman with the assistance of the Secretary, as summarised below.

The following tasks are carried out by the Chairman, the Secretary or the responsible person:

Examine and state the condition of outer envelopes before opening them in order of receipt, announcing the name of the tenderer. Only tenders in envelopes received by the date and time indicated in the tender dossier are considered for evaluation.

Initial the front page of each document and all pages of the financial offer.

The Committee must decide whether or not tenders comply with the formal requirements. The Summary of tenders received, which is attached to the Tender Opening Report (see Annex D06) must be used to record the compliance of each of the tenders with the formal requirements. The tenders not considered for further evaluation must be kept by the Contracting Authority, together with the other tenders — the associated guarantees may be returned to the tenderers on request.

| ( | The Tender Opening Report, which comprises the Summary of tenders submitted and the minutes of the tender opening session, must be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee. It may be made available to the tenderers upon request. The Tender Opening Report must state: □ the date, time and place of the session; □ the persons present; □ the names of the tenderers who have replied within the deadline; □ whether the originals of the tenders were duly signed, and whether technical offers were sent in the requisite number of copies; □ the names of any tenderers whose tenders were found to be non-compliant at the opening session and the requirement(s) with which their tenders failed to comply; □ the names of any tenderers who withdrew their tenders; □ any declarations made by the tenderers. |
| --- | --- |

6.3.9.4	Evaluation of Technical Offers

It is obligatory that the technical evaluation uses the evaluation grid published in the tender dossier.

As part of the technical evaluation, the Evaluation Committee analyses the commercial aspects, and, where applicable, the training component of the tenders to determine whether they satisfy the requirements set in the tender dossier. The results are recorded in a YES/NO grid for all elements specified in the tender dossier. No scoring method should be used. If the tender is divided into lots, the evaluation should be carried out lot-by-lot.

Part 1: Administrative compliance

Before conducting a detailed evaluation of the tenders, the Contracting Authority checks that they comply with the essential requirements of the tender dossier.

A tender is deemed to comply if it satisfies all the conditions, procedures and specifications in the tender dossier without substantially departing from or attaching restrictions to them. Substantial departures or restrictions are those which affect the scope, quality or performance of the contract, differ widely from the terms of the tender dossier, limit the rights of the Contracting Authority or the tenderer's obligations under the contract or distort competition for tenderers whose tenders do comply.

Tenders which do not comply with the tender dossier may be rejected by the Contracting Authority and may not subsequently be made to comply by undergoing corrections or having discrepancies or restrictions removed. The evaluation committee may decide to ask for missing documents or formal corrections. This decision has to be applied equally to all tenders.

Copies of the technical offers are distributed to the Committee members. The originals are locked away for safe keeping.

Each technical offer is examined for compliance with the tender dossier, in particular that:

the documentation is complete;

the language required by the tender dossier has been used;

the tenderer has initialled the front page of both the Technical Specifications and General Conditions;

for consortia: the confirmation of association and designation of a lead company has been signed by all consortium members;

for tenderers intending to subcontract tasks: the tenderer has included a statement regarding the content and extent of subcontracting envisaged, and, if known, the names of the proposed sub-contractors.

With the agreement of the other Evaluation Committee members, the Chairman may communicate in writing with tenderers whose submissions require clarification, offering them the possibility to respond within an acceptable time limit. The evaluation committee may decide to ask for missing documents or formal corrections. This decision has to be applied equally to all tenderers.

| ( | The Chairman must check that no member of the Evaluation Committee has a potential conflict of interest with any of the tenderers (on the basis of the shortlist, the tenders received, consortium members and any identified subcontractor). Any Evaluation Committee member or observer who has a potential conflict of interest due to a link with any tenderer must declare it and immediately withdraw from the Evaluation Committee. He will be excluded from participating further in any capacity in the evaluation meetings. Any Evaluation Committee member who withdraws from the Evaluation Committee for whatever reason must be replaced (following the standard procedure for appointing members of the Evaluation Committee, as explained in Section 3.1) and the evaluation process must be restarted. |
| --- | --- |

The administrative compliance of each of the tenders must be recorded in the Evaluation Report (see Annex D07).

Part 2: Technical compliance of tenders

The detailed evaluation of the tenders takes place after checking that the tenders satisfy the formal requirements of tender submission. The criteria to be applied are those published in the tender dossier and, accordingly, the evaluation grid included in the tender dossier must be used. Under no circumstances may the Committee or its members change the evaluation grid communicated to the tenderers in the tender dossier.

The purpose of this evaluation is to assess whether or not the competing tenders meet the minimum technical requirements and eligibility criteria. As part of the technical evaluation, the Evaluation Committee analyses the commercial aspects, and, where applicable, the training component of the tenders to determine whether they satisfy the requirements set in the tender dossier. The results are recorded in a YES/NO grid for all elements specified in the tender dossier. No scoring method should be used. If the tender is divided into lots, the evaluation should be carried out lot-by-lot.

| ( | Rule of origin: All tenders must satisfy the rule that the goods to be supplied originate in EU Member States and/or the countries and territories of the regions covered and/or allowed by the Regulation or other instruments governing the programme under which the contract is being financed. |
| --- | --- |

| ( | Tenders which clearly fail to satisfy the rule of origin must be rejected. |
| --- | --- |

| ( | Nationality of experts and subcontractors: The Evaluation Committee must check at this stage that the nationalities of any experts and/or subcontractors identified in the technical offers satisfy the nationality rule in Section 1.3. |
| --- | --- |

Having evaluated the tenders, the Evaluation Committee rules on the technical compliance of each tender, classifying it as technically compliant or not technically compliant. If the tenderer has submitted a permitted variant solution in accordance with any specific rules for the submission of variants, the variant tender should be evaluated.

6.3.9.5	Evaluation of Financial Offers

Once the technical evaluation has been completed, the Committee checks that the financial offers contain no arithmetical errors. Arithmetical errors which can be corrected without prejudice to the tenderer must be corrected and notified to the tenderer concerned. Otherwise the tenderer must be given the opportunity to correct the error.

If the tender procedure contains several lots, financial offers are compared for each lot. The financial evaluation will have to identify the best financial offer for each lot.

If, for a given contract, tenders appear to be abnormally low, the Contracting Authority must, before rejecting such tenders on that ground alone, request in writing details of the constituent elements of the tender which it considers relevant and verify those constituent elements, after due hearing of the parties, taking account of the explanations received.

The Contracting Authority may, in particular, take into consideration explanations relating to:

(a)	the economics of the manufacturing process, of the provision of services or of the construction method;

(b)	the technical solutions chosen or the exceptionally favourable conditions available to the tenderer;

(c)	the originality of the work proposed by the tenderer.

The justification for rejecting or accepting an abnormally low offer must be recorded in the Evaluation Report and, where a tender is rejected on the grounds of an unapproved state aid, the Contracting Authority must notify the European Commission of its decision.

6.3.9.6	Choice of Contractor

According to the chosen award criterion, the successful tender is either the least expensive tender classified as "technically compliant" during the technical evaluation or the "most economically advantageous" tender when the pre-determined award criteria are applied according to the method described in the Tender Dossier. This must be declared the successful tender if it is equal to or lower than the maximum budget available for the contract. If the chosen tender exceeds the maximum budget available for the contract, the provisions set out in 6 .2.1.3 (b) apply.

6.3.9.7	Conclusions of the Evaluation Committee

| ( | As a result of its deliberations, the Evaluation Committee may make any of the following recommendations: □ Award the contract to the tenderer which has submitted a tender: – which complies with the formal requirements and the eligibility rules; – whose total budget is within the maximum budget available for the project; – which meets the minimum technical requirements specified in the tender dossier; and – which is the least expensive tender (satisfying all of the above conditions); or – which is the most economically advantageous tender. □ Cancel the tender procedure in exceptional circumstances, such as: – None of the tenders satisfies the selection/award criteria of the tender procedure; □ All tenders received exceed the maximum budget available for the contract. |
| --- | --- |

The entire procedure (technical and financial evaluation) is recorded in an Evaluation Report (see template in Annex D7) to be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee. This must submitted to the Contracting Authority, which must decide whether or not to accept its recommendations.

The Contracting Authority must then submit the Evaluation Report together with its recommendation to the European Commission for approval. If there is an award proposal and the European Commission has not already received the original tender of the recommended tenderer and copies of the other tenders, these must be submitted.

At the same time, for any award proposal, a contract dossier including a proposed contract must be prepared on the basis of the recommended tender. It must be submitted to the European Commission for endorsement (agreement to finance the proposed contract).

If the European Commission does not accept the recommendation of the Evaluation Committee and the Contracting Authority, it must write to the Contracting Authority stating the reasons for its decision. The European Commission may also suggest how the Contracting Authority should proceed and give the conditions under which the European Commission may endorse a proposed contract on the basis of the tender procedure.

If the European Commission approves the recommendation of the Evaluation Committee, the Contracting Authority will either commence awarding the contract or cancel the tender, as recommended by the Evaluation Committee.

The report is drawn up, dated and kept for future reference. That written record must contain at least the following:

(a)	the name and address of the Contracting Authority, and the subject and value of the contract or framework agreement;

(b)	the names of the candidates or tenderers rejected and the reasons for their rejection;

(c)	the names of the candidates or tenderers to be examined and the reasons for their selection;

(d)	the names of the candidates or contractor proposed and the reasons for that choice and, if known, the proportion of the contract or the framework agreement which the contractor intends to subcontract to third parties.

The Contracting Authority will then take its decision giving at least the following:

(a)	its name and address, and the subject and value of the contract or framework contract;

(b)	the names of the candidates or tenderers rejected and the reasons for their rejection;

(c)	the names of the candidates or tenderers to be examined and the reasons for their selection;

(d)	the names of the candidates or contractor selected and the reasons for that choice by reference to the selection and award criteria announced in advance and, if known, the proportion of the contract or the framework contract which the contractor intends to subcontract to third parties;

(e)	in the case of negotiated procedures, the circumstances referred to in these rules which justify their use;

(f)	where appropriate, the reasons why the Contracting Authority has decided not to award a contract.

The entire evaluation procedure, including notification of the successful tenderer, must be completed while the tenders are still valid. It is important to bear in mind that the successful tenderer might be unable to maintain its tender if the evaluation procedure takes too long.

| ( | Save to the extent that the contracting authority will be required by the directive and national legislation to notify its award decisions and to provide de-briefing on request, the entire tender procedure is confidential from the end of the tender opening session to the signature of the contract by both parties. In particular, the Evaluation Committee's decisions are collective and its deliberations must remain secret. The Evaluation Committee members and any observers are bound to secrecy. |
| --- | --- |

The Evaluation Report, in particular, is for official use only and may be divulged neither to tenderers nor to any party outside the authorised services of the Contracting Authority, the European Commission and the supervisory authorities (e.g., the Court of Auditors). It may be given to a competent court under an open court case.

6.3.9.8	Contract Preparation

If the Evaluation Committee recommends the award of a contract to a particular tenderer and the Contracting Authority approves the Evaluation Report, the Contracting Authority must use the standard contract format (see Annex D04/D04bis) to prepare the proposed contract. All the components of the proposed contract should be available from either the tender dossier or the tender submitted by the recommended tenderer. Only the Special conditions should need to be completed.

A contract dossier must be prepared using the following structure:

a) Explanatory note using the format in Annex A6 b) Copy of the financing agreement authorising the project c) Copy of the tender announcements (PIN, if any, and contract notice), Site Visit Report, Tender Opening Report, Evaluation Report and any other relevant information d) Three copies of the proposed contract, which is based on the standard service contract template (see Annex D04/D04bis): □ Special conditions (to be completed by the Contracting Authority); □ General conditions for works contracts (standard version in the tender dossier); □ Technical specifications (from the tender dossier); □ Budget (from the recommended tender); □ Miscellaneous (from the tender dossier and including, for example, tax and customs arrangements, financial guarantee format, and the standard invoice format to be used by the contractor).

| ( | The standard contract annexes for the General conditions and Miscellaneous Information (see Annex D04/D04bis) must be reproduced without modification in every works contract. The Special conditions must be completed by the Contracting Authority. |
| --- | --- |

### 6.3.10	Cancelling the Tender Procedure

The Contracting Authority may decide to cancel the tender procedure at any stage, but particularly in the light of the Evaluation Report, if:

the tender procedure has been unsuccessful, i.e., when no tenders or suitable tenders have been received;

the economic or technical data of the project have been fundamentally altered;

exceptional circumstances or force majeure render normal performance of the contract impossible;

all technically compliant tenders exceed the financial resources available;

there have been irregularities in the procedure, in particular where these have prevented fair competition.

In the event of cancellation of any tender procedure, tenderers must be notified of the cancellation by the Contracting Authority. Such tenderers will not be entitled to compensation if the contracting authority has reserved the right to cancel, but they will be entitled to the immediate release of their tender guarantee. When the tender procedure is cancelled before the outer envelope of any tender has been opened, the unopened and sealed envelopes must be returned to the tenderers.

The responsibility for cancelling a tender procedure lies with the Contracting Authority, with the prior approval of the European Commission.

### 6.3.11	Award of the Contract

6.3.11.1	Notifying the Successful Tenderer

After the Contracting Authority and the European Commission have given their formal approval and before the period of validity of tenders expires, the Contracting Authority notifies the successful tenderer in writing that its tender has been accepted (see format of letter in Annex D08), as well simultaneously in writing informs the unsuccessful tenderers. It draws attention to any arithmetical errors which were corrected during the evaluation process.

This notification to the successful tenderer implies that the validity of the successful tender is automatically extended for a period of 60 days from the date of notification of award of the contract. Unless there is challenge of the award decision by any of the unsuccessful tenderers within 15 days from the date of notification, the Contracting Authority sends the contract to the tenderer for signature.

Where a contract is awarded under a financing agreement which had not been concluded at the time the tender procedure was launched, the Contracting Authority must not notify the successful tenderer before the financing agreement has been concluded.

6.3.11.2	Contract Signature

In preparing the contract for signature, the Contracting Authority must proceed as follows:

1)	use the contract dossier prepared following acceptance of the recommendation of the Evaluation Committee.

2)	sign all copies of the contract, making conclusion of the contract subject there not being a challenge within 15 days, say.

3)	send all three signed copies of the contract to the successful tenderer, who must countersign them within 15 days of receipt (and, in any case, before the expiry of the tender validity period) and return two copies to the Contracting Authority together with the advance guarantee required in the contract. If the successful tenderer fails to do this within the specified deadline or indicates at any stage that it is not willing or able to sign the contract, the tenderer cannot be awarded the contract and forfeits its tender guarantee. The contract preparation process must be restarted from step 1 with a new contract dossier prepared using the tender which has the next lowest price or which is the next most economically advantageous (provided that that tender is technically compliant and is within the maximum budget available for the contract)

4)	On receipt of the two signed copies from the successful tenderer, the Contracting Authority sends one to the financial service in charge of payments and the second copy is sent to the European Commission. A copy of the signed contract must be sent to the Project Manager.

| ( | The Contracting Authority and the Contractor must note on the contract the date on which they sign it. Subject to any conditions imposed, the contract takes effect on the date of the later signature. A contract cannot cover earlier works/supplies/services or enter into force before this date. |
| --- | --- |

6.3.11.3	Publicising the Award of the Contract

As indicated above, the Contracting Authority informs candidates and tenderers of decisions reached concerning the award of the contract as soon as possible, including the grounds for any decision not to award a contract for which there has been competitive tendering or to recommence the procedure.

Once the contract has been awarded, the Contracting Authority must prepare a contract award notice (using the template in Annex D09) and send it, where possible in electronic form and within 48 days of the award decision, to the OJEU for publication. In addition, the Contracting Authority must record all statistical information concerning the contract award procedure including the contract value, the names of the other tenderers and the successful tenderer.

## 6.4	Restricted Procedure for Contracts above the EU Threshold

In cases appropriate to the characteristics of the contract, a Restricted Procedure may be used.

In exceptional cases justified by the special characteristics of certain projects, a restricted tender procedure may be used. The European Commission must give its prior approval to the use of this approach and will provide technical support to the Contracting Authority on a case-by-case basis.

The publication of a contract notice in the OJEU remains mandatory.

The restricted procedure begins with a short-listing phase which must be specially designed for each project. On the basis of the outcome of this short-listing phase, the Contracting Authority draws up a list of firms that will be invited to tender.

The Contracting Authority sends a letter of invitation to tender accompanied by the tender dossier only to the candidates on the shortlist.

In this procedure, there must be a minimum of 40 days (26 days where the Contracting Authority has published a PIN) between the date of dispatch of the letters of invitation to tender and the deadline for receipt of tenders.

| ( | The measures applicable to an open procedure apply by analogy to the restricted procedure for works contracts. |
| --- | --- |

## 6.5	Local open Procedure for Contracts below the EU Threshold

In this case, the procurement notice is published only in the beneficiary country. It may be published on the website of the Contracting Authority and/or in the official Procurement Bulletin issued by the government, or in another appropriate media. As the cost of publishing the full procurement notice in the local media may be prohibitive, the template in Annex C3 gives the minimum information which must be included in a local advertisement. However, the full procurement notice must be available from the address referred to in the advertisement, together with the tender dossier. This publication is under the responsibility of the beneficiary country.

Note that a local open tender procedure must provide other eligible contractors with the same opportunities as local firms. No conditions seeking to restrict the participation of other eligible contractors are allowed (e.g., obliging such firms to be registered in the beneficiary country or to have won contracts there in the past).

In this procedure, there must be a minimum of 60 days (30 days if the estimated value is less than € 300, 000) between the date of publication of the procurement notice in the local press and the deadline for receipt of tenders.

|  | ( | The measures applicable to an international open procedure, as described previously, apply by analogy to the local open procedure. The Contracting Authority may require a tender guarantee. It may as well require documentary evidence only from the successful tenderer at the stage of awarding rather than to all bidders at the stage of selection. There’s no contract award notice but each tenderer has to be informed as per international tender. The public opening is optional if the estimated value is less than € 300, 000. |
| --- | --- | --- |

|  | ( | The Contracting Authority may award works contracts of a value of €5,000 or less on the basis of a single tender. Note that projects must not be split artificially to circumvent the procurement thresholds. |
| --- | --- | --- |

## 6.7	Modifying Works Contracts

Works contracts may need to be modified during their duration if the circumstances affecting project implementation have changed since the initial contract was signed. However, the application of the Directive and the requirements for equal treatment and transparency limit the changes that are possible without a further call for competition. Contract modifications must in any case be formalised through an addendum to the contract. Such an addendum must be signed by the contracting parties, unless they are explicitly allowed under the conditions of the contract.

Changes of address, changes of bank account and changes of auditor may simply be notified in writing by the contractor to the Contracting Authority, although this does not affect the right of the Contracting Authority to oppose the contractor's choice of bank account or auditor.

### 6.7.1	General Principles

The following general principles must always be respected:

A contractor's requests for contract modifications should not automatically be accepted by the Contracting Authority. Such requests must be properly substantiated. The Contracting Authority must examine the reasons given and reject requests which have little or no substantiation.

Contracts can only be modified within the lifetime of the contract; modifications cannot be made retroactively.

The purpose of the addendum must be closely connected with the nature of the project covered by the initial contract.

Major changes, such as a fundamental alteration of the Technical Specifications, cannot be made by means of an addendum.

The addendum must not alter the competition conditions prevailing at the time the contract was awarded.

Unit prices must be identical to those in the initial contract, unless the initial contract stipulates otherwise (i.e., there is a price-revision clause).

Any modification extending the performance period of the contract must be such that implementation and final payments can be completed before the expiry of the financing agreement under which the initial contract was financed.

Any modifications which require additional funding must have been foreseen in the Technical Specifications of the initial contract and can only be agreed before the expiry of the financing agreement under which the initial contract was financed. The additional funding must come from the same budget line as that used for the initial contract.

| ( | Under no circumstances can the Contracting Authority increase the budget of the initial contract or agree to/arrange for the purchase of equipment that was not covered in the Technical Specifications of the initial tender and subsequent contract. The only exception to this rule is for additional works not included in the initial contract but which have, through unforeseen circumstances, become necessary for the works initially foreseen to be carried out, provided that the award is made to the contractor already carrying out such work: – where such works cannot be technically or economically separated from the main contract without serious inconvenience for the Contracting Authority; – where such works, although separable from the performance of the initial contract, are absolutely necessary to its completion. This should remain exceptional and should not be used to cover deficiencies in the technical specifications of the tender dossier. However, the aggregate cost of contracts awarded for additional works must not exceed 50% of the amount of the main contract. |
| --- | --- |

| ( | Requests for contract modifications to works contracts must be made (by one contracting party to the other) allowing at least 30 days for the addendum to be signed before the end of the period of execution of the initial contract. |
| --- | --- |

### 6.7.2	Preparing an Addendum

In preparing the addendum, the Contracting Authority must proceed as follows:

1)	Use the standard template for an addendum (see Annex A07).

| ( | All references in the proposed addendum to article numbers and/or annexes to be modified must correspond to those in the initial contract. |
| --- | --- |

Any addendum modifying the budget must include a replacement budget showing how the full budget breakdown of the initial contract has been modified by this addendum (and any previous addenda). The following column headings should be used:

| Budget Item | Initial contract budget | Addendum 1 | (Addendum 2…) | Revised budget |
| --- | --- | --- | --- | --- |

| ( | If the budget is modified by the proposed addendum, the payment schedule must also be modified accordingly, taking into account any payments already made in the course of the contract. The payment schedule must not be modified unless either the budget is being modified or the contract is being extended. |
| --- | --- |

2)	Prepare a dossier comprising the following items:

a) Explanatory note (see template in Annex A6) providing a technical and financial justification for making the modifications in the proposed addendum b) Copy of the contractor's request for (or agreement to) the proposed modifications c) Copy of the financing agreement authorising the project d) Copy of the initial contract and any subsequent addenda e) Copy of the tender announcements (contract forecast and contract notice), Site Visit Report, Tender Opening Report, Evaluation Report and any other relevant information f) Three copies of the proposed addendum, which is based on the standard addendum template (see Annex A07) and includes any revised annexes.

3)	Sign all copies of the addendum and send the addendum dossier to the European Commission for approval and endorsement.

4)	Send the three signed copies of the addendum to the contractor, who must countersign them within 30 days of receipt and return two copies to the Contracting Authority together with any financial guarantee required in the addendum.

5)	On receipt of the two signed copies from the successful tenderer, the Contracting Authority sends one to the financial service in charge of payments and the second copy is sent to the European Commission. A copy of the signed addendum must be sent to the Project Manager.

| ( | The Contracting Authority and the Contractor must note on the addendum the date on which they sign it. The addendum takes effect on the date of the later signature. An addendum cannot cover earlier works/supplies/services or enter into force before this date. |
| --- | --- |

Section 7.	 Grant Contracts

## 7.1 Introduction

### 7.1.1 Definition

A grant is a direct payment of a non-commercial nature by the Contracting Authority to a specific beneficiary to implement an action intended to help achieve an objective forming part of a European Union policy.

In certain cases the grant may also finance the operation of a body which pursues an aim of general European interest or has an objective forming part of a European Union policy.

A body pursuing an aim of general European interest is: a European body involved in education, training, information or research and study in European policies or a European standards body; or a European network representing non-profit bodies active in the Member States or in the candidate countries and promoting principles and policies consistent with the objectives of the Treaties.

The body signing a grant contract is known as the grant beneficiary and should not be confused with the final beneficiary of the operation which is generally the target group or the people living in the country where the operation is taking place.

Grants should be distinguished from other legal commitments entered into in the external action framework and the correct rules applied accordingly. A grant contract can be distinguished from a procurement contract in a number of ways:

- A grant is made for an operation which is proposed to the Contracting Authority by a potential beneficiary (an “applicant”) and falls within the normal framework of the beneficiary's activities. This is in contrast to a procurement contract, in which the Contracting Authority draws up the terms of reference for a project it wants to be carried out.

- A contract should be classified as a public procurement contract rather than a grant contract if its subject matter relates primarily or broadly to the administrative functions of the Contracting Authority.

- A grant beneficiary is responsible for implementing the operation and retains ownership of its results. By contrast, under a procurement contract, it is the Contracting Authority which owns the results of the project and closely supervises its implementation.

- A grant beneficiary generally contributes to the financing of the action except in cases where full Community financing is essential for the action to be carried out. In the case of procurement contracts, however, the contractor does not normally contribute financially.

- A grant can only be made for an operation whose immediate objective is non-commercial. Under no circumstances may the grant give rise to profits (i.e., it must be restricted to the amount required to balance income and expenditure for the action). Grant beneficiaries are generally non-profit-making. The fact that a body is non-profit-making does not necessarily mean that a contract to be concluded with it will be a grant contract; non-profit bodies can also tender for procurement contracts. The action itself must be of a non-commercial nature.

- The amount of a grant is based on the actual eligible cost of the action calculated on the basis of the eligible costs actually incurred by the beneficiary. The amount of a procurement contract, on the other hand, represents a price fixed in accordance with competitive tendering rules.

Payments made to the delegatee bodies of the Commission referred to in Articles 54, 55 and 185 of the Financial Regulation are not grants.

Financing agreements concluded with beneficiary States do not constitute grants. If an operation involves an agreement with the beneficiary State (or a ministry or other State central administrative body), this must be in the form of a financing agreement and not a grant contract.

Grants paid under financing or related agreements with the bodies referred to in Articles 54, 55 and 185 of the Financial Regulation are covered by the rules set out below.

If there is any doubt about whether an operation should be considered as a grant, the Contracting Authority may refer to the European Commission for advice.

(	A grant contract cannot be signed unless the action concerned meets the definition of a grant according to the abovementioned criteria. An action eligible to receive grant funding must be clearly identified. No action may be split for the purpose of evading compliance with the rules laid down in this Guide.

The Contracting Authority, which is always specified in the Call for Proposals notice, is the authority empowered to conclude the contract.

### 7.1.2 Overview

Where grant contracts financed by the European Community are concluded in the course of cooperation with third countries, procedures are governed by the following legal framework:

- the Financial Regulation No 1605/2002 of 25 June 2002 applicable to the general budget of the European Communities and in particular Title VI of Part One, on grants, and Title IV of Part Two, on External Actions;

- Regulation No 2342/2002 of 23 December 2002 laying down detailed rules for the implementation of the abovementioned Financial Regulation;

- the regulations or decisions of the Council, referred to as “basic acts” in the Financial Regulation and this Guide, and other specific instruments relating to the various cooperation programmes.

The following are also applicable:

- The Framework Agreement signed by the EC and the beneficiary country concerned, where such an agreement exists. This agreement contains the rules for administrative cooperation between the two bodies for the implementation of external aid.

- The Financing Memorandum signed by the EC and the beneficiary country concerned for the EC-funded programme, where such an agreement exists. This sets out the programme objectives and budget.

- The standard documents and templates in the annexes to this Guide, which include the standard grant contract for external actions (see Annex E3E), and standard documents for Calls for Proposals (see Annexes E1, E2 & E3).

The rules and procedures established by the European Commission for grant management under the EC external actions programmes are consolidated in this Guide and must be applied when implementing all these programmes.

Grants are awarded by the Contracting Authority designated in the financing memorandum, i.e., the government or an entity of the beneficiary country with legal personality with which the European Commission establishes the financing agreement.

Before launching calls for proposals, the Contracting Authority must submit the annual work programmes, call for proposals notices and Guidelines for Applicants to the European Commission for approval.

On the basis of decisions thus approved, and in close consultation with the European Commission, the Contracting Authority is responsible for publishing annual work programmes, issuing calls for proposals, receiving proposals, chairing evaluation sessions and deciding on the results of calls for proposals. The Contracting Authority must submit the Evaluation Report, details of the proposed grants and, where appropriate, the draft contracts to the European Commission for endorsement.

Once the grant has been approved, the Contracting Authority will sign the contract and notify the European Commission accordingly. As a general rule, the European Commission will be represented as an observer when proposals are opened and evaluated and must always be invited.

In the case of international calls for proposals, the Contracting Authority must submit the annual work programmes, call for proposals notices, Guidelines for Applicants and grant award notices to the European Commission for publication.

### 7.1.3 Eligibility criteria

#### 7.1.3.1 Nationality rule

Grant contract procedures are open on equal terms to all legal persons coming within the scope of the Treaty establishing the European Community and, in accordance with the specific provisions in the basic instruments governing the cooperation sector concerned, to all such legal persons of the beneficiary third countries or of any other third country as are expressly mentioned in those instruments. See Annex A2 for the list of countries for each aid programme or instrument.

By way of exception, depending on the nature of the action or the objective pursued by the applicant, natural persons may receive grants if this is provided for in the basic act.

For the purposes of verifying compliance with the nationality rule, the Call for Proposals requires applicants to state the country of which they are nationals by presenting the documents required under that country's law.

If the Contracting Authority suspects that an applicant has only a registered office in an eligible country or state and that the nationality of the applicant is ineligible, the applicant is responsible for demonstrating effective and continuous links with that country's economy. This is to avoid awarding contracts to organisations whose nationalities are ineligible but which have set up 'letter box' organisations in an eligible country to circumvent the rules on nationality.

#### 7.1.3.2 Exceptions to the nationality rule

In duly substantiated exceptional cases, the nationality rule may be waived.

The possibility of waiver must be specifically mentioned in the Guidelines for Applicants and is subject to the specific prior approval of the European Commission.

#### 7.1.3.3 Grounds for exclusion

Natural or legal persons are not entitled to participate in Calls for Proposals or be awarded grants if:

- they are bankrupt or being wound up, are having their affairs administered by the courts, have entered into an arrangement with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations;

- they have been convicted of an offence concerning professional conduct by a judgement which has the force of res judicata (ie, against which no appeal is possible);

- they are guilty of grave professional misconduct proven by any means which the Contracting Authority can justify;

- they have not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those of the country of the Contracting Authority or those of the country where the action is to take place;

- they have been the subject of a judgement which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the Communities' financial interests;

- they have been declared to be in serious breach of contract for failure to comply with their contractual obligations following a procurement procedure or another grant award procedure financed by the Community budget.

Natural or legal persons are also excluded from participation in Calls for Proposals or the award of grants if, at the time of the call for proposals, they:

- are subject to a conflict of interest;

- are guilty of misrepresentation in supplying the information required by the Contracting Authority as a condition of participation in the call for proposals or fail to supply this information;

- have attempted to obtain confidential information or influence the Evaluation Committee or the Contracting Authority during the evaluation process of the current or previous Calls for Proposals.

In the cases referred to in points (a), (c), (d), (f), (h) and (i) above, the exclusion applies for a period of two years from the time when the infringement is established. In the cases referred to in points (b) and (e), the exclusion applies for a period of four years from the date of notification of the judgement. Applicants must supply with their applications a sworn statement that they do not fall into any of the above categories (a) to (f). The same conditions apply to procurement done by grant beneficiaries. The Contracting Authority may, before signing the contract, request certificates in support of the sworn statement.

## 7.2 Basic rules for grants

The award of grants is subject to the principles of programming, transparency and equal treatment. They may not be cumulative or awarded retrospectively and they must involve co-financing.

The grant may not have the purpose or effect of producing a profit for the beneficiary.

Compliance with rules of sound management is required.

### 7.2.1  Programming

Grants must be programmed by the Contracting Authority with clearly defined objectives .

The annual programme must be published, by budget heading or programme, on the Internet site of the Contracting Authority (or any other appropriate media) and of the Commission as appropriate, following the work programme template in Annex E01.

The annual work programme must specify the legal basis, the objectives, the schedule of calls for proposals with the indicative amount and the results expected.

Any substantial change in the work programme must also be published in the same conditions as the initial work programme.

The work programme will be adopted by the Contracting Authority and published on its Internet site (or any other appropriate media) and, in the case of international calls for proposals, on the grants Internet site of the Commission not later than 31 January of each financial year.

The Contracting Authority must submit the work programme to the European Commission for approval before publishing it.

### 7.2.2 Transparency

The availability of grants must be publicised widely and in an easily accessible way. The work programme will accordingly be implemented through the publication of calls for proposals save in duly substantiated exceptional cases of urgency or where the characteristics of the beneficiary make it the sole choice for a given action. All grants awarded in the course of a financial year will be published annually with due observance of the requirements of confidentiality and security.

### 7.2.3 Equal treatment

The grant award process must be completely impartial. This means notably that the proposals must be selected by an Evaluation Committee, with the advice of assessors where appropriate, using the published eligibility and evaluation (selection and award) criteria.

### 7.2.4  Non-cumulation

No single beneficiary may receive more than one grant financed by the European Community for a given action. A beneficiary may be awarded only one operating grant financed by the European Community per financial year.

### 7.2.5  Non-retroactivity

Grants may, as a rule, only cover costs incurred after the date on which the grant contract is signed. A grant may be awarded for an action which has already begun only where the applicant can demonstrate the need to start the action before the contract is signed.

In such cases, expenditure incurred prior to the deadline for submitting proposals or, in the case of direct award, the date of submission of the grant application, and if applicable the date of signature of the relevant financing agreement, will not be eligible for financing. No grant may be awarded retroactively for actions already completed .

The contract for an operating grant may not be signed more than four months after the start of the beneficiary's budget year. Expenditure incurred before the grant application was lodged or before the start of the beneficiary's budget year will not be eligible for financing.

### 7.2.6  Co-financing

Grants may not as a rule finance the entire cost of the action, with the following exceptions.

The financing of an action in full may be authorised in the following cases, save where prohibited by the basic act:

- humanitarian aid, including assistance for refugees, uprooted persons, rehabilitation and mine clearance;

- aid in crisis situations within the meaning of article 168 paragraph 2 of the Implementing Rules of the Financial Regulation;

- actions to protect health or the fundamental rights of peoples;

- actions resulting from the implementation of financing agreements or actions with international organisations.

The Contracting Authority must be in a position to show that financing in full is essential to carry out the action in question and must substantiate its award decision accordingly.

Grants may not finance the entire operating expenditure of a beneficiary body. When operating grants are renewed, they will be gradually decreased.

### 7.2.7  Non-profit

Grants may not have the purpose or effect of producing a profit for the beneficiary. Profit is defined as:

- a surplus of aggregate receipts over costs for the action in question at the time when the request is made for final payment of a grant for an action. 	

However, in the case of actions designed specifically to strengthen the financial capacity of a beneficiary, profit is defined as the distribution of the surplus revenue resulting from its activity to the members making up the beneficiary body, leading to their personal enrichment.

- A surplus balance on the operating budget of a body in receipt of an operating grant.

The above provisions do not apply to study, research or training scholarships paid to natural persons, nor to prizes awarded following contests.

### 7.2.8  Rules of sound management

- Availability of funds: before initiating any grant award process, the funds must be available.

- Use of standard documents: the standard grant contract and other document formats (as provided in the Annexes) must be used according to the rules.

- Record keeping: written records of the entire evaluation procedure must be kept confidential and retained by the Contracting Authority for seven years after the grant award decision. These must include the originals of all proposals submitted, together with the corresponding Call for Proposals and any related correspondence.

- Procurement of services, supplies or works for a grant-funded action: if the implementation of an action involves the procurement of services, supplies or works by the grant beneficiary, the contract award procedures specified in section 5.8 of this Guide must be applied for each procurement contract.

- Any deviation from the procedures set out in this section 5 requires the prior approval of the European Commission.

## 7.3 Award procedures

### 7.3.1 Call for Proposals

(	Grants must be awarded following the publication of a Call for Proposals except in the cases listed in section 7.3.2 below.

#### 7.3.1.1 International or local call for proposals

A local call for proposals (see section 7.5) may be launched if at least one of the following criteria is met:

- the overall budget for the programme is under €2,000,000;

- the maximum size of each grant to be awarded within the programme is under or equal to €100,000;

- the grant programme is reserved exclusively for national applicants of the beneficiary country(countries).

In the above cases, the Contracting Authority has the option of an international call for proposals. In all other cases, an international call for proposals is compulsory.

An international call for proposals must also be published locally where it is not organised by a service of the European Commission headquarters.

#### 7.3.1.2 Open or restricted call for proposals

Calls for proposals are open as a rule and all applicants are free to submit a grant application form in response to the Guidelines for Applicants published on the Internet (see section 7.4.2). However, in the case of an international call for proposals and where warranted by the technical nature of the field or the expected number of proposals, the Contracting Authority may organise a restricted call for proposals in accordance with the rules in section 7.6: potential applicants are short listed on the basis of a preliminary proposal (see Annex E3F) in response to Guidelines for Applicants published on the Internet (see section 7.4.2.). Only the short listed applicants will be invited to submit a grant application form.

The Contracting Authority must seek prior approval from the European Commission for the use of a restricted call for proposals.

#### 7.3.1.3 Partnerships

Grant contracts may form part of framework partnership agreements with a view to establishing long-term cooperation with the Contracting Authority. Framework agreements specify the common objectives, the nature of actions planned on a one-off basis or as part of an approved annual work programme, the procedure for awarding specific grants, in compliance with the principles and procedural rules in this Guide, and the general rights and obligations of each party under the specific contracts. The duration of framework agreements may not exceed four years. Framework partnership agreements are treated as grants for the purposes of the award procedure.

Partnerships of this nature (between the Contracting Authority and the beneficiary) are rare and not to be confused with the possibility frequently used by beneficiaries of carrying out an action in partnership with one or more other organisations as their “partners”.

In the case of framework partnership agreements, the Contracting authority may pre finance 100% after a positive assessment has been carried out.

The Contracting Authority must seek prior approval from the European Commission for the use of a framework partnership agreement.

### 7.3.2 Direct award

The Contracting Authority must seek prior approval from the European Commission for the use of the direct award procedure.

Only in the following circumstances is it unnecessary to organise a Call for Proposals before awarding grants:

- In duly substantiated exceptional cases of urgency, i.e., where unforeseeable events oblige the Contracting Authority to act with an urgency incompatible with the periods laid down for Call for Proposals procedures described in section 7.3.1. The circumstances cited as grounds for extreme urgency must in no way be attributable to the Contracting Authority (e.g., imminent expiry of the financing agreement).

Actions carried out in crisis situations as referred to in Article 168(2) of the Financial Regulation implementing rules are considered to satisfy the test of extreme urgency. The authorising officer by delegation, where appropriate in consultation with the other authorising officers by delegation concerned, establishes that a situation of extreme urgency exists and reviews his decision regularly having regard to the principle of sound financial management. 	

Only the competent services of the European Commission may declare the existence of a crisis situation.

- Where the grant is awarded to a body with a de jure or de facto monopoly, duly substantiated in the Contracting Authority's award decision.

For these purposes, “de facto” or “de jure” monopoly means that the beneficiary, which may be a consortium:

-	has exclusive competence in the field of activity and/or geographical area to which the grant relates pursuant to any applicable law; or

-	is the only organisation (i) operating or (ii) capable of operating in the field of activity and/or geographical area to which the grant relates by virtue of all considerations of fact and law.

- Where the grant is to be awarded to a body identified in the relevant basic act as a recipient of a grant.

- Where the grant is to be awarded to an international organisation for the implementation by joint management of a specific action which is in keeping with that organisation's mandate and jointly identified by it and the Contracting Authority.

In all cases, the Contracting Authority must prepare a report explaining the manner in which the grant beneficiaries were identified and the grant amounts established, and the grounds for the resulting award decision. The procedures described in section 7.4.10 must be followed by analogy, with the aforementioned report being included in the contract dossier.

## 7.4 International Call for Proposals

### 7.4.1 Publicity

In order to ensure the widest possible participation and the requisite transparency, a Call for Proposals notice must be published for every international Call for Proposals. It must be prepared by the Contracting Authority using the template given in Annex E2.

The notice must clearly identify the Contracting Authority and the purpose of the Call for Proposals.

The Call for Proposals notice is published in the Official Journal of the European Union, C series, on the Internet and in any other appropriate media (specialised press, local publications, etc…).

The Contracting Authority is responsible for preparing the Call for Proposals notices and for submitting them in electronic form to OJEU for publication.

### 7.4.2 Drafting and contents of the Guidelines for Applicants

The Guidelines for Applicants (which include an Application Form and other annexes) explain the purpose of the Call for Proposals, the rules regarding the eligibility of applicants and partners, the types of action and costs which are eligible for financing, and the evaluation criteria. They also contain instructions on how to fill in the application form, what to annex to it and what procedures to follow for applying. They give information on the evaluation process that will follow (including an indicative timetable) and the contractual conditions which will apply to successful applicants.

The Guidelines should set out very clearly and in detail the objectives and priorities of the call for proposals, and give particular attention to the eligibility criteria. The information published in this connection will subsequently become binding on the Evaluation Committee. The evaluation grid must be included in the Guidelines and cannot be changed.

The Application Form to be completed by the applicants is included with the Guidelines. It comprises the following parts:

- Information about the action proposed, including its budget

- Information about the applicant

- Information about any partners.

The Guidelines should be drafted for each Call for Proposals using the template provided in Annex E3.

The Contracting Authority must submit the Guidelines for Applicants to the European Commission for approval prior to issue.

The Guidelines for Applicants are published on the Internet together with the Call for Proposals notice, and are also available in hard copy from the Contracting Authority. They should be available in the languages appropriate to the context of the Call for Proposals.

### 7.4.3 Eligibility and evaluation criteria

#### 7.4.3.1 Eligibility criteria

The eligibility criteria relate to three different aspects:

- Eligibility of the applicant: this refers to the applicant's legal and administrative status - see sections 1.3 (Rules on nationality) and 7.1.4.3 (Grounds for exclusion).	 

If a Call for Proposals relates to actions to be implemented in partnership, the minimum number of partners and the eligibility criteria applicable to each of the partners of the lead applicant must be specified. The eligibility criteria applicable to the lead applicant and to the partners may differ.

- Eligibility of the action: this refers to the types of activities, sectors or themes and geographical areas covered by the Call for Proposals.

- Eligibility of costs: this details the types of costs which may be financed. In brief they must be real costs, which will actually be incurred and are necessary for carrying out the project.

#### 7.4.3.2 Evaluation criteria: selection and award

The evaluation criteria consist of selection and award criteria, all of which are defined in the evaluation grid.

- The published selection criteria are designed to assess the applicant's financial and operational capacity to complete the proposed action: the applicant must have stable and sufficient sources of funding to maintain its activity throughout the period during which the action is being carried out and to participate, where appropriate, in its funding. Applicants and their partners must also have the necessary professional competencies and qualifications to complete the proposed action.	

The verification of financial standing does not apply to natural persons in receipt of scholarships, Member State public authorities or international organisations.

- The published award criteria are used to assess the quality of proposals against the set objectives and priorities, so that grants are awarded to the actions which maximise the overall effectiveness of the call for proposals. They should enable the Contracting Authority to select proposals which it can be confident will comply with its objectives and priorities and guarantee the visibility of the Community financing.	

The award criteria relate, in particular, to the relevance of the action and its compatibility with the objectives of the grant programme under which the Call for Proposals is being financed, to the quality, expected impact and sustainability of the action, and to its cost-effectiveness.

All eligibility and evaluation criteria specified in the Call for Proposals must be applied as they stand and cannot in any circumstances be changed in the course of the procedure. The criteria should be precise, non-discriminatory and not prejudicial to fair competition. The evaluation will be based on the standard administrative compliance and eligibility grid and evaluation grid - see the templates given in Annexes E7 and E10.

### 7.4.4 Additional information before the deadline for submission of proposals

During the time between publication and the deadline for the submission of proposals, applicants should be able to ask questions to help them fill in the form and put together their applications. The Contracting Authority should therefore provide a contact point to which questions may be addressed. Applicants may submit questions of substance in writing up to 21 days before the deadline for the submission of proposals. The Contracting Authority must reply to all such questions at least 11 days before the deadline for submission of proposals.

In the interests of transparency and equal opportunity, the answer provided to one applicant on points which may be of interest to the other applicants should be made available to all the others. The easiest - and recommended - way to achieve this is to publish on the Internet, where appropriate, a table of questions and answers along with the Guidelines for Applicants. This must be updated regularly until 11 days before the deadline for submission of proposals.

### 7.4.5 Deadline for submission of proposals

Proposals must reach the Contracting Authority at the address and, at the very latest, by the date and time indicated in the Call for Proposals. The deadline for submission must be long enough to allow for high-quality proposals. Experience shows that too short a deadline may prevent would-be applicants from submitting proposals or cause them to submit incomplete or ill-prepared proposals. The deadline for submissions must be at the close of business of a working day in the country in which the Contracting Authority is situated (e.g., 16:00 local time on a Tuesday).

The minimum period between the date of publication of the Call for Proposals and the deadline for receipt of proposals is 90 days. However, in exceptional cases, and with the prior authorisation of the European Commission, a shorter deadline may be allowed.

A call for proposals may set more than one deadline for submissions, either to allow for staggered processing or in cases where the actions to be financed cannot by their nature be planned long in advance. In this case, proposals received by the Contracting Authority after one deadline are automatically carried over to the next.

### 7.4.6 Submission of proposals

Each proposal must be placed in a sealed parcel or envelope bearing:

- the address for submission of proposals indicated in the Call for Proposals;

- the reference number of the Call for Proposals to which the applicant is responding;

- the full name and address of the applicant;

- the words "Not to be opened before the opening session" written in the language of the Call for Proposals and in the local language;

Applications must be sent by registered mail or courier service or delivered by hand. They must contain the original and the number of copies of the completed application form, budget and logical framework as well as other supporting documents required in the call for proposals. The application form, budget and logical framework should also be provided in electronic format where so required in the call for proposals.

Applicants must provide a sworn statement on the application form that:

- they (and their partners as applicable) do not fall into any of the categories mentioned in points (a) to (f) of section 7.1.4.3;

- they possess the sources of funding and professional competencies and qualifications referred to in section 7.4.3.2.

They must also include with their application the profit and loss account, the balance sheet for the last financial year for which the accounts have been closed and any other supporting document requested.

In the case of actions where the cost to be financed exceeds €300,000 and operating grants of over €75,000, the application must be accompanied by an external audit report produced by an approved auditor. The report must certify the accounts for the last financial year available and give an assessment of the financial viability of the applicant within the meaning of section 7.4.3.1. Depending on its analysis of management risks, the Contracting Authority may exempt public bodies from that obligation. The obligation does not extend to international organisations.

Originals of the requested supporting documents must be provided or, if none are available, copies certified true by an approved independent agency. If the supporting documents are written in a language other than the language(s) of the call for proposals, a faithful translation into one of those languages must be attached which will apply for the purposes of interpreting the proposal.

### 7.4.7 The Evaluation Committee

#### 7.4.7.1 Composition

Proposals are opened and evaluated by an Evaluation Committee appointed by the Contracting Authority comprising a non-voting Chairman, a non-voting Secretary and an odd number of voting members (minimum of three). The voting members must possess the technical and administrative capacities necessary to give an informed opinion on the proposals.

The Evaluation Committee (i.e., the Chairman, the Secretary and the voting members), must be nominated on a personal basis by the Contracting Authority. The composition of the Evaluation Committee must be submitted for prior approval to the European Commission. The European Commission may nominate an observer to follow all or part of the proceedings of the Evaluation Committee. The participation of other observers must be authorised in advance by the European Commission.

The Evaluation Committee members should attend all meetings. Any absence must be recorded and explained in the Evaluation Report.

Any Evaluation Committee member who withdraws from the Evaluation Committee for whatever reason must be replaced following the standard procedure for appointing members of the Evaluation Committee, as explained in section 7.4.7.1. The chairman of the evaluation committee determines to what extent the evaluation process must be restarted. Such decision as well as any decision relating to the replacement of a committee member must be recorded and justified in the evaluation report.

All voting members of the Evaluation Committee have equal voting rights. The names and functions of all those involved in the evaluation process must be recorded in the Evaluation Report.

The Evaluation Committee should be formed early enough to ensure the availability of the designated members (and any observer nominated by the European Commission, in the case of decentralised ex-ante control) during the period necessary to prepare and conduct the evaluation process. The evaluation of proposals should be completed as soon as possible.

#### 7.4.7.2 Use of assessors

Where the proposals received are particularly numerous or highly technical, it may not always be possible for the Evaluation Committee to examine each one in detail. If necessary, all or part of this detailed examination may be carried out by assessors so that the Evaluation Committee may conduct its deliberations on the basis of their assessments.

Assessors work under the supervision of the chairman of the Evaluation Committee. They may only be used for the stages of the evaluation procedure described in detail in sections 7.4.8.3 (Assessment of Administrative Compliance and Eligibility) and 7.4.8.3 (Assessment of Technical and Financial Quality). Although the same assessors may be used for both stages, different types of expertise are required for the two assessments and it is recommended to use different persons wherever possible.

- With respect to the assessment of administrative compliance and eligibility, the task of assessors consists of carrying out a screening of each proposal on the basis of the relevant grid (see Annex E7). Each proposal need only be screened by one assessor.	

It would be preferable to delegate this work to officials or other staff members of the Contracting Authority. Outside assessors may be recruited as required.

- With respect to the assessment of technical and financial quality, the task of assessors consists of carrying out a written assessment of each proposal on the basis of the published evaluation grid (see Annex E10). At least two assessors must assess each proposal, working independently of each other.	

The external assessors must have an in-depth knowledge of the issues covered by the grant programme concerned. Their expertise should be verified on the basis of their CVs. A minimum of five years' experience of a particular issue should be expected.

The assessors are selected by the Contracting Authority. The list must be submitted for approval to the European Commission.

(	Assessors are not members of the Evaluation Committee but may attend its meetings as observers to present the results of their assessments and answer any questions from committee members.

#### 7.4.7.3 Impartiality and confidentiality

All members of the Evaluation Committee, any observers and any assessors must sign a Declaration of Impartiality and Confidentiality (see Annex A4). Any Evaluation Committee member, observer or assessor who has a potential conflict of interests due to a link with any applicant must declare it and immediately withdraw from the evaluation. He will be excluded from participating further in any capacity in the evaluation meetings.

There is a conflict of interests where the impartial and objective exercise of the functions of a member or observer of the Evaluation Committee or of an assessor is compromised for reasons involving family, emotional life, political or national affinity, economic interest or any other shared interest with an applicant.

(	No information about the examination, clarification, evaluation or comparison of proposals or decisions about the grant award can be disclosed. Any attempt by an applicant to influence the process in any way (whether by initiating contact with members of the Evaluation Committee/assessors or otherwise) will result in the immediate exclusion of its proposal from further consideration and in its exclusion from participating in calls for proposals for a period of two years.

The proceedings of the Evaluation Committee, from the opening of proposals to the conclusion of its work, are conducted in camera and are confidential.

In order to maintain the confidentiality of the proceedings, participation in Evaluation Committee meetings is restricted to the members of the Evaluation Committee, any assessors designated by the Contracting Authority and any authorised observers.

Apart from the copies given to any assessor(s), the proposals should not leave the room/building in which the committee meetings take place before the conclusion of the work of the Evaluation Committee. They should be kept in a safe place when not in use.

#### 7.4.7.4 Responsibilities of the Evaluation Committee members

The Chairman is responsible for supervising the work of assessors, co-ordinating the evaluation process in accordance with the procedures in this Guide and ensuring its impartiality and transparency. The voting members of the Evaluation Committee have collective responsibility for decisions taken by the Committee. The Secretary to the Committee is responsible for carrying out all administrative tasks connected with the evaluation procedure. These will include:

- circulating and collecting the Declarations of Impartiality and Confidentiality;

- supervising the opening session;

- ensuring that evaluation grids are completed and made available in good time to the members of the Evaluation Committee;

- keeping and filing the minutes of all meetings of the Evaluation Committee; and

- registering attendance at meetings and compiling the Evaluation Report and its supporting annexes.

With the agreement of the other Evaluation Committee members, the Chairman may communicate in writing with applicants whose proposals require clarification, offering them the opportunity to respond by fax within a deadline to be fixed by the Committee.

Any request for clarification requiring communication with the applicants during the evaluation process must be conducted in writing (by fax or letter) and signed by both the Chairman and the Secretary of the Evaluation Committee. Copies of any such communication must be annexed to the Evaluation Report.

### 7.4.8 Stages in the evaluation process

The evaluation process starts with the receipt of the proposals by the Contracting Authority, and ends with the decision to award grants to the selected applicants. The procedure is set out below.

#### 7.4.8.1	Receipt and registration of proposals

On receiving proposals, the Contracting Authority must register them and provide a receipt for those delivered by hand (see template in Annex E4). The envelopes containing the proposals must remain sealed and be kept in a safe place until they are opened.

#### 7.4.8.2	Opening

All proposals should be opened in an opening session at which the registration details will be checked and completed and the proposals numbered (whether or not they were received before the deadline for submission of proposals). The secretary to the Evaluation Committee supervises the opening session and requests the assistance of other staff of the Contracting Authority as need be.

The registration of proposals should contain the following information:

- registration number of proposal

- date of arrival

- the applicant's name and address.

For each proposal,

- the original is kept safely in the archives of the Contracting Authority;

- the copies are distributed to the evaluators and, where appropriate, to the assessors.

(	Following the opening session, the Evaluation Committee meets to decide on any contentious case and sign the Proposal Opening Report, which includes the minutes of the Proposal Opening Session (see template in Annex E5). This must state:

- the date, time and place of the session;

- the persons present;

- the names of the applicants who submitted proposals within the stipulated deadline; and

- the names of the applicants who submitted proposals after the stipulated deadline.

The Contracting Authority must send an acknowledgement letter as soon as possible after the end of the opening session. The acknowledgement letter (see template in Annex E6) includes a statement informing the applicant whether or not the application was received within the deadline.

#### 7.4.8.3	Assessment of administrative compliance and eligibility

This assessment must be carried out using the administrative compliance and eligibility grid (see Annex E7) and the criteria set out in the Guidelines for Applicants. Under no circumstances may assessors or members of the Evaluation Committee change the administrative compliance and eligibility grid.

- Administrative compliance: is the dossier complete? Incomplete dossiers will be disqualified from the evaluation process unless the evaluation committee decides to ask for missing documents or formal corrections. This decision has to be applied equally to all applicants.

- Eligibility: are the applicant, the partners and action eligible? This is assessed according to the criteria set out in the Guidelines for Applicants. Ineligible proposals will not be considered further.

The administrative compliance and eligibility grid (see Annex E7) must be used to record the compliance of each proposal with the requirements of the Guidelines for Applicants. The Contracting Authority must keep proposals not considered for further evaluation. The assessment of administrative compliance and eligibility may be carried out by members of the Evaluation Committee or by assessors. Each proposal will be examined by one person.

If the members of the Evaluation Committee do not carry out the assessment themselves, the Evaluation Committee must review the conclusions of the assessors on the basis of their completed administrative compliance and eligibility grids. In order to facilitate the Evaluation Committee's review of the assessments, the Secretary to the Evaluation Committee must ensure that two lists are drawn up: one containing proposals which are ineligible and one containing those deficient in administrative compliance. For each entry on a list, the grounds for ineligibility or administrative non-compliance must be identified.

When the call for proposals is organised by a headquarters service of the European Commission and in case of doubt on the eligibility of a proposal, the Evaluation Committee consults the European Commission delegation in the country where the proposed action is to take place.

(	The first part of the Evaluation Report covering administrative compliance and eligibility, which comprises the checklists, and the minutes of the session, must be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee (see template in Annex E11). It must state:

- the date, time and place of the session;

- the persons present;

- the names of any applicants whose proposals were found to be ineligible or non-compliant and the requirement(s) with which their proposals failed to comply.

The checklists must specify the missing documents and the eligibility criteria which have not been met and the reasons for this.

As soon as possible after the first part of the evaluation report being signed, the Contracting Authority must send a standard letter (see Annex E9) to those applicants who are ineligible and/or whose proposals have been found to be non-compliant, stating the requirement(s) with which their proposals failed to comply.

#### 7.4.8.4	Assessment of technical and financial quality

The quality of all eligible proposals must be assessed by at least two different people (who may be either committee members or assessors) on the basis of the evaluation grid (see Annex E10) containing the selection and award criteria. A score is given for each sub-heading. Comments are made for each heading on the basis of the questions and criteria used for that heading. In particular cases, comments may need to be made for specific subheadings. The overall assessment is based on the scores obtained under each subheading, added up by heading. The final score is the mathematical average of the scores given by those examining each proposal.

Where the call for proposals is organised by a headquarters service of the European Commission, a copy of each eligible proposal must be sent to the European Commission delegation in the country where the proposed action is to take place (see format of letter in Annex E8 or E16 for a restricted call for proposals) to enable it inter alia to give its opinion on the relevance of the action.

The Secretary will then prepare a list of all the proposals, ranked by score. The completed evaluation grids for each proposal and any opinions from delegations on the proposals must be sent to the Evaluation Committee.

#### 7.4.8.5	Conclusions of the Evaluation Committee

The Evaluation Committee will draw up its recommendations after the assessors have examined all the proposals. The Evaluation Committee must not change the assessors' scores or recommendations and must not alter the evaluation grids completed by the assessors.

The Evaluation Committee may decide to approve the ranking drawn up by the secretary on the basis of the assessors' report. If the Committee does not accept the scores awarded by the assessors to a proposal, for example on account of the opinion of the delegation concerned, it must nominate two of its voting members to prepare two new evaluation grids for the proposal concerned. The list will be amended on the basis of the scores from the new evaluations, which replace those completed by the assessors.

All such decisions must be recorded and fully substantiated in the Evaluation Report. The evaluation grids completed by the members of the Evaluation Committee must be kept with those completed by the assessors.

The Evaluation Committee's decisions are taken independently and in an advisory capacity. The Evaluation Committee must ultimately draw up a list of the proposals selected for financing, indicating the score obtained by each proposal, the amount of the proposed grant and the proportion of the eligible costs it is proposed to finance. Subject to the following considerations, this list is made up of the proposals obtaining the best scores, ranked by order, within the limits of the funds available under the call for proposals.

- The Committee may not allocate all the available funds if it finds that there are too few proposals of the quality required to receive a grant.

- The Committee may draw up a list by subject or geographical area specified in the Guidelines for Applicants.

- The Committee may reject a proposal if it has selected another which is of a similar nature but has been awarded a higher score.

(	The second part of the Evaluation Report, covering the technical and financial quality of proposals, is drawn up following the final meeting of the Evaluation Committee. It comprises the evaluation grids, the minutes of the evaluation sessions and, where applicable, the opinions of the European Commission delegations, and must be signed by all members of the Evaluation Committee. It must state:

- the date, time and place of the session;

- the persons present;

- the average score of each proposal;

- the successful applicants, the recommended grant amounts to be awarded to them and the proposed rate of financing of eligible costs;

- the unsuccessful applicants and reasons for non-selection.

The entire evaluation procedure is recorded in an Evaluation Report (see template in Annex E11) to be signed by the Chairman, the Secretary and all voting members of the Evaluation Committee and submitted to the Contracting Authority, which must decide whether or not to accept its recommendations. The Contracting Authority must then submit the Evaluation Report and any award proposals to the European Commission for approval.

Once this approval has been given, the Contracting Authority will commence awarding the grants (see section 7.4.10).

If the Contracting Authority confirms that there are no derogations (either in the special conditions or in the proposed contract annexes) from the standard contract conditions annexed to the Guidelines for Applicants, the European Commission's approval of the evaluation report and of the list of award proposals counts as a global endorsement of the corresponding contracts. The list must include all the elements necessary to conclude the contracts (including the applicant's details, grant amount and contract duration).

The award decision contains the subject and overall amount of the decision, the approved evaluation report and, where appropriate, the grounds for the decision by the Contracting Authority to depart from the recommendations made by the Committee in the report in respect of a particular proposal.

(	The entire procedure, from the drawing-up of the Call for Proposals to the selection of successful applicants, is confidential. The Evaluation Committee's decisions are collective and its deliberations must remain secret. The committee members are bound to secrecy.

The Evaluation Report, in particular, is for official use only and may be divulged neither to applicants nor to any party outside the authorised services of the Contracting Authority, the European Commission, OLAF and the European Court of Auditors.

### 7.4.9	Cancelling the call for proposals procedure

The Contracting Authority may decide to cancel the call for proposals procedure at any stage, but particularly in the light of the Evaluation Report, if:

- the call for proposals has been unsuccessful, ie, no worthwhile proposal has been received or there were no replies;

- the economic or technical data of the programme have been fundamentally altered;

- exceptional circumstances or force majeure render the normal conduct of the planned actions impossible;

- there have been irregularities in the procedure, in particular where these have prevented fair competition.

The responsibility for cancelling a call for proposals procedure lies with the Contracting Authority, with the prior approval of the European Commission.

In the event of cancellation of a call for proposals, applicants must be notified of the cancellation by the Contracting Authority but will not be entitled to compensation.

### 7.4.10		Awarding grants

#### 7.4.11	Notification of applicants

After the Contracting Authority and the European Commission have given their official approval to the final list of grants to be awarded, the Contracting Authority notifies the successful applicants in writing that their applications have been selected (see template in Annex E13).

It must also send the unsuccessful applicants a standard letter (see template in Annex E12) informing them that they have not been selected and specifying the reasons.

(	The letters to the successful applicants must be sent within 15 days of the award decision and letters to the unsuccessful applicants within a further 15 days of that.

#### 7.4.12	Contract preparation

In preparing grant contracts for each of the successful applicants on the final list, the Contracting Authority must proceed as follows:

- Use the modified contract template (see Annex E3E).

- Prepare a general background dossier containing information applicable to all grant contracts to be concluded as a result of the Call for Proposals, using the following structure:

- Explanatory note using the format in Annex A6;

- Copy of the Call for Proposals notice, Guidelines for Applicants, Proposal Opening Report, Evaluation Report, the list of grants to be awarded, the award decision and any other relevant information;

- Prepare a dossier for each grant contract to be concluded as a result of the Call for Proposals comprising the following items:

Three copies of the specific parts of the proposed contract prepared using the standard grant contract (see Annex E3E):

- Special Conditions (any additions to or derogations from the General Conditions must be specified in Article 7 of the Special Conditions, which is provided for that purpose)

- Description of the action

- General Conditions

- Budget for the action

- Procurement procedures to be used if services, supplies or works need to be procured as part of an action funded by a grant;

- Request for payment and financial identification form;

- Model audit certificate;

- Model financial guarantee.

(	The standard contract annexes containing the General Conditions, procurement procedures and models (see Annex E3E) must be reproduced without modification in every grant contract. The Special Conditions and Budget of the action must be completed by the Contracting Authority. The financial identification form must be completed by the successful applicant before the contract is signed by either party.

The budget proposed for the action by the successful applicant at the call for proposals stage must be corrected to remove any arithmetical errors or ineligible costs prior to signing the contract. The Description of the action is corrected accordingly if need be. Other clarifications or minor corrections may be brought to the Description of the action in so far as they relate to aspects clearly identified by the Evaluation Committee and would not call into question the grant award decision or be contrary to the equal treatment of applicants.

(	Any other alteration to the successful applicant's proposal or negotiation with him is prohibited.

Characteristics of the standard grant contract

- The standard grant contract recognises the beneficiary's independence of action and lays down simplified management rules accordingly. In particular, it allows the recipient to adapt or modify the action without the prior consent of the Contracting Authority provided that the modifications are not substantial and do not result in a change of more than 15% to any budget heading.

- The first pre-financing payment, which covers either 80% of the amount of the contract or 80% of the first annual budget, is paid after both parties have signed the contract and the Contracting Authority has received a standard payment request from the beneficiary. Subsequently, in the case of contracts for large amounts, an interim report (technical and financial) and payment request must be sent once a year as soon as 70% of the previous payment (and 100% of earlier ones) has been used up. A new payment of pre-financing is made on that basis. The balance is paid on approval of the final report. The beneficiary must not send documents in support of its request to the Contracting Authority but must keep them in case of inspection or audit for a period of seven years after payment of the balance.

- The Community finances a specific percentage of the total eligible costs rather than a particular part of the action. If at the end of the action, the actual eligible cost is lower than anticipated, the grant will be reduced proportionately.

- An external audit of the accounts of the action is attached to the request for payment of the balance were the grant is of more than €100,000, to a request for payment of additional pre-financing when the cumulated pre-financing exceeds €750,000, or to any request for payment exceeding €75,000 per financial year in the case of an operating grant. A financial guarantee is required where pre-financing represents over 80% of the total amount of the grant or, where the beneficiary is a non-governmental organisation, when it exceeds €1,000,000 or 90% of the total amount of the grant.

- In awarding any procurement contracts required for the purposes of the action, the beneficiary must comply with the rules set out in section 7.8.

- Unless otherwise requested or agreed by the European Commission, beneficiaries must take the necessary measures to ensure the visibility of the EU financing or contribution to the financing.

- Sign all the copies of each contract and, if no global endorsement has been given in accordance with point 7.4.8.5, send the contract dossier to the European Commission for endorsement.

- Using the standard letter (see format in Annex A8), send the three signed copies of each contract to the beneficiary, who must countersign them within 30 days of receipt and return two copies to the Contracting Authority together with a payment request and any financial guarantee required in the contract.

- On receipt of the two signed copies from the grant beneficiary, the Contracting Authority sends one to the relevant service in charge of payments and the other to the European Commission. A copy of the signed contract must be sent to the Project Manager.

(	The Contracting Authority and the grant beneficiary must note on the contract the date on which they sign it. The contract takes effect on the date of the later signature. A contract cannot cover earlier activities except in duly substantiated exceptional cases (see section 7.2.5).

(	All actions funded by the European Communities are subject to audit at any stage, whether during the award process, during implementation of the action or once it has been completed.

Contracting Authorities must retain all selection and grant documentation for a period of seven years after the completion of an action. These documents must be made available for inspection by the European Commission, OLAF and the Court of Auditors.

#### 7.4.10.3	Publicising the award of grants

Once the contracts have been signed, the Contracting Authority prepares a notice of award for each call for proposals (using the template in Annex E14) giving the following minimum details in each case: the name and address of the beneficiary, the subject of the grant, the amount allocated and the proportion of the costs of the action it is funding. It sends this immediately to the European Commission, which publishes the results of the call for proposals on the Internet. In addition, the Contracting Authority must record all statistical information concerning the contract award procedure (including the grant amounts, the names of the applicants, and details of the beneficiaries).

At the end of each year, the Contracting Authority also prepares and submits to the European Commission for publication a summary table based on the format in annex (Annex E14, including the table of "grants made without a call for proposals"), containing the above particulars for every grant made during the year.

(	The Contracting Authority is responsible for preparing the grant contract award notice using the template in Annex E14 and for submitting it in electronic form to the OJEU for publication.

The Contracting Authority also publishes this information on its own Internet site and/or any other appropriate media.

The European Commission may authorise the Contracting Authority to waive the above obligations if publication of the information may threaten the safety of the beneficiaries or harm their business interests.

## 7.5	Local Call for Proposals

(	The measures applicable to an international Call for Proposals, as described in section 0, apply by analogy to a local Call for Proposals, except as specified below.

In a local Call for Proposals, the Call for Proposals notice and Guidelines for Applicants are published only in the beneficiary country.

A local call for proposals has to be open.

The minimum period between the date of publication of the Call for Proposals and the deadline for receipt of proposals is 60 days. However, in exceptional cases, and with the prior authorisation of the European Commission, a shorter deadline may be allowed.

## 7.6	Restricted Call for Proposals

(	The measures applicable to an open international Call for Proposals, as described in section 7.4, apply by analogy to a restricted Call for Proposals, except as specified below.

In a restricted call for proposals, the notice and the Guidelines for Applicants invite applicants to submit a preliminary proposal using the format in Annex E3F.  Administrative compliance, eligibility and headings 1 and 2 of the technical and financial evaluation grid are assessed on this basis.

Where the call for proposals is organised by a headquarters service of the European Commission, a copy of each eligible preliminary proposal must be sent to the European Commission delegation in the country where the proposed action is to take place (see format of letter in Annex E15) to enable it inter alia to give its opinion on the relevance of the action.

The second part of the Evaluation Report (see Annex E11), covering the technical and financial quality of the preliminary proposals (headings 1 and 2 of the technical and financial evaluation grid), is drawn up following the final meeting of the Evaluation Committee dealing with this stage of the procedure. It comprises the evaluation grids, the minutes of the evaluation sessions and, where applicable, the opinions of the European Commission delegations, and must be signed by all members of the Evaluation Committee. It must state:

- the date, time and place of the session;

- the persons present;

- the applicants selected for submission of a full proposal;

- the unsuccessful applicants and reasons for non-selection.

The Guidelines for Applicants may indicate that a specific number of applicants will be invited to submit a full proposal. In this case a list restricted to the published number is drawn up consisting of the preliminary proposals with the best scores, ranked in order.

The shortlisted applicants are then invited in writing (see format of letter in Annex E16) to submit a full application form on the basis of which the evaluation of the items mentioned under headings 3 to 5 of the technical and financial evaluation grid will be carried out. Unsuccessful candidates are notified by letter (see Annex E17 for format) giving the grounds for the decision to refuse their application.

The minimum period between the date of publication of the Call for Proposals and the deadline for receipt of preliminary proposals is 45 days. However, in exceptional cases, and with the prior authorisation of the European Commission, a shorter deadline may be allowed.

The minimum period between the dispatch of the letter of invitation to submit full forms and the deadline for receipt of proposals is 45 days. However, in exceptional cases, and with the prior authorisation of the European Commission, a shorter deadline may be allowed.

## 7.7	Modifying grant contracts

Grant contracts may need to be modified during their lifetime if the circumstances in which the action is implemented have changed since the initial contract was signed. Grant contract modifications require a formal addendum to the contract, unless they are explicitly allowed under the contract. Such an addendum must be signed by the contracting parties.

Minor changes, changes of address, changes of bank account and changes of auditor may simply be notified in writing by the grant beneficiary to the Contracting Authority, although this does not affect the right of the Contracting Authority to oppose the grant beneficiary's choice of bank account or auditor.

### 7.7.1	General principles

The following general principles must always apply:

- A grant beneficiary's requests for grant contract modifications should not automatically be accepted by the Contracting Authority. Such requests must be properly substantiated. The Contracting Authority must examine the reasons given, and reject requests which have little or no substantiation.

- The modifications must not have the purpose or the effect of making such changes to the contract as would call into question the grant award decision or be contrary to the equal treatment of applicants.

- Grant contracts can only be modified within the lifetime of the contract; modifications cannot be made retroactively.

- Any modification extending the performance period of the contract must be such that implementation and final payments can be completed before the expiry of the financing decision, and as the case may be of the execution period of the financing agreement, under which the initial grant contract was financed.

(	Requests for contract modifications to grant contracts must be made (by one contracting party to the other) allowing at least 30 days for the addendum to be signed before the modifications are intended to enter into force.

### 7.7.2	Preparing an addendum

In preparing an addendum, the Contracting Authority must proceed as follows:

1)	Use the standard template for an addendum (see Annex A7)

(	All references in the proposed addendum to article numbers and/or annexes to be modified must correspond to those in the initial contract.

Any addendum modifying the budget must include a replacement budget showing how the full budget breakdown of the initial contract has been modified by this addendum (and any previous addenda). The following column headings should be used:

|  | Budget Item | Initial contract budget | Addendum 1 | (Addendum 2 … ) | Revised budget |
| --- | --- | --- | --- | --- | --- |

If the budget is modified by the proposed addendum, the payment schedule may also need to be modified accordingly, taking into account any payments already made in the course of the grant contract.

The payment schedule must not be modified unless either the budget is being modified or the contract is being extended.

2)	Prepare a dossier comprising the following items:

- Explanatory note (see template in Annex A6) setting out the technical and financial grounds for making the modifications in the proposed addendum

- Copy of the grant beneficiary's request for (or agreement to) the proposed modifications, if available

- Copy of the financing agreement authorising the action where necessary

- Copy of the initial contract and any subsequent addenda

- Three copies of the proposed addendum, which is based on the standard addendum template (see Annex A7) and includes any revised annexes.

3)	Sign all copies of the addendum and send the addendum dossier to the European Commission for approval and endorsement.

4)	Using the standard letter (see format in Annex A8), send the three signed copies of the addendum to the grant beneficiary, who must countersign them within 30 days of receipt and return two copies to the Contracting Authority together with any financial guarantee required in the addendum.

5)	On receipt of the two signed copies from the grant beneficiary, the Contracting Authority sends one to the relevant service in charge of payments and the other to the European Commission. A copy of the signed addendum must be sent to the manager responsible for the action.

(	The Contracting Authority and the grant beneficiary must note on the addendum the date on which they sign it. The addendum takes effect on the date of the later signature. An addendum cannot cover earlier activities or enter into force before this date.

## 7.8	Procurement by grant beneficiaries

Grant beneficiaries that are contracting authorities in the sense of the Public Procurement Directives must follow their national legislation implementing the EU acquis. Other beneficiaries should follow the rules included in that section.

### 7.8.1	General principles

When the beneficiary of a grant from the Community under pre accession instruments is a contracting authority within the meaning of public procurement purposes (see the Glossary of terms in Annex A01) and has to award a contract to implement the financed action, this contract shall be awarded in accordance with the directives on public procurement and the relevant national legislation.

When the contracting entity is not a contracting authority within the meaning of these directives, the contract shall be awarded to the most economically advantageous tender (i.e., the tender offering the best price-quality ratio), in compliance with the principles of transparency and fair competition for potential contractors. In any case, the contracting authority or entity shall take care to avoid any conflicts of interest.

To this end, grant contracts provide for compliance with the rules set out in sections 7.8.2 to 7.8.7 below, subject to section 7.8.8. Where the grant beneficiary makes use of the services of a central buying office, the buying office must follow the same rules which are to be followed by the beneficiary. In the event of failure to comply with the rules referred to above, expenditure relating to the operations in question is not eligible for Community financing. The Commission will carry out ex-post checks on the compliance of grant beneficiaries with these rules. Grant contracts must provide expressly for the Commission, including the European Anti-Fraud Office (OLAF), and the Court of Auditors to exercise their powers of control, on documents and on the spot, over all contractors and subcontractors which have received Community funds.

These rules are compulsory for individual contracts of more than € 300,000. Below this threshold, the Contracting  Authority may decide to apply national procurement rules with the agreement of the European Commission.

### 7.8.2	Eligibility for contracts

#### 7.8.2.1	The nationality rule

Participation in tender procedures administered by grant beneficiaries is open on equal terms to all natural and legal persons of the Member States and the States and territories of regions expressly covered and/or allowed by the Financial Regulation, the basic legislation or other instruments governing the aid programme under which the grant is being financed.

This rule also applies to the experts proposed by service providers taking part in tender procedures or service contracts financed by the grant. Tenderers must state, in the tender, the country of which they are nationals by presenting the usual proof of nationality under their national legislation.

#### 7.8.2.2	The rule of origin

If the basic act or the other instruments applicable to the programme under which the grant is financed contain rules of origin for supplies acquired by the grant beneficiary in the context of the grant, the tenderer must state the origin of supplies. Contractors must present a certificate of origin to the grant beneficiary no later than when the first invoice is presented. The certificate of origin must be made out by the competent authorities of the country of origin of the supplies or supplier and must comply with the international agreements to which that country is a signatory or to the relevant Community legislation if it is an EU Member State.

#### 7.8.2.3	Exceptions to the rules on nationality and origin

Where an agreement on widening the market for procurement of goods or services applies, the procurement contracts must also be open to nationals of other countries under the conditions laid down in that agreement.

In addition, in duly substantiated exceptional cases, the Commission may allow nationals of countries other than those referred to tender for contracts (or supplies of goods originating in such countries) on the basis of the specific conditions laid down in the basic act or other instrument governing the programme under which the grant is financed.

#### 7.8.2.4	Grounds for exclusion from participation in contracts

Candidates or tenderers will be excluded from participation in a procurement procedure if:

- they are bankrupt or being wound up, are having their affairs administered by the courts, have entered into an arrangement with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations;

- they have been convicted of an offence concerning their professional conduct by a judgment which has the force of res judicata;

- they have been guilty of grave professional misconduct proven by any means which the beneficiary of the grant can justify;

- they have not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those of the country of the grant beneficiary or those of the country where the contract is to be performed;

- they have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the Communities' financial interests;

- following another procurement procedure or grant award procedure financed by the Community budget, they have been declared to be in serious breach of contract for failure to comply with their contractual obligations.

Candidates or tenderers must certify that they are not in one of the situations listed above.

#### 7.8.2.5	Exclusion from award of contracts

Contracts may not be awarded to candidates or tenderers which, during the procurement procedure:

(a)	are subject to a conflict of interests;

(b)	are guilty of misrepresentation in supplying the information required by the beneficiary of the grant as a condition of participation in the contract procedure or fail to supply this information.

### 7.8.3	Rules common to all tender procedures

The tender documents must be drafted in accordance with best international practice. If they do not have their own documents, grant beneficiaries may use the models (in particular the tender dossier) published on the Commission’s web site relating to external actions. The time-limits for receipt of tenders and requests to participate must be long enough to allow interested parties a reasonable and appropriate period to prepare and submit their tenders.

All requests to participate and tenders declared as satisfying the requirements must be evaluated and ranked by an evaluation committee on the basis of the exclusion, selection and award criteria announced in advance.

### Rules applicable to service contracts

#### Contracts of €200,000 or more

Service contracts worth EUR 200,000 or more must be awarded by means of an international restricted tender procedure following publication of a procurement notice.

The procurement notice is to be published in all appropriate media, in particular on the grant beneficiary’s web site, in the international press and the national press of the country in which the action is being carried out, or in other specialist periodicals. It must state the number of candidates which will be invited to submit tenders. This will be within a range of four to eight candidates, and must be sufficient to ensure genuine competition.

All would-be service providers fulfilling the conditions referred to in section 7.8.2. may ask to participate but only candidates satisfying the published selection criteria and invited in writing by the grant beneficiary may submit a tender.

#### Contracts under €200,000

Service contracts worth less than EUR 200,000 must be awarded by means of a negotiated procedure without publication, in which grant beneficiaries consult at least three service providers of their choice and negotiate the terms of the contract with one or more of them.

For services of a value of EUR 5,000 or less, the beneficiary may place orders on the basis of a single tender.

### Rules applicable to supply contracts

#### Contracts of €150,000 or more

Supply contracts worth EUR 150,000 or more must be awarded by means of an international open tender procedure following publication of a procurement notice.

The procurement notice is to be published in all appropriate media, in particular on the grant beneficiary’s web site, in the international press and the national press of the country in which the action is being carried out, or in other specialist periodicals.

Any would-be supplier which fulfils the conditions referred to in section 7.8.2. may submit a tender.

#### Contracts between €30,000 and €150,000

Such contracts are awarded by means of an open tender procedure published locally: the procurement notice is published in all appropriate media but only in the country in which the action is being carried out.

A local open tender procedure must provide other eligible suppliers with the same opportunities as local firms.

#### Contracts under €30,000

Supply contracts worth less than EUR 30,000 must be awarded by means of a negotiated procedure without publication, in which grant beneficiaries consult at least three suppliers of their choice and negotiate the terms of the contract with one or more of them.

For supplies of a value of EUR 5,000 or less, the beneficiary may place orders on the basis of a single tender.

### Rules applicable to works contracts

#### Contracts of €5,000,000 or more

Works contracts worth EUR 5,000,000 or more must be awarded by means of an international open tender procedure following publication of a procurement notice.

The procurement notice is to be published in all appropriate media, in particular on the grant beneficiary’s web site, in the international press and the national press of the country in which the action is being carried out, or in other specialist periodicals.

Any contractor which fulfils the conditions referred to in section 7.8.2. may submit a tender.

#### Contracts of between €300,000 and €5,000,000

Such contracts are awarded by means of an open tender procedure published locally: the procurement notice is published in all appropriate media but only in the country in which the action is being carried out.

A local open tender procedure must provide other eligible contractors with the same opportunities as local firms.

#### Contracts under €300,000

Works contracts worth less than EUR 300,000 must be awarded by means of a negotiated procedure without publication, in which grant beneficiaries consult at least three contractors of their choice and negotiate the terms of the contract with one or more of them.

For works of a value of EUR 5,000 or less, the beneficiary may place orders on the basis of a single tender.

### 7.8.7	Use of the negotiated procedure

The beneficiary of the grant may use the negotiated procedure on the basis of a single tender in the following cases:

(a)	where, for reasons of extreme urgency brought about by events which the grant beneficiary could not have foreseen and which can in no way be attributed to him, the time-limit for the procedures referred to in sections 0 to 0 cannot be kept. The circumstances invoked to justify extreme urgency must in no way be attributable to the grant beneficiary.

Actions carried out in crisis situations identified by the Commission are considered to satisfy the test of extreme urgency. The Commission will inform the grant beneficiary if a crisis situation exists and when it comes to an end.

(b)	where the services are entrusted to public-sector bodies or to non-profit institutions or associations and relate to activities of an institutional nature or designed to provide assistance to peoples in the social field;

(c)	where contracts extend activities already under way which are not included in the main contract but which, because of unforeseen circumstances, have become necessary to perform the contract, or which consist of the repetition of similar services entrusted to the contractor providing services under the initial contract;

(d)	for additional deliveries by the original supplier intended either as a partial replacement of normal supplies or installations or as the extension of existing supplies or installations, where a change of supplier would oblige the grant beneficiary to acquire equipment having different technical characteristics which would result in either incompatibility or disproportionate technical difficulties in operation and maintenance;

(e)	for additional works not included in the initial contract concluded which have, through unforeseen circumstances, become necessary for carrying out the works;

(f)	where the tender procedure has been unsuccessful, that is where no qualitatively and/or financially worthwhile tender has been received. In such cases, after cancelling the tender procedure, the grant beneficiary may negotiate with one or more tenderers of its choice, from among those that took part in the tender procedure, provided that the initial terms of the tender procedure are not substantially altered;

(g)	where the contract concerned follows a contest and must, under the rules applying, be awarded to the winner of the contest or to one of the winners of the contest, in which case, all winners shall be invited to participate in the negotiations;

(h)	where, for technical reasons, or for reasons connected with the protection of exclusive rights, the contract can be awarded only to a particular service provider;

(i)	where warranted by the nature or particular characteristics of the supplies, for example, where performance of the contract is exclusively reserved for the holders of patents or licences to use patents.

### 7.8.8	Special cases

#### Co-financing

Where:

- the action is cofinanced by several donors and

- one of the other donors, whose contribution to the total cost of the action is greater than that of the Commission, imposes procurement rules on the grant beneficiary that differ from those set out in the relevant sections of this guide,

the grant beneficiary may apply the rules imposed by the other donor. In all cases, the general principles and rules on nationality and origin set out in sections 4, 5 and 6 still apply.

#### International organisations

Where the beneficiary of a grant is an international organisation, it applies its own procurement procedures if they provide guarantees equivalent to internationally accepted standards. If not or in specific cases, the Commission and the international organisation agree to apply other rules which provide such guarantees. The international organisations covered by this section are: international public-sector organisations set up by intergovernmental agreements, and specialised agencies set up by such organisations; the International Committee of the Red Cross (ICRC); the International Federation of National Red Cross and Red Crescent Societies. In the event of joint management, the rules on nationality and origin of the international organisation apply, if the basic act or other instruments governing the programme under which the grant is financed permit this.  In all other cases, the rules on nationality and origin set out in section 5.8.2 apply. In all cases, the general principles set out in section 5.8.1 remain applicable.

Section 8.	 Relations with international organisations and other donors

External aid projects may need to be co-financed with a partner who may be an international organisation, an EU Member State or a non-EU country. The procurement rules and procedures applicable vary from case to case.

There are two types of co-financing : parallel and joint co-financing. Under parallel co-financing, the project is broken down into clearly identifiable sub-projects which are each funded by the different co-financing partners. The rules and procedures included in this Guide are applicable in their entirety and without modification to the EC-funded part of all projects with parallel co-financing.

Under joint co-financing, the total project cost is divided between the co-financing partners and all the funds are pooled such that the source of funding for a specific activity within the project cannot be identified.

Specific cases of joint co-financing are examined in the following sections.

## RELATIONS WITH INTERNATIONAL ORGANISATIONS

International organisation means:

- international public-sector organisations set up by intergovernmental agreements, and specialised agencies set up by such organisations - these organisations may have worldwide or regional scope;

- the International Committee of the Red Cross (ICRC);

- the International Federation of National Red Cross and Red Crescent Societies.

Within the meaning of the Financial Regulation, there is joint management when co-financing with an international organisation involves an action for which the resources of a number of donors have to be pooled and it is not reasonably possible or appropriate to assign the share contributed by each donor to each type of expenditure. International organisations involved in joint management must apply standards in their accounting, audit, control and procurement procedures which offer guarantees equivalent to internationally accepted standards. Provided the Commission is sure of compliance with these conditions, international organisations need not be obliged to follow procedures other than their own (see also section 0 of this Guide for the relevant procurement procedures). The Commission must also ensure that suitable arrangements exist for the control and audit of the action in its entirety.

For the purposes of this Guide, joint management implies a grant and is subject accordingly to the rules set out in Part 7. above unless otherwise provided for in the Guide and in particular in the model contribution agreement to an international organisation (see Annex F1). Grants to international organisations other than in the case of joint management are wholly subject to the rules in Part 7 of this Guide.

Framework agreements on financial and contractual procedures have been concluded between the Commission and some international organisations, notably the World Bank (Trust Fund and Co-financing Framework Agreement of 8 November 2001, see Annex F2) and the United Nations (Financial and Administrative Framework Agreement of 29 April 2003, see Annex F3). These framework agreements take the above rules into account and must be applied. The standard contribution agreement to an international organisation implements notably the framework agreement of 29 April 2003 with the United Nations. It must be used with all international organisations, both for grants and cases of joint management, unless otherwise agreed with the international organisation concerned (for instance specific standard contracts apply for contributions to the World Bank).

Wherever possible, contracts to be concluded with international organisations should be signed following the centralised management pattern.

## RELATIONS WITH EU MEMBER STATES

### Co-financing

Joint co-financing is possible with EU Member States, candidate countries and the member states of the European Economic Area, or with national public-sector bodies or private-law entities with a public-service mission of these countries. The applicable procurement rules and procedures must be compatible with those of the Commission as set out in this Guide.

### delegation budget implementation tasks

Special procedures apply where the Commission delegates tasks of public authority, and in particular budget implementation tasks, to the abovementioned national bodies. Specific procedures apply in this case.

#### basic requirements

In order for a delegation of budget implementation tasks to be possible, all the following conditions must be fulfilled:

- The bodies concerned must offer adequate financial guarantees. Such guarantees must be underwritten by a public authority and allow full recovery of amounts owed to the Commission.

- Delegation is only possible where provided for in the legal basis.

- The delegation must meet the requirements of sound financial management, in particular the principles of economy, efficiency and effectiveness. These requirements must be identified in advance by a prior analysis on which the competent committee provided for in the legal basis must give an opinion. The committee may express an opinion on the proposed application of the selection criteria.

- The bodies concerned must be chosen in an objective and transparent manner, following a cost-effectiveness analysis, to match the performance requirements identified by the Commission.

- The delegation must comply with the principle of non-discrimination and the choice of the body to which the executive tasks will be delegated may not entail any discrimination between the various Member States or countries concerned.

- The delegation must comply with the rules on the visibility of Community action.

- Performance of the delegated implementation tasks must not give rise to conflicts of interests.

- Bodies performing implementation tasks must conduct regular checks to ensure that actions financed from the EC budget have been implemented correctly.

- The bodies concerned must take appropriate measures to prevent irregularities and fraud.

- These bodies must be governed by the law of one of the Member States, EEA States, the candidate countries or other States specified in the legal basis.

#### Delegation decision

Before any delegation is issued, a specific Commission decision is required. The delegation decision must meet the following requirements:

- No body may be designated without the agreement of the State concerned.

- Decisions to delegate implementation tasks must include appropriate provisions to ensure the transparency of the actions carried out.

These decisions must include:

- transparent procurement and grant-award procedures which are non-discriminatory and exclude any conflict of interests and which are in accordance with the provisions of Titles V and VI of the Financial Regulation;

- an effective internal control system for management operations;

- accounting arrangements for these operations and procedures for the presentation of the accounts which will enable the correct use of Community funds to be ascertained and the true extent of this use to be reflected in the Community accounts;

- an independent external audit;

- public access to information at the level provided for in Community regulations.

Note, however, that the Commission may recognise audit, accounting and procurement systems as equivalent to its own, taking due account of internationally accepted standards.

The delegation decision must specify that the Commission is responsible for the supervision, evaluation and scrutiny of the delegated tasks.

#### Delegation Agreement

The delegation decision must be accompanied by an agreement with the body concerned containing:

- a definition of the delegated tasks;

- the conditions and detailed arrangements for performing the delegated tasks, including appropriate provisions for demarcating responsibilities and organising the controls to be carried out;

- rules for reporting to the Commission on how the delegated tasks are performed;

- the conditions under which performance of the delegated tasks terminates;

- the detailed arrangements for Commission scrutiny;

- conditions governing the use of separate bank accounts, the beneficiary of the interest yielded and the use made of it;

- provisions guaranteeing  the visibility of the Community action in relation to the other activities of the body concerned;

- an undertaking by the body concerned to refrain from any act giving rise to a conflict of interests.

Procurement contracts awarded by national bodies granted such a delegation must comply with the eligibility rules contained in this Guide.

## RELATIONS WITH THIRD COUNTRIES

Third countries means countries other than:

- EU Member States

- members of the European Economic Area

- candidate countries for accession to the EU

- beneficiary countries.

National public law bodies of the above are likewise treated as third countries.  Actions may be co-financed with third countries provided that the procurement rules and procedures applicable comply with those of the Commission as set out in this Guide.

Where the legal basis so provides, and in accordance with the conditions it lays down, eligibility for participation in contracts co-financed with a third country may be extended to natural and legal persons with the nationality of that country.

# Footnotes

“Practical Guide to contract procedures financed from the General Budget of the European Communities in the context of external actions” published by the European Commission with effect from May 2003.

The Services, Supplies and Works Directives (92/50, 93/36, 93/37/EC), all as amended by Directives 97/52/EC and 2001/78/EC.

The Utilities Directive (93/38/EC) as amended by Directives 98/4/EC and 2001/78/EC.

The Services, Supplies and Works Directives (92/50, 93/36, 93/37/EC), all as amended by Directives 97/52/EC and 2001/78/EC.

The Utilities Directive (93/38/EC) as amended by Directives 98/4/EC and 2001/78/EC.

OJEU C 309, 19/12/2003.

Commission Directive 2001/78/EC.

OJ C 316, 27.11.1995, p.48.

OJ C 195, 25.6.1997, p.1.

OJ L 351, 29.12.1998, p. 1. Joint Action of 21 December 1998 making it a criminal offence to participate in a criminal organisation in the Member States of the European Union.

OJ L 166, 28.6.1991, p. 77. Directive of 10 June 1991, as amended by Directive 2001/97/EC of the European Parliament and of the Council of 4 December 2001 (OJ L 344, 28.12.2001, p.76).

See Section 1.4.2 (Approximately €154 000 for central government Part A, €236 000 for others and Part B).

The national equivalent of the Euro equivalent of 5 000 000 SDR.

The Guide does not cover humanitarian aid within the meaning of Regulation 1257/96 of 20 June 1996 (Official Journal No L 163, 2.7.1996, p. 1), for which there are special arrangements managed by the Community's humanitarian office ECHO.

This does not apply to crisis management aid within the meaning of article 168.2 of the Implementing Rules of the Financial Regulation.

In the case of crisis situations within the meaning of article 168, paragraph 2 of the Implementing Rules of the Financial Regulation, expenditure incurred by a beneficiary before the date of submission of the application shall be eligible for Community financing solely in the following cases : where the expenditure relates to the constitution of stocks by the applicant for use in connection with the action for which the grant is awarded ; by way of exception and for properly substantiated reasons, where the financing decision and the grant contract explicitly provide for this by setting an eligibility date earlier than the date for submission of the application.

# Comments

Isn’t the point that minor errors which do not prejudice the tenderer can be amended and notified  but that substantial arithmetical corrections need to be accepted by the tenderer before they can be taken into account.