monthly report

march 2006

# Contract 5821902-03-01/0002

# Integration of Roma Children into Regular Primary Schools

Date of issue of the Draft Monthly Report: April 3, 2006

Date of issue of the Final version of the Monthly Report: May 31, 2006

Final version of the Monthly Report approved by: Novotná Kinga

Date of approval of the Final version of the Monthly Report:

CONTENT

list of acronyms	3

1	introduction	5

2	Project outputs and deliverables	6

3	Progress in the project implementation	7

4	Factors influencing the implementation	10

4.1	Deviations from the initial work plan	10

4.2	Internal and external factors influencing the project implementation	10

4.3	Recommendations and proposals	10

5	Activities planned for the next reporting period	12

6	Annexes	15

6.1	Annex 1 – Expert’s input in the reporting period	15

6.2	Príloha 2 - Monitoring of cooperation between SPS, PS and PPAC	16

6.3	Annex 3 - Monitoring of particpation of parents in the educational process	19

6.4	Annex 4 - Monitoring of school attendance in the transitive classes	21

6.5	Annex 5 – Proposal of tests for the transitive classes	23

list of acronyms

AU			Teacher assistant (Asistent učiteľa)

CC			Community Centre

ECO			European Consultants Organization

EU			European Union

PPAC		Pedagogic-Psychology Advisory Centre

PS		Primary school

RICPP		Research Institute of Child Psychology and Patopsychology

ROCEPO		Roma education, information, documentation, advisory and consultancy centre

RR Screening		Test battery developed under Phare 2001 project

RTA		Roma Teacher Assistant (Teacher Assistant)

SPS		Special Primary School

SR		Slovak Republic

Ø		Average

introduction

In March, the time schedule and the content of the project strategy were followed. The project team continued in close cooperation with the special primary schools and standard primary schools and participated in addressing current issues related to the functioning of transitive classes. The communication took a place not only with directors of the schools and pedagogic staff, but also with psychologists cooperating with the schools, representatives of communities and parents of pupils. In the month of March, a special attention was paid to complex support to integration of pupils from the transitive classes into standard primary school classes (in Hanušovce nad Topľou and Piešťany).

The performed interventions in March 2006 related mainly to:

Communication with directors, teachers and teacher assistants regarding the functioning of the transitive classes,

Collection and assessment of materials for monitoring of the school attendance of pupils, visits of parents and psychologists in the schools,

Communication with the psychologists,

Strengthening of cooperation between school, family and community,

Monitoring of the educational process in the transitive classes, use of time-thematic plans and individual educational plans of pupils,

Preparation and active participation in the presentational seminar (Prešov),

Mentoring and provision of consultations in implementation of plans for effective cooperation with parents and community,

Mentoring and provision of consultations in the implementation of plans for cooperation between special and standard primary schools,

Mentoring and provision of consultations in the implementation of educational and out of school activities,

Provision of consultations to pedagogic staff of the standard primary schools regarding integration process,

Tutoring in the integration of rediagnosed children into the standard primary schools,

Communication with relevant partners and project beneficiaries,

Preparation of regular monthly report for March 2006 and the project Final report.

Project outputs and deliverables

|  | Outputs and deliverables | 2005 | 2006 | Outputs related to the activity no. |
| --- | --- | --- | --- | --- |
|  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |  |
| As annex | List of outputs completed within the reporting period |  |  |  |  |  |  |  |  |  |  |
| 1 | Overview of the experts’ input in the reporting period |  |  |  |  |  |  |  |  |  |  |
| 2 | Monitoring of cooperation between SPS, PS and PPAC |  |  |  |  |  |  |  |  |  | 6.2 |
| 3 | Monitoring of participation of parents in the educational process |  |  |  |  |  |  |  |  |  | 6.2 |
| 4 | Proposal for updated test for transitive classes from math and Slovak language |  |  |  |  |  |  |  |  |  | 6.3 |
| 5 | Monitoring school attendance in transitive classes |  |  |  |  |  |  |  |  |  | 6.2 |
|  | List of outputs to be completed |  |  |  |  |  |  |  |  |  |  |
|  | Draft final report |  |  |  |  |  |  |  |  |  | 3.9, 3.13 |

Progress in the project implementation

|  | Interventions | 2005 | 2006 |
| --- | --- | --- | --- |
|  |  | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |
| 1 | Inception/Analytical Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Contacting all relevant partners and establishment of communication channels |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Complex analysis of the special primary schools/classes environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | Complex analysis of the standard primary schools/classes environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 | Detailed training needs analysis of the target groups (teachers, RTA and psychologists) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5 | Assessment of the transitive classes preparedness |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6 | Analysis of the cooperation between schools and parents/communities/other partners |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 | Evaluation of all information and data collected during analytical phase |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.8 | Inventory of the existing models/approaches for education of soc. disadvantaged children |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.9 | Detailed work plan based on the results of the analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Preparatory phase – special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Assistance to the establishment of the transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Development of the modified curricula for the purposes of the transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Preparation and development of the appropriate teaching methods for transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Elaboration of the plans for effective cooperation with parents and communities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 | Preparation of the training programme for special primary schools teachers and RTAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6 | Preparation and monitoring of individual education plans of students |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.7 | Preparation of the training programme for psychologists working with special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | Preparatory phase – standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Preparation of plan for cooperation between special and standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Development of the methodology for re- integration of children into standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Preparation and development of the appropriate teaching methods for re-integrated children |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Elaboration of the individual educational plans for each re-integrated child |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.5 | Plans for cooperation between standard primary schools with parents and community |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.6 | Preparation of the training programme for standard primary schools teachers and RTAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.7 | Preparation of the training programme for psychologists working with standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Preparatory phase – Practical guidance book |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Collection of the relevant information and practices |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Drafting the practical guidance book |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Publishing and distribution of the practical guidance book to relevant partners |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Working in the school environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Support provided to the special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Assistance to the establishment and functioning of the transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 | Mentoring and guidance provided to the pedagogical staff of transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 | Consultations for the pedagogic staff and psychologists of special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5 | Facilitation of cooperation between both types of schools and parents/communities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.6 | Implementation of out of school activities in both types of schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.7 | Strengthening the cooperation between special and standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.8 | Assistance provided to pedagogic staff of standard primary schools in integration of children |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.9 | Ensuring the integration/re-integration of re-diagnosed children in methodological way |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.10 | Tutoring of the re-diagnosed children integrated in the standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.11 | Consultations provided for pedagogic staff of the standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.12 | Monitoring of the implementation of model of transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.13 | On-going evaluation of the interventions and quality control |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Delivery of the training |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Delivery of the training programme for teachers and RTAs of special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 | Delivery of the training programme for teachers and RTAs of standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 | Delivery of the training programme for the psychologists (PPACs) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Final phase |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Presentation of the outcomes/outputs to professional public |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 | Distribution of the project outcomes to relevant partners |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 | Formulation of the proposals and recommendations for future actions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Communications with the relevant partners/beneficiaries |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 | Monitoring and on-going evaluation (quality assurance) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3 | Regular reporting on the progress of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.4 | Participation at project steering meeting and other meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.5 | Project visibility |  |  |  |  |  |  |  |  |  |  |  |  |  |

Factors influencing the implementation

Deviations from the initial work plan

In March, there has been a deviation from the initial plan in the experts’ input (Mrs. Končoková and Mrs. Majzlánová) and delay in the approval of the output materials.

Internal and external factors influencing the project implementation

Two pupils from the transitive classes were integrated into the classes of standard primary schools since the beginning of the 2nd half of the school year 2005/2006:

In Hanušovce n./Topľou – Rómeo Bihári – integrated from the 2nd grade of the transitive class into the 2nd grade of the standard primary school,

In Piešťany –Anna Puľová - integrated from the 2nd grade of the transitive class into the 2nd grade of the standard primary school.

Recommendations and proposals

Adopt relevant legislation on the establishment and functioning of transitive classes.

Until the new legislation on establishment of transitive classes is published, the Ministry of Education SR should ensure usability of all project outputs in the process of integration of Roma pupils on participating school in the most appropriate way.

Recommendation for the implementation of Teaching and learning methods in transitive classes into pedagogical practice of the school and use of the Transitive class – practical guidance book for work with the pupils from socially disadvantaged environment.

Elaborate and distribute clauses to certificates in the transitive classes as well as statutes.

Appoint a competent person to provide a methodological guidance (management) of the transitive classes in order to ensure continual integration of pupils from the special primary schools into standard primary schools after the completion of the project (the person should be appointed by the Ministry of Education SR) ,

Propose implementation of the specificities of the transitive classes into study programmes of the relevant pedagogic universities (faculties),

We propose to develop a competency profile of a pupil in the reading literacy within the preparation of the national curricula. Ensure transformation of requirements related to reading skills into specific objectives of individual courses and their consequent implementation into the educational standards.

Ensure support to further cooperation of the special primary schools with standard primary schools in area of integration of Roma pupils. Create “model schools of integration” (in which the transitive classes are well functioning) for dissemination of good practice, create web publication.

Develop an intensive system to support school attendance of pupils from socially disadvantaged environment. Introduce school buses if necessary (experience from EU member states, analysis of expenditure). The precondition is strengthening of cooperation with parents.

Activities planned for the next reporting period

|  | Interventions | 2005 | 2006 |
| --- | --- | --- | --- |
|  |  | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr |
| 1 | Inception/Analytical Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 | Contacting all relevant partners and establishment of communication channels |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 | Complex analysis of the special primary schools/classes environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 | Complex analysis of the standard primary schools/classes environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 | Detailed training needs analysis of the target groups (teachers, RTA and psychologists) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5 | Assessment of the transitive classes preparedness |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.6 | Analysis of the cooperation between schools and parents/communities/other partners |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.7 | Evaluation of all information and data collected during analytical phase |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.8 | Inventory of the existing models/approaches for education of soc. disadvantaged children |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.9 | Detailed work plan based on the results of the analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Preparatory phase – special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Assistance to the establishment of the transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Development of the modified curricula for the purposes of the transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Preparation and development of the appropriate teaching methods for transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Elaboration of the plans for effective cooperation with parents and communities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 | Preparation of the training programme for special primary schools teachers and RTAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.6 | Preparation and monitoring of individual education plans of students |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.7 | Preparation of the training programme for psychologists working with special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 | Preparatory phase – standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1 | Preparation of plan for cooperation between special and standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2 | Development of the methodology for re- integration of children into standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.3 | Preparation and development of the appropriate teaching methods for re-integrated children |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.4 | Elaboration of the individual educational plans for each re-integrated child |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.5 | Plans for cooperation between standard primary schools with parents and community |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.6 | Preparation of the training programme for standard primary schools teachers and RTAs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.7 | Preparation of the training programme for psychologists working with standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 | Preparatory phase – Practical guidance book |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 | Collection of the relevant information and practices |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Drafting the practical guidance book |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2 | Publishing and distribution of the practical guidance book to relevant partners |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Working in the school environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Support provided to the special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Assistance to the establishment and functioning of the transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 | Mentoring and guidance provided to the pedagogical staff of transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 | Consultations for the pedagogic staff and psychologists of special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5 | Facilitation of cooperation between both types of schools and parents/communities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.6 | Implementation of out of school activities in both types of schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.7 | Strengthening the cooperation between special and standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.8 | Assistance provided to pedagogic staff of standard primary schools in integration of children |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.9 | Ensuring the integration/re-integration of re-diagnosed children in methodological way |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.10 | Tutoring of the re-diagnosed children integrated in the standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.11 | Consultations provided for pedagogic staff of the standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.12 | Monitoring of the implementation of model of transitive classes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.13 | On-going evaluation of the interventions and quality control |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Delivery of the training |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Delivery of the training programme for teachers and RTAs of special primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 | Delivery of the training programme for teachers and RTAs of standard primary schools |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 | Delivery of the training programme for the psychologists (PPACs) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Final phase |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 | Presentation of the outcomes/outputs to professional public |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 | Distribution of the project outcomes to relevant partners |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 | Formulation of the proposals and recommendations for future actions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Project management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 | Communications with the relevant partners/beneficiaries |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 | Monitoring and on-going evaluation (quality assurance) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3 | Regular reporting on the progress of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.4 | Participation at project steering meeting and other meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.5 | Project visibility |  |  |  |  |  |  |  |  |  |  |  |  |  |

Annexes

Annex 1 – Expert’s input in the reporting period

| Project title: INTEGRATION OF ROMA CHILDREN INTO REGULAR PRIMARY SCHOOLS | Programme title: FURTHER INTEGRATION OF ROMA CHILDREN IN THE FIELD OF EDUCATION AND IMPROVED LIVING CONDITIONS | Country: SLOVAK REPUBLIC |
| --- | --- | --- |
| Implementation period: 04/2005 – 04/2006 | Prepared on: 05/02/2006 | Contractor: ECO, Belgium |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |  |
| Name of the Expert | 04/05 | 05/05 | 06/05 | 07/05 | 08/05 | 09/05 | 10/05 | 11/05 | 12/05 | 01/06 | 02/06 | 03/06 | 04/06 | Total spent | Total Available |
| Eva Končoková Team Leader | 0 | 12 | 17 | 13 | 13 | 13 | 13 | 13 | 10 | 10 | 12 | 12 |  | 138 | 12 |
| Daniela Čechová Key expert no. 2 | 15 | 20 | 17 | 19 | 21 | 18 | 16 | 15 | 15 | 20 | 17 | 17 |  | 210 | 10 |
| Miroslava Čerešníková Key expert no. 3 | 17 | 15 | 15 | 20 | 21 | 17 | 17 | 17 | 15 | 18 | 18 | 15 |  | 205 | 15 |
| Katarína Majzlánová Key expert no. 4 | 14 | 15 | 18 | 22 | 19 | 17 | 17 | 17 | 16 | 16 | 17 | 20 |  | 208 | 12 |
| Alica Petrasová Key expert no. 5 | 13 | 17 | 17 | 22 | 20 | 19 | 19 | 19 | 16 | 16 | 16 | 17 |  | 211 | 9 |

Príloha 2 - Monitoring of cooperation between SPS, PS and PPAC

V mesiacoch september 2005 – február 2006 sme monitorovali kontakty medzi špeciálnou základnou školou resp. tranzitívnou triedou a štandartnou základnou školou (v tabuľke je uvedený počet kontaktov). Kontakt bol najčastejšie realizovaný prostredníctvom vzájomných návštev pedagóga alebo asistenta učiteľa orientovaný na výmenu „najlepších skúseností“ a budovanie lokálnych integračných stratégií. Rovnako boli realizované výmenné pobyty detí tranzitívnej a partnerskej triedy, ktorých cieľom bolo vzájomné zoznámenie, zoznámenie sa s novým edukačným prostredím a odbúranie jestvujúcich stereotypov viažucich sa na vzdelávanie v konkrétnom type základnej školy. Rovnako sme sledovali participáciu psychológov na edukácii v tranzitívnej triede, prípadne ich oboznámenie sa s prostredím, do ktorého budú žiaci tranzitívnej triedy integrovaní. Nižší počet návštev psychológov v základných škôl počas školského roka je pochopiteľný, nakoľko sa bežne vykonáva pri vyskytnutí sa ťažkostí a vyžiadaní (je však potrebné ho zvýšiť po integrácií žiakov ŠZŠ), celkovo však počet návštev psychológov v tranzitívnych triedach považujeme za nízky.

| Monitoring spolupráce medzi špeciálnou základnou školou / základnou školou a pedagociko-psychologickou poradňou |
| --- |
| september 2005 – február 2006 |
| P.č. | Špeciálna základná škola | Fekvencia kontaktov |
|  |  | Poč. žiakov | Učiteľ, resp. AU navštívil triedu ZŠ | Učiteľ, resp. AU sa zúčastnili na spol. podujatiach | Psychológ navštívil triedu ŠZŠ | Psychológ navštívil triedu ZŠ | Žiaci ŠZŠ navštívili ZŠ | Žiaci ZŠ navštívili ŠZŠ | Iná forma kontaktu | Spolu počet návštev |
|  |  |  | počet návštev | počet návštev | počet návštev | počet návštev | počet návštev | počet návštev |  |  |
| 1. | Markušovce, Michalská 39 | 9 | 5,00 | 0,00 | 0,00 | 0,00 | 0,00 | 1,00 | telefonáty, rozhovor s riaditeľom a špec.pedagógom, učiteľmi 1.stupňa | 6 |
| 2. | Zborov, Školská 478 | 9 | 6,00 | 5,00 | 2,00 | 0,00 | 2,00 | 2,00 | konzultácie s učiteľom ZŠ, divadelné predstavenie, karneval | 15 |
| 3. | Toporec 39 | 5 | 14,00 | 7,00 | 1,00 | 1,00 | 11,00 | 11,00 | spolupráca s vedením ZŠ, starostom obce, návšteva v osade, výmena skúseností medzi učiteľkami ZŠ a ŠZŠ, spoločné stretnutia, osobný kontakt s psychológom | 33 |
| 4. | Chminianske Jakubovany 22 | 10 | 5,00 | 3,00 | 1,00 | 1,00 | 3,00 | 4,00 |  | 13 |
| 5. | Stará Ľubovňa, Levočská 22 | 9 | 2,00 | 2,00 | 8,00 | 1,00 | 1,00 | 0,00 |  | 12 |
| 6. | Prešov, Matice slovenskej 11 | 8 | 1,00 | 2,00 | 15,00 | 0,00 | 1,00 | 1,00 | 2 spoločné stretnutia rodičov a žiakov | 19 |
| 7. | Jarovnice 96 | 8 | 2,00 | 1,00 | 3,00 | 2,00 | 1,00 | 1,00 | športový deň | 7 |
| 8. | Lipany, Tehelná 3 | 9 | 3,00 | 1,00 | 5,00 | 2,00 | 1,00 | 1,00 | návšteva divadelného predstavenia | 10 |
| 9. | Trebišov, M.R.Štefánika 83 | 9 | 1,00 | 1,00 | 2,00 | 2,00 | 0,00 | 0,00 |  | 4 |
| 10. | Trebišov, Poľná 1 | 7 | 0,00 | 2,00 | 3,00 | 0,00 | 0,00 | 0,00 | stretnutie žiakov ŠZŠ - tranzitívnej triedy so žiakmi ZŠ v cukrárni | 5 |
| 11. | Košice, Rovníková 11 | 7 | 1,00 | 2,00 | 0,00 | 0,00 | 1,00 | 1,00 |  | 4 |
| 12. | Košice, Inžinierska 24 | 7 | 5,00 | 3,00 | 0,00 | 0,00 | 3,00 | 1,00 |  | 9 |
| 13. | Košice, Odborárska 2 | 7 | 2,00 | 3,00 | 6,00 | 1,00 | 2,00 | 1,00 |  | 12 |
| 14. | Pavlovce nad Uhom, Hlavná 1 | 7 | 6,00 | 7,00 | 20,00 | 2,00 | 1,00 | 2,00 | osobné a telefon.kontakty - učiteľ - asistent | 35 |
| 15. | Veľké Kapušany, J. Dószu 32 | 7 | 3,00 | 3,00 | 1,00 | 0,00 | 2,00 | 1,00 |  | 8 |
| 16. | Piešťany, Valová 40 | 8 | 4,00 | 0,00 | 1,00 | 0,00 | 1,00 | 0,00 |  | 5 |
| 17. | Lučenec, Zvolenská cesta 59 | 8 | 2,00 | 1,00 | 2,00 | 0,00 | 1,00 | 1,00 |  | 6 |
| 18. | Hanušovce nad Topľovu, Kukorelliho 552 | 5 | 57,00 | 1,00 | 2,00 | 0,00 | 3,00 | 3,00 |  | 63 |
| 19. | Hnúšťa, Zápotockého 127 | 10 | 4,00 | 3,00 | 24,00 | 5,00 | 2,00 | 2,00 | deň otvorených dverí, športový deň, spol. stretnutia učiteľov, psychológa, asistentov, vedenia školy, rodičov, komunit. centra, spoločné kultúrne podujatie žiakov ZŠ a ŠZŠ | 33 |
| 20. | Jelšava, Námestie republiky 62 | 9 | 1,00 | 3,00 | 3,00 | 0,00 | 1,00 | 2,00 |  | 9 |
|  | SPOLU: | 158 | 124,00 | 50,00 | 99,00 | 17,00 | 37,00 | 35,00 |  | 308 |

Annex 3 - Monitoring of particpation of parents in the educational process

V mesiacoch september 2005 – február 2006 sme monitorovali kontakty medzi rodičmi žiakov tranzitívnej triedy a učiteľom resp. asistentom učiteľa, priemerný počet kontaktov (na jedného žiaka) uvádzame v tabuľke. Môžeme konštatovať, že systém školy sa podarilo otvoriť smerom k rodine. Pravdou je, že v niektorých lokalitách rodičia uprednostňovali skôr kontakt s učiteľom mimo školy, ale všade sa podarilo nadviazať efektívnu spoluprácu s rodinou, často prostredníctvom starých rodičov. Z uvedených dôvodov sú niektoré uvedené údaje mierne skreslené a reálnych kontaktov s rodičmi alebo rodinnými príslušníkmi dieťaťa bolo viac. Pozitívom je, že klesajúcu tendenciu mali respektíve sa v mnohých lokalitách vôbec nevyskytli kontakty vyvolané problémovým správaním dieťaťa (predvolanie rodičov, sankcionovanie rodičov a podobne).

| Monitoring participácie rodičov v edukačnom procese a spolupráca rodiny a školy |
| --- |
| september 2005 – február 2006 |
| P.č. | Špeciálna základná škola | Fekvencia kontaktov |
|  |  | Počet žiakov | Rodič navštívil triedu | Rodič sa stretol s učiteľom - rodič sám inicioval kontakt | Rodič sa stretol s učiteľom - učiteľ inicioval kontakt | Rodič sa zúčastnil rodičovského stretnutia | Iná forma kontaktu | Spolu počet kontaktov v Ø na jedného žiaka |
|  |  |  | Ø počet kontaktov na jedného žiaka | Ø počet kontaktov na jedného žiaka | Ø počet kontaktov na jedného žiaka | Ø počet kontaktov na jedného žiaka |  |  |
| 1. | Markušovce, Michalská 39 | 9 | 0,62 | 0,07 | 0,55 | 0,42 | neformálne stretnutia v obci | 2 |
| 2. | Zborov, Školská 478 | 9 | 1,00 | 0,83 | 1,00 | 0,50 | vianočná besiedka | 3 |
| 3. | Toporec 39 | 5 | 0,30 | 0,43 | 0,70 | 0,26 | návšteva osady, stretnutia v obci, príprava Helloween, návšteva učiteľa a asistenta v osade | 2 |
| 4. | Chminianske Jakubovany 22 | 10 | 0,66 | 0,00 | 1,50 | 0,66 | mimoškolské aktivity každý druhý mesiac | 3 |
| 5. | Stará Ľubovňa, Levočská 22 | 9 | 0,23 | 0,40 | 0,30 | 0,22 | rôzne mimoškolské aktivity 2 x mesačne | 1 |
| 6. | Prešov, Matice slovenskej 11 | 8 | 4,50 | 4,35 | 4,75 | 1,00 | návšteva v rodinách | 15 |
| 7. | Jarovnice 96 | 8 | 5,00 | 2,00 | 3,00 | 2,00 | 2 spoločné stretnutia rodičov a žiakov | 12 |
| 8. | Lipany, Tehelná 3 | 9 | 0,00 | 0,00 | 0,50 | 0,50 |  | 1 |
| 9. | Trebišov, M.R.Štefánika 83 | 9 | 8,00 | 4,00 | 8,00 | 5,00 |  | 25 |
| 10. | Trebišov, Poľná 1 | 7 | 5,00 | 3,00 | 4,00 | 2,00 | oznamy pre rodičov písomnou formou v slovníčku | 14 |
| 11. | Košice, Rovníková 11 | 7 | 1,00 | 0,00 | 1,00 | 0,42 |  | 2 |
| 12. | Košice, Inžinierska 24 | 7 | 4,00 | 2,00 | 2,00 | 0,00 |  | 8 |
| 13. | Košice, Odborárska 2 | 7 | 1,60 | 0,00 | 1,70 | 0,60 | náhodné stretnutia | 4 |
| 14. | Pavlovce nad Uhom, Hlavná 1 | 7 | 8,37 | 4,22 | 4,25 | 0,50 | návšteva v rodine | 17 |
| 15. | Veľké Kapušany, J. Dószu 32 | 7 | 2,14 | 1,86 | 1,14 | 1,14 | návšteva učiteľa v osade | 6 |
| 16. | Piešťany, Valová 40 | 8 | 2,00 | 9,00 | 3,00 | 1,00 |  | 15 |
| 17. | Lučenec, Zvolenská cesta 59 | 8 | 1,00 | 0,00 | 0,50 | 2,00 | spoločná príprava karnevalu - masky, návšteva v rodinách | 4 |
| 18. | Hanušovce nad Topľovu, Kukorelliho 552 | 5 | 2,00 | 2,00 | 1,60 | 0,33 | telefonicky, stretnutia v obci, návšteva v rodine | 6 |
| 19. | Hnúšťa, Zápotockého 127 | 10 | 2,10 | 0,50 | 2,10 | 0,60 |  | 5 |
| 20 | Jelšava, Námestie republiky 62 | 9 | 0,70 | 0,10 | 0,30 | 0,00 |  | 1 |
|  | SPOLU: | 158 | 50,22 | 34,76 | 41,89 | 19,15 |  | 146 |

Annex 4 - Monitoring of school attendance in the transitive classes

Na základe monitorovania školskej dochádzky môžeme jasne identifikovať lokality, v ktorých je ohrozením úspešnosti školskej kariéry dieťaťa práve dochádzka do školy. Výsledky uvedené v tabuľke, najmä počty neospravedlnených hodín, vypovedajú aj o chudobe a sociálnom vylúčení ľudí žijúcich v jednotlivých lokalitách a o naviazaní týchto faktorov na školskú kariéru dieťaťa – vysoko narástol počet neospravedlnených hodín v mesiacoch január, február, čo je do istej miery, podľa nášho názoru, spôsobené dlhou zimou, podmienkami na bývanie, nedostatkom teplého oblečenia detí, vzdialenosťou detského lekára, ktorý by vystavil potvrdenie o chorobe dieťaťa a podobne.

| Monitorovanie školskej dochádzky v tranzitívnej triede |  |  |
| --- | --- | --- |
| september 2005 – február 2006 |  |  |
| P.č. | Špeciálna základná škola ročník 1. | Počet žiakov | September | Október | November | December | Január | Február | Spolu počet vymeškaných hodín | Spolu počet vymeškaných hodín v priemere na 1 žiaka |
|  |  |  | počet prac. dní | počet prac. dní | počet prac. dní | počet prac. dní | počet prac. dní | počet prac. dní |  |  |
|  |  |  | 19 | 19 | 20 | 16 | 17 | 17 |  |  |
|  |  |  | Počet vymeškaných hodín | Počet vymeškaných hodín | Počet vymeškaných hodín | Počet vymeškaných hodín | Počet vymeškaných hodín | Počet vymeškaných hodín |  |  |
|  |  |  | ospr. | neospr. | ospr. | neospr. | ospr. | neospr. | ospr. | neospr. | ospr. | neospr. | ospr. | neospr. | ospr. | neospr. | ospr. | neospr. |
| 1. | Markušovce, Michalská 39 | 9 | 0 | 17 | 82 | 35 | 13 | 14 | 183 | 9 | 10 | 10 | 5 | 4 | 293 | 89 | 32,56 | 9,89 |
| 2. | Zborov, Školská 478 | 9 | 82 | 0 | 86 | 0 | 79 | 0 | 136 | 0 | 116 | 40 | 52 | 32 | 551 | 72 | 61,22 | 8,00 |
| 3. | Toporec 39 | 5 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 84 | 0 | 16,80 | 0,00 |
| 4. | Chminianske Jakubovany 22 | 10 | 44 | 0 | 88 | 20 | 23 | 72 | 54 | 33 | 8 | 24 | 20 | 4 | 237 | 153 | 23,70 | 15,30 |
| 5. | Stará Ľubovňa, Levočská 22 | 9 | 58 | 0 | 78 | 0 | 112 | 0 | 34 | 0 | 51 | 0 | 20 | 0 | 353 | 0 | 39,22 | 0,00 |
| 6. | Prešov, Matice slovenskej 11 | 8 | 72 | 0 | 155 | 15 | 274 | 42 | 147 | 97 | 358 | 134 | 135 | 92 | 1 141 | 380 | 142,63 | 47,50 |
| 7. | Jarovnice 96 | 8 | 0 | 0 | 59 | 4 | 62 | 2 | 10 | 34 | 45 | 36 | 37 | 55 | 213 | 131 | 26,63 | 16,38 |
| 8. | Lipany, Tehelná 3 | 9 | 13 | 134 | 15 | 105 | 136 | 21 | 54 | 12 | 108 | 170 | 97 | 32 | 423 | 474 | 47,00 | 52,67 |
| 9. | Trebišov, M.R.Štefánika 83 | 9 | 44 | 26 | 40 | 125 | 87 | 149 | 79 | 77 | 201 | 143 | 43 | 166 | 494 | 686 | 54,89 | 76,22 |
| 10. | Trebišov, Poľná 1 | 7 | 80 | 0 | 119 | 0 | 66 | 0 | 81 | 0 | 87 | 0 | 202 | 0 | 635 | 0 | 90,71 | 0,00 |
| 11. | Košice, Rovníková 11 | 7 | 31 | 47 | 42 | 0 | 46 | 0 | 79 | 0 | 148 | 0 | 149 | 0 | 495 | 47 | 70,71 | 6,71 |
| 12. | Košice, Inžinierska 24 | 7 | 75 | 190 | 52 | 215 | 34 | 285 | 95 | 202 | 99 | 181 | 80 | 136 | 435 | 1 209 | 62,14 | 172,71 |
| 13. | Košice, Odborárska 2 | 7 | 120 | 38 | 170 | 45 | 56 | 34 | 77 | 94 | 60 | 127 | 54 | 113 | 537 | 451 | 76,71 | 64,43 |
| 14. | Pavlovce nad Uhom, Hlavná 1 | 7 | 21 | 28 | 163 | 0 | 197 | 37 | 191 | 106 | 137 | 164 | 216 | 208 | 925 | 543 | 132,14 | 77,57 |
| 15. | Veľké Kapušany, J. Dószu 32 | 7 | 82 | 75 | 17 | 92 | 19 | 130 | 68 | 32 | 41 | 252 | 46 | 207 | 273 | 788 | 39,00 | 112,57 |
| 16. | Piešťany, Valová 40 | 8 | 90 | 82 | 123 | 84 | 138 | 84 | 184 | 68 | 193 | 71 | 140 | 60 | 868 | 449 | 108,50 | 56,13 |
| 17. | Lučenec, Zvolenská cesta 59 | 8 | 32 | 0 | 168 | 0 | 92 | 0 | 76 | 0 | 64 | 0 | 92 | 0 | 524 | 0 | 65,50 | 0,00 |
| 18. | Hanušovce nad Topľovu, Kukorelliho 552 | 5 | 21 | 14 | 38 | 0 | 22 | 0 | 68 | 0 | 34 | 0 | 5 | 17 | 188 | 31 | 37,60 | 6,20 |
| 19. | Hnúšťa, Zápotockého 127 | 10 | 23 | 18 | 33 | 13 | 97 | 4 | 51 | 9 | 71 | 0 | 168 | 15 | 443 | 59 | 44,30 | 5,90 |
| 20. | Jelšava, Námestie republiky 62 | 9 | 63 | 0 | 77 | 0 | 59 | 0 | 62 | 0 | 146 | 16 | 61 | 0 | 468 | 16 | 52,00 | 1,78 |
|  | SPOLU: | 158 | 951 | 669 | 1 605 | 753 | 1 632 | 874 | 1 729 | 773 | 2 041 | 1 368 | 1 622 | 1 141 | 9 580 | 5 578 | 60,63 | 35,30 |

Annex 5 – Proposal of tests for the transitive classes

# Upozornenie:

Len pre vnútorné potreby lektorov a učiteľov. Cvičný materiál!

Testovanie

# Matematika

1. ročník ŠZŠ

Eva Končoková

Testovanie

Slovenský jazyk

2. ročník ŠZŠ

Eva Končoková