monthly report

august 2005

# Contract 5821902-03-01/0002

# Integration of Roma Children into Regular Primary Schools

Date of issue of the Draft Monthly Report: 		September 5, 2005

Date of issue of the Final version of the Monthly Report:

November 11, 2005

Final version of the Monthly Report approved by: 	Novotná Kinga

Date of approval of the Final version of the Monthly Report:

CONTENT

list of acronyms	3

1	introduction	5

2	Project outputs and deliverables	6

2.1	List of outputs completed within the reporting period	6

2.2	List of outputs to be completed	6

3	Progress of the project during the reporting period	7

3.1	Development of the modified curriculum	7

3.2	Selection and preparation of the proper teaching methods	7

3.3	Working in the school environment	8

3.4	Cooperation between the partners involved in the project	9

3.5	Individual educational plans	9

3.6	Training program	10

3.7	Elaboration of the practical guidance book	11

3.8	Recommendations and proposals for the future actions	12

3.9	Presentation of the project results and outcomes	12

4	Factors influencing the implementation	13

4.1	Deviations from the initial work plan	13

4.2	Internal and external factors influencing the project implementation	13

5	Activities planned for the next reporting period	14

6	Annexes	15

6.1	Annex 1 – Expert’s input in the reporting period	15

6.2	Annex 2 – Building positive social atmosphere and environment in school	16

6.3	Annex 3 – Evaluation of the first training session for teachers and teacher assistants			24

list of acronyms

CC			Community Centre

CEEC			Central and Eastern European Countries

CFCU			Central Finance and Contracting Unit of the Ministry of Finance

C.o.L.			Collection of Laws

CV			Curriculum Vitae

CVPP			Centre for educational and psychological prevention

DERC	Department of Education of Roma Communities at Ministry of Education

ECO			European Consultants Organisation

EU			European Union

FR			Final Report

IEP			Individual Educational Plans

IR			Inception Report

MoEd			Ministry of Education of the Slovak Republic

M-PC			Methodological-Pedagogical Centre

MR 			Monthly Report

NGO			Non-Governmental Organisation

NMS		New Member States

NSD		Wide Open School Foundation

OG, SHRM		Office of Government, Section of Human Rights and Minorities

PIU		Programme Implementation Unit

PPAC		Pedagogic-Psychology Advisory Centre

PS		Primary school

RICPP		Research Institute of Child Psychology and Patopsychology

RO		Regional Office

ROCEPO		Roma education, information, documentation, advisory and consultancy centre

RR Screening		Test battery developed under Phare 2001 project

RSO		Regional School Office

RTA		Roma Teacher Assistant (Teacher Assistant)

SEI		Section of European Integration

SPI		State Pedagogical Institute

SPS		Special Primary School

SR		Slovak Republic

SSI		State School Inspection

TA		Technical Assistance

TL 		Team Leader

ToR		Term of Reference

UNDP		United Nations Development Programme

introduction

In the August, we continued in the implementation of the defined tasks in line with the time schedule. The progress has been achieved in the area of development of modified curriculum for the 1st and 2nd grade of the transitive classes, and by 15 August 2005 beneficiaries received the first draft of the modified curriculum for comments. In return, we received the comments from Mrs. Farkašová (RICPP), which were incorporated into the final version of the modified curriculum.

Parallel with the development of the modified curriculum, we worked on the elaboration of the appropriate educational and developmental methods for the transitive classes with emphasis on complex and intensive development of a child’s personality and support to its mental development. The first draft, which represents a basic methodological instrument for teachers and teacher assistants of the transitive classes, has been submitted by 15 August 2005 to beneficiaries for the comments. The methods of work in the transitive classes are compatible with the developed curriculum and enable a teacher to conduct the teaching lesson in comprehensive way and effectively. The material provides instructions and motivates teachers to implement new curriculum and teaching methods in the transitive and integrative classes, what requires that they understand the interrelations between social and emotional development and academic success of their pupils. They should be able of reflection and anticipation in relation to the educational needs of their pupils and practically and effectively utilize all their capacities, knowledge from their specialization: pedagogy and psychology, their own experiences from the educational practice and integrate them using the newly developed curriculum and methods in the transitive classes.

We also further developed the basic frameworks of plans for cooperation between school, family and community, which are partially incorporated in the methodological recommendations of the curriculum for the transitive class and will be presented during the training sessions. During working meetings with teachers and teacher assistants from both types of schools, we obtained and consequently analysed the experiences of the pedagogic staff in the field of cooperation with Roma community and between the schools. The creation of the plans for cooperation has to take into account the local specificities.

From 29th – 31st August 2005, the first training session for teachers and teacher assistants of special primary schools and primary schools was held. All project experts participated at the training session. More information on the training is provided in the chapter 3.6.

Further, we finalised the manual for the second training session for teachers and teacher assistants – Building a positive social atmosphere and environment in the school. The pupils selected for the transitive class has passed the psychological diagnosing, they are not mentally handicapped, but they are missing the information and skills, so not meeting the criteria of school readiness and without  stimulation probably not able to pass the standard primary school using the classic teaching methods. The role of the transitive class is to stimulate building of such a knowledge, social skills and overall development of personality of children coming from socially disadvantaged environment, which allows them to adapt to fulfilment of schools duties in the standard primary school. Pupils will be more motivated to learn, when we can create a pleasant and inclusive atmosphere in a classroom. Where people are respected, there is no need for threats. The emphasis is put on the relation between teacher and pupils (teacher assistant and pupils) since such good relationship can help to eliminate also the inappropriate learning environment at home, in case, we will not be successful to gain sufficient support and cooperation of parents.

Project outputs and deliverables

List of outputs completed within the reporting period

Modified curriculum for 1st and 2nd grade of the transitive classes (the draft submitted to the project beneficiaries),

Teaching and learning methods to be used in the transitive classes (the draft submitted to the project beneficiaries),

Building positive social atmosphere and environment in school – manual for the training of teachers and teacher assistants of special primary schools and standard primary schools (Annex 2),

Evaluation of the first training session for teachers and teacher assistants (Annex 3).

List of outputs to be completed

Proposal for the structure of work (and cooperation) with individual educational plans (September 2005),

Creation of plans for cooperation (September 2005),

Elaboration of inventories of appropriate methods for development of knowing yourself, self-confidence, communication skills, cooperation and creativity (September 2005),

Proposal for organisation and content of the training for psychologists (September 2005),

Elaboration of individual educational plans for pupils of the transitive class (September and October 2005),

Progress of the project during the reporting period

Development of the modified curriculum

The project team and its activities in the August focused on the finalisation of the draft of modified curriculum for 1st and 2nd grade of the transitive classes. The draft of the modified curriculum was submitted to the project beneficiaries (OG, SHRM and MoEd) for assessment and comments within the agreed deadline (15 August 2005).

Consequently, after the receipt of the comments of Mrs. Farkašová from the Research Institute of the Child Psychology and Pato-psychology on the submitted draft, the project experts concentrated on:

Detailed analysis and assessment of the comments on the draft of the modified curriculum,

Communication between the experts on the possibilities for an incorporation of the comments,

Incorporation and respecting of the comments in the preparation of the final version of modified curriculum,

Completion of the final version of the modified curriculum for 1st and 2nd grade of the transitive classes.

Selection and preparation of the proper teaching methods

For the methods proposed by the project team to be used in the transitive classes is characteristic that:

They are based in humanistic and democratic class management in a partnership.

Apply individual approach to a pupil as a unique human being.

Work with the class as a group is considered to be a core for the creation of working and social habits and life skills.

Taking into account the educational needs of socially disadvantaged children, we recommend using participative and experiential methods, which integrate the content into logic and authentic experience as basic methods.

Content wise, the material besides the main basis and developmental characteristics of pupils, which presents the introductory chapters and are important from the point of view of an introduction of the theoretical basis of the project and description of cognitive and personality development of pupils in the first grades of the primary school (grade1 – 4), provides general and also concrete methods of work in the following chapters:

From dominance of teacher to focus on a pupil,

Role of teacher in the classes focused on a pupil,

Creation of classes focused on a pupil,

Development of social skills,

Evaluation,

Cooperation with family.

The role of a teacher can not be substituted. The teacher educates, but also raises (tutors). He/she represents a model. Mainly during the beginning of the school attendance, teacher is very often an important, almost non-critically accepted model of behaviour and conduct. From the developmental point of view, at the beginning of the school attendance, the child is in age when it forms its own personality and is very sensitive to all influences from its environment. The teacher manages the educational process, modifies the learning environment, organises the work with learning material and in some extent is responsible for creation of the environment in his/her class.

Individual approach to pupils means mainly that the competition in the class is not supported and teacher identifies and develops in his/her pupils all types of capabilities. We suppose that learning through an experience and problem solving stimulates pupils to be active and adopt the information in the following order: experience – deduction of information – strengthening of information. It requires an empathy, intuition and creative skills of teachers as well as ability to perceive a pupil in complex, as a unique individual with a potential.

The important aspect, in our opinion, is the group work with the class - many skills, but also information (knowledge) should be, in some cases must be taught in the social context. A group can help an individual and represents a new quality. Individual learns and absorbs the information and experiences by influence of the group. If a pupil fells in the class accepted, then contributes, develops the sense of loyalty, belonging and responsibility.

Development of social skills, such as communication, empathy, skills for understanding and respecting me and other, as well as skills developing responsibility is part of methods for an education in the transitive classes. It leads to a better self-recognition and self-confidence of pupils, building the identification with a class and motivation to learn, encouragement to test new strategies and to even do mistakes. Development of social, life skills contributes to an activity of a pupil and activity is considered to be an important factor of the overall approach to a life.

In order to enrich the inventory of methods, we offer to the teachers also alternative methods to evaluate performance and behaviour of pupils, which are objective and we propose approaches for documenting of the evaluation. Parents are crucial for cooperation with a school. In this respect, one chapter is dedicated to the methods and forms of cooperation between school and family, mainly communication between school and family, meeting with parents, supporting the involvement of parents in voluntary activities in the schools and parents as partners of school.

Working in the school environment

In the month of August, we communicated with the school managements and pedagogical staff of special and standard primary schools involved in the project mainly via telephones and emails. We concentrated on the collection of information about the preparedness for the new school year, personal and material provision of model of transitive class in the special primary schools. The project experts tried to promptly respond to the identified problems and difficulties in the individual locations.

There was also an intensive communication in order to ensure participation of teachers and teacher assistants from both types of schools at the initial seminar, which took a place in Košice and Prešov. The teachers and teacher assistants were during the seminar provided with consultations on building educational environment of class, plans for cooperation with family and community and experiences with using the individual educational plans.

We assume, that the beginning of the new school year will require an intensive cooperation and communication with the individual schools involved in the project, mainly special primary schools opening the transitive classes. The project experts plan to personally visit the schools in the beginning of September in order to promptly solve the potential problems.

Cooperation between the partners involved in the project

Special and standard primary schools

Based on the previous consultations, interviews and studying of the relevant sources, we gradually prepare the basic framework for cooperation between the special and standard primary schools. This will serve as basis for elaboration and implementation of the concrete plans of cooperation. During the initial seminar, we also mentioned the importance of cooperation between both types of schools and pedagogic staff in the process of integration (reintegration) of children into standard primary schools.

Schools, parents and communities

We continue in the activities related with the preparation of inventory of activities for strengthening and improving the relations between school, parents and community, which focus on:

Collection and processing of information, experiences, comments ad proposals,

Analysis of the best practice,

Evaluation of implementation of plans for effective cooperation of school with parents and community.

The inventory of the activities for strengthening the cooperation is gradually being completed. The actual activities will be implemented as out of school activities with participation of families of pupils and wider community.

Schools and psychologists (RICPP)

In August, we kept on being in contact with psychologists responsible for psychological diagnosing of children in Toporec and Zborov, where the diagnosing and selection of children for the transitive classes has not been finished. The attention was paid to preparation of the content and organisation of the first training session for psychologists participating in the project.

Cooperation with the Research Institute of Child Psychology and Pato-psychology and the assigned representative cooperating with the project team is without problems. In this respect, we appreciate a prompt delivery of the comments on the draft of modified curriculum for 1st and 2nd grade of the transitive classes.

Other relevant partners

In the month of August, we mainly organised the working meetings among the project experts, eventually with the representatives of the consortium leader aimed at fulfilment of given tasks in line with the Terms of Reference.

Individual educational plans

In the area of individual educational plans we continued in the activities that started in the previous months:

Acquiring the information about using and experience with individual educational plans in both types of schools and its analysis in the relation to the educational needs of pupils attending transitive class,

Studying of literature, casuistic, existing individual educational plans for children coming from socially disadvantaged environment,

Exchange of experience in the area of individual educational plans and conditions for its development,

Elaboration of a plan of cooperation within the framework of individual educational plans.

Training program

Training of teachers and teacher assistants from special primary schools

Training of teachers and teacher assistants from standard primary schools

In the month of August (29 – 31 August 2005), we organised in Prešov and Košice the first training session for teachers and teacher assistants of special and standard primary schools. The main objectives of the training session, which aimed at building the multicultural competences and introduction of modified curriculum and its use in transitive classes were to:

Develop multicultural and intercultural competences of participants – competences of intercultural understanding and skills, knowledge and attitudes necessary for development of multicultural education,

Support the mutual tolerance and understanding the difference of individuals and social groups,

Support an acceptance of cultural and ethic specificities of Roma,

Develop pedagogic knowledge and thinking of teachers and teacher assistants, deepen, improve and widen their pedagogic competences in a way that they can provide an adequate education to Roma children in line with the democratic principles,

To get familiar with the terms (terminology) and content of the modified curriculum for the transitive classes,

Introduce to participants the components of the modified curriculum for the transitive classes and its specificities,

Acquire skills for creation of time-thematic plans according to the modified curriculum taking into account the individual needs of pupils.

71 teachers and teacher assistants participated at the training session and in general, they evaluated the quality of the training positively (in average 4 points from maximum 5 points). The details on the training and its evaluation by participants are presented in the Annex no. 3.

The main objective of the second training session for teachers and teacher assistants of special and standard primary schools with a title „Building positive social atmosphere and environment in school“ is to introduce to participants strategies for management of class and building of inclusive environment. The session is supposed to inform the teachers how to build positive social atmosphere in the class, how to avoid confrontations, how to use appropriate interventions and professionally solve the conflict situations with emphasis on social-cultural specificities of Roma pupil. Our intention is also to train the participant to strengthen and support the wanted behaviour of their pupils based on the correct diagnosing. The training session will be held on 26 and 27 September 2005 in Košice a Prešov under responsibility of Mrs. Daniela Čechová a Mrs. Miroslava Čerešníková.

We consider the integration of personality – development of cognitive, emotional and behavioural aspects of teacher’s personality as a basis for development of teacher’s competences. Topics to be presented and covered:

Humanistic concepts of building of social atmosphere,

Social-cultural specificities of Roma children in school,

Small social group and its dynamics,

Techniques for building positive social atmosphere,

Class management and academic success of pupils,

Diagnosing of pupil’s behaviour,

Interventions and conflict solving,

Cooperation and inclusion in a class

Training of psychologists cooperating with the schools

Activities were oriented on the preparation of proposal of basis, objectives, content and organisation of training sessions for psychologists cooperating with the schools involved in the project.

Proposal for content and organisation of the training sessions:

1st training session (November 2005):

Multicultural education in school, multicultural competences of teacher and teacher assistant

Modified curriculum and teaching methods in the transitive classes

Lecturers: E. Končoková, A. Petrasová, K. Majzlanová

2nd training session (probably December 2005- together with teachers and teacher assistants)

Partnership and communication of school, family and community

Lecturers: D. Čechová, M. Čerešníková, E. Končoková, A. Petrasová, K. Majzlanová

3rd training session (January 2006)

Diagnostic methods, application of new diagnostics in practice with emphasis on the specificities of the transitive classes

Social-cultural specificities of Roma children

Integration of Roma children from transitive classes into the standard primary school classes

Lecturers: D. Čechová, M. Čerešníková (we propose to invite also the authors of the new methodologies: E. Farkašová, B. Mesárošová, p. Marušková)

Based on the presented structure, we will in September elaborate the manual for the training for psychologists.

Elaboration of the practical guidance book

In this field we continued in collecting relevant information and best practices, which will be used as a basis for elaboration of the practical guidance book.

Recommendations and proposals for the future actions

Institutional level

Focus on the development of newer forms of cooperation of school and other institutions with family, cooperation with community centre and social department.

Content level

Harmonisation of the content of modified curriculum with time-thematic plans.

Adapting the educational plans to individual needs of individual pupils, which will be part of IEP.

Implement supporting mechanisms in areas, which can cause the failure of pupils (transport of pupils to school, preparation for education, provision of meals, travel costs, material need).

Legislative level

Solve the questions about managing (writing) school documentation in transitive classes.

Presentation of the project results and outcomes

So far produced project outcomes were presented to teachers and teacher assistants during the seminar that took a place in Prešov and Košice.

Factors influencing the implementation

Deviations from the initial work plan

The modified curriculum for 1st and 2nd grade of transitive classes was completed and submitted one month earlier in comparison to time schedule presented in the Inception report.

Preparation and monitoring of the individual educational plans is shifted to the next period (September – October) due to the summer holidays and unfinished additional psychological diagnosing of pupils.

The training for cooperating psychologists will be delivered in November 2005, when there will be an opportunity for model solutions of concrete problems of pupils of the transitive classes (based on the requests of teachers and psychologists).

Elaboration of plans for cooperation and methodology for reintegration of pupils to the standard primary schools is directly dependent on the receipt of comment of SPI on the draft of curriculum and teaching and learning methods for transitive classes (the reason for deviation from the original work plan).

Internal and external factors influencing the project implementation

In August, there were no external or internal factors substantially influencing the implementation of the project and its activities.

We received the comments of Mrs. Farkašová (RICPaP) on the draft of modified curriculum for 1st and 2nd grade of transitive classes.

Activities planned for the next reporting period

Assistance in the establishment and functioning of transitive classes from the beginning of the school year (monitoring of psychological diagnosing, solving the potential problems),

Completion of modified curriculum for transitive classes,

Modification and adaptation of activities and techniques within the framework of defined methods for development of child’s personality and its social competence,

Elaboration of framework for concrete plans for development of cooperation of school with family of pupil and community,

Preparation and delivery of the training session for teachers and teacher assistants: Building positive social atmosphere and environment in school, which will take a place on 26-27 September 2005 in Košice and Prešov,

Preparation of training programme for psychologists participating in the project,

Preparation of individual educational plans and its monitoring,

Preparation of plans for cooperation between special and standard primary schools,

Development of methodology for reintegration of children into standard primary school,

Selection of suitable teaching methods for pupils re-integrated into standard primary school,

Elaboration of individual educational plans for re-integrated pupils,

Collection of relevant information and strategies for elaboration of practical guidance book, preparation of a preliminary outline,

Assistance provided to special primary schools, assistance in establishing and functioning of transitive classes,

Support and strengthening of cooperation between both types of schools in individual locations,

Consultations for teachers of both types of schools,

Provision of professional guidance to teacher of transitive classes,

Implementation of out of school activities in the schools,

Integration/re-integration of re-diagnosed children into standard primary schools in a methodological way,

Tutoring of re-integrated children in the standard primary schools,

Monitoring of functioning of transitive class model – development of monitoring instruments,

Assessment of interventions and quality control,

Formulation of proposals and recommendations for the next steps,

Communication with relevant partners,

Presence on the experts meetings (Steering committee),

Information on the progress achieved in September.

Annexes

Annex 1 – Expert’s input in the reporting period

| Project title: INTEGRATION OF ROMA CHILDREN INTO REGULAR PRIMARY SCHOOLS | Programme title: FURTHER INTEGRATION OF ROMA CHILDREN IN THE FIELD OF EDUCATION AND IMPROVED LIVING CONDITIONS | Country: SLOVAK REPUBLIC |
| --- | --- | --- |
| Implementation period: 04/2005 – 04/2006 | Prepared on: 02/09/2005 | Contractor: ECO, Belgium |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |  |
| Name of the Expert | 04/05 | 05/05 | 06/05 | 07/05 | 08/05 | 09/05 | 10/05 | 11/05 | 12/05 | 01/06 | 02/06 | 03/06 | 04/06 | Total spent | Total Available |
| Eva Končoková Team Leader | 0 | 12 | 17 | 13 | 13 |  |  |  |  |  |  |  |  | 55 | 95 |
| Daniela Čechová Key expert no. 2 | 15 | 20 | 17 | 19 | 21 |  |  |  |  |  |  |  |  | 92 | 128 |
| Miroslava Čerešníková Key expert no. 3 | 17 | 15 | 15 | 20 | 21 |  |  |  |  |  |  |  |  | 88 | 132 |
| Katarína Majzlánová Key expert no. 4 | 14 | 15 | 18 | 22 | 19 |  |  |  |  |  |  |  |  | 88 | 132 |
| Alica Petrasová Key expert no. 5 | 13 | 17 | 17 | 22 | 20 |  |  |  |  |  |  |  |  | 89 | 131 |

Annex 2 – Building positive social atmosphere and environment in school

Budovanie pozitívnej sociálnej atmosféry a prostredia v škole

(Manuál odborno-metodického semináru pre učiteľov a rómskych asistentov učiteľov špeciálnych základných škôl a bežných základných škôl)

2005

OBSAH

- Východiská

- Ciele

  - Ciele semináru

  - Predpokladané výsledky

- Obsah a organizácia

- Literatúra

- Prílohy

1 Východiská

V dobách antiky, v starovekom Grécku, bola vyslovená téza: „Človek je tvor spoločenský“. Už novorodenec sa vyznačuje prosociálnym správaním - inklináciou k ľudskej spoločnosti. Dvoj-trojmesačné dieťa sa nediferencovane usmieva na všetky tváre, pretože patria k jeho druhu. Sme doslova nastavení na život v určitej societe, ktorá na nás vplýva, a tak spolu so zdedenými dispozíciami formuje našu osobnosť.

Aby sa človek stal adaptovanou a šťastnou osobnosťou, potrebuje, aby sa v sociálnom prostredí, v ktorom sa nachádza, a kde prichádza do interakcií s inými ľuďmi, cítil dobre. Cítime sa dobre vtedy, ak sme presvedčení, že niekam patríme a máme svoje miesto. Uspokojenie potreby „patriť“ následne vedie k prispievaniu, lojalite a zodpovednosti. Týmto všetkým potom smerujeme k sebaaktualizácii ako najvyššiemu stupienku rozvoja osobnosti.

Primárnou sociálnou skupinou je pre každého zvyčajne rodina, ktorá mu sprostredkúva primárny vplyv kultúry, učí ho orientácii vo svete symbolov, zvykov, hodnôt. Z histórie Rómov vieme, že tradičná rómska rodina prijímala dieťa ako dar, bolo pre rodičov požehnaním a žena, ktorá nemala viac detí, bola rómskou komunitou považovaná za menejcennú(Říčan, 1998; Liégeois, 1995). Pre zdravý vývin dieťaťa je však dôležité aj presadenie sa v rodine, získanie záujmu zo strany rodičov a súrodencov, možnosť zapájať sa do rozhodovania, schopnosť napĺňať a regulovať svoje potreby a žiadosti.

Zároveň sa však potrebuje primerane socializovať do väčšej spoločnosti, v ktorej žije jeho komunita a osvojiť si kultúrne vzorce, ktoré v nej fungujú. Fáza začlenenia rómskeho dieťaťa z „iného“ sveta do kultúrno-spoločenského prostredia európskej krajiny sa javí ako problémová a pre samotné rómske dieťa frustrujúca a neraz zraňujúca. Rómske dieťa, pre ktoré je jeho rodina, so svojimi zvykmi, hodnotami a normami celým svetom, sa v šiestich rokoch dostáva zrazu do sveta celkom odlišného, plného nových ľudí, vecí, pravidiel a povinností, ktoré do „jeho“ sveta nepatria. Dostáva sa do školskej triedy, ktorá by mala byť jeho referenčnou skupinou.

Skúsenosti zo zahraničia potvrdzujú, že deti i dospelí z odlišnej kultúrnej či etnickej skupiny prežívajú najmenej stresu vtedy, ak si čiastočne uchovávajú hlavné špecifiká a normy svojej kultúry a čiastočne sa prispôsobujú väčšinovej kultúre. Ak sa snažia úplne asimilovať, prípadne ak kompletne odmietajú väčšinovú spoločnosť, vyúsťuje to do distresu, depresie a maladujustácie. Ak chceme dieťaťu uľahčiť prispôsobenie sa školskému prostrediu a socializáciu v triede je potrebné brať túto skutočnosť do úvahy.

Dieťa si v triede, v skupine rovesníkov, pod vedením učiteľa, osvojuje a prehlbuje sociálne skúsenosti s inými ľuďmi, na základe ktorých potom realizuje svoje interakcie a rozvíja sociálne zručnosti.

Trieda by sa pre žiakov mala stať pozitívnym, stimulujúcim a bezpečným prostredím. Dôraz má byť kladený na rozvíjanie vzťahov medzi dieťaťom a dospelým, či pôjde o učiteľa, jeho asistenta alebo psychológa, ktorý spolupracuje so školou. Bowlbyho teória attachmentu aj individuálna psychológia (Nicoll, 2004) potvrdzujú, že ak je v živote dieťaťa aspoň jeden dôležitý blízky človek, do značnej miery to redukuje potencionálne emocionálne problémy a ťažkosti. Jedinečný vzťah medzi dieťaťom a školským profesionálom môže pomôcť eliminovať negatívne rodinné prostredie, dokonca ak sa nám nepodarí získať dostatočnú podporu a spoluprácu zo strany rodiny. Teória skupinovej socializácie (Harris, 2000) priniesla množstvo dôkazov o tom, že naučené správanie sa prispôsobuje konkrétnym vzťahom a kontextu, inými slovami jeho účinky sú špecifické kontextu, v ktorom bolo naučené správanie formované. Konzekventne, vstupom dieťaťa do školy, v ktorej trávi značný čas, bude významné, s čím sa v nej stretne.

Ak sa proces socializácie v prostredí školy nerealizuje pozitívne, z rómskeho dieťaťa sa stáva outsider skupiny, vzápätí sa dostáva na okraj i kvôli vzdelávacím výsledkom, a tak sa snaží kompenzovať novovzniknutý cit menejcennosti produkciou nevhodného správania s cieľom dať o sebe vedieť.

Aby sme sa tomu vyhli, vo výchovno-vzdelávacej praxi je dôležité zamerať pozornosť na budovanie pozitívnej sociálnej atmosféry v triede, na optimalizáciu interakcie učiteľ - žiak a na spôsoby eliminácie problémového správania rómskych žiakov, pretože inštitucionalizovaná socializácia rómskych detí je v našich (i európskych) kultúrno-spoločenských podmienkach problematická, a to nielen z hľadiska etnicko-kultúrnych odlišností v hodnotovej orientácii a tradíciách v rodinnom živote, z hľadiska sociálno-ekonomického postavenia v spoločnosti, ale hlavne z pohľadu rozvoja citu spolupatričnosti u rómskych detí, a zároveň ich sociálnej akceptácie a prijímania rovesníkmi a učiteľmi.

Cestou k budovaniu pozitívnej sociálnej atmosféry v triede i v prostredí školy sú princípy humanistickej a kooperatívnej výchovy. Je dôležité vziať do úvahy progresívne názory a výskumné nálezy svedčiace o vzťahu medzi sociálno-emočným vývinom a školským výkonom (Pratt, Mastroianni, 1984, Webb, Brigman, Campbell, 2005 a iní). Kľúčom k lepšiemu výkonu je lepšia atmosféra v škole, a tú možno dosiahnuť zlepšením kvality vzťahov medzi učiteľom a žiakom. Učitelia, ktorí riadia triedu na partnerských a demokratických princípoch stanovia hranice, avšak správajú sa k žiakom s rešpektom a všemožne ich povzbudzujú. Učia ich spolupracovať, robiť rozhodnutia a niesť si za ne zodpovednosť. Dodávaním odvahy stúpa žiakom sebadôvera, zlepšuje sa ich sebaobraz a tiež sebakontrola, vhodné a prispôsobivé správanie. Spolupráca je nevyhnutná pre efektivitu každej skupinovej aktivity a je priam životne dôležitá pre účinnú inklúziu, inkluzívne prostredie triedy.

Ak nezískame žiakov pre spoluprácu a spolupatričnosť, môžeme očakávať, že sa budú snažiť získať osobnú dôležitosť nežiaducimi spôsobmi, ktorými viac či menej narušia vzdelávací proces v celej triede. Vyriešenie takýchto situácií obyčajne stojí na pedagogickom a ľudskom majstrovstve učiteľa. Ak však učiteľ nemá potrebné informácie z oblasti psychológie a dôvodoch a cieľoch nevhodného správania žiaka, nedisponuje technikami efektívneho zvládania výchovných problémov v škole, a navyše je vyčerpaný neustálym napomínaním, trestaním a „riešením“ problémového správania žiaka, nebude už mať silu zostať nad problémovou situáciou, a nechá sa do nej vtiahnuť, bude sa cítiť nahnevaný, bezmocný, porazený a jeho výchovné zásahy nebudú adekvátne, s dlhodobými účinkami.

Hlavným cieľom výcvikového seminára je naučiť učiteľov a ich asistentov ako budovať sociálnu atmosféru spolupráce v triede, ako sa vyhýbať konfrontáciám, používať vhodné intervencie a fundovane riešiť konflikty, s dôrazom na sociálno-kultúrne špecifiká rómskeho žiaka. Taktiež je naším zámerom vyškoliť účastníkov, aby vedeli na základe správnej diagnostiky posilňovať  a podporovať žiadúce správanie svojich žiakov.

2 Ciele

Ciele seminára

- Priblížiť východiská vybraných humanistických koncepcií aplikovaných v systéme výchovy a vzdelávania – Rogers, Adler, Goleman, Dreikurs

- Stimulovať a rozvíjať partnerský prístup k dieťaťu za rešpektovania a akceptovania jeho individuality

- Oboznámiť učiteľov a ich asistentov so zastúpením a významom faktorov, ktoré ovplyvňujú školskú úspešnosť žiakov

- Viesť k vytváraniu atmosféry dôvery a bezpečia v školskej triede

- Mať zažité fungovanie skupinovej dynamiky

- Rozvíjať schopnosť sebapercepcie

- Rozvíjať schopnosť poznávania iných prostredníctvom empatie a intuície

- Osvojiť si zručnosti práce s technikami rozvoja sociálnych zručností – kooperácie, asertivity, zodpovednosti, empatie a sebakontroly

- Podporovať osvojenie spôsobov a techník na zabezpečenie spolupráce a inklúzie v triede

- Zabezpečiť, aby si učitelia osvojili štýly riadenia triedy s dôrazom na demokratický triedny manažment

- Predstaviť systematický prístup k diagnostike správania žiakov v škole.

- Rozvíjať u účastníkov schopnosti správnej identifikácie a diagnostiky správania žiakov.

- Prezentovať zásady výchovných intervencií učiteľa v triede.

- Vyškoliť účastníkov v používaní repertoáru intervenčných stratégií a zručností riešenia konfliktov v triede.

- Akceptovať význam kooperácie medzi jednotlivými účastníkmi výchovno-vzdelávacieho procesu.

- Rozvíjať kooperatívne budovanie pozitívneho školského prostredia.

- Prostredníctvom zážitkového učenia priblížiť techniky riešenia problémov, mediácie, práce s predsudkami, budovania pozitívneho prostredia pre edukáciu

Predpokladané výsledky

- Byť schopný pracovať s triedou ako malou sociálnou skupinou, osvojiť si a vedieť využívať situačne primeraný štýl riadenia triedy

- Disponovať zručnosťami potrebnými na budovanie pozitívnej sociálnej atmosféry v triede

- Mať zažitý vplyv sociálno-psychologických intervenčných a rozvíjajúcich techník na prežívanie a správanie v reálnej malej sociálnej skupine

- Dokázať správne identifikovať a diagnostikovať správanie žiakov v triede

- Vedieť kompetentne intervenovať pri výskyte problémov a konfliktov v triede

3 Obsah a organizácia

Deň 1

9.00 - 11.00:	Humanistické koncepcie budovania sociálnej atmosféry

11.00 - 11.30:	Prestávka

11.30 - 13.00:	Sociálno-kultúrne špecifiká rómskeho dieťaťa v škole

13.00 - 14.00:	Obed

14.00 - 15.30:	Malá sociálna skupina a jej dynamika

15.30 - 16. 00:	Prestávka

16.00 - 17.30:	Techniky budovania pozitívnej sociálnej atmosféry

17.30 - 18.00:	Spätná väzba

Deň 2

9.00 - 11.00: 		Manažment triedy a školská úspešnosť žiakov

11.00 - 11.30:		Prestávka

11.30 - 13.00:		Diagnostika správania žiakov

13.00 - 14.00:		Obed

14.00 - 15.30:		Intervencie a riešenie konfliktov

15.30 - 16. 00:		Prestávka

16.00 - 17.30:		Spolupráca a inklúzia v triede

17.30 - 18.00:		Spätná väzba

4 Literatúra

- Albert, L . : Cooperative Discipline. AGS, Circle Pines 1996a.

- Albert, L. : Cooperative Discipline. Implementation Guide. AGS, Circle Pines 1996b.

- Bratská, M.: Metódy aktívneho sociálneho učenia a ich aplikácia. Bratislava: UK, 2000

- Dreikurs, R. , Grunwald, B. B. , Pepper, F. C. : Maintaining Sanity in the Classroom. HarperCollins, New York 1982.

- Gajdošová, E. – Herényiová, G.: Škola rozvíjania emocionálnej inteligencie. Bratislava: Príroda, 2002

- Harris, J. R.: Socialization, Personality Development, and the Child´s Environments: Comment on Vandell . Developmental Psychology, 2000, 26, è. 6, s. 711 - 723.

- Křivohlavý, J.: Jak si navzájem lépe porozumíme. Praha: Návrat, 1997

- Liégeois, J.P.: Rómovia, cigáni, kočovníci. Bratislava: Rada Európy, 1995

- Nicoll, G. W. : Konzultačné stratégie s deťmi a adolescentmi v psychoterapii. Slovenská adlerovská spoločnosť, Bratislava 2004.

- Pike, G. – Sellby, D.: Cvičení a hry pro globální výchovu I. Praha: Portál, 2000

- Pike, G. – Sellby, D.: Cvičení a hry pro globální výchovu II. Praha: Portál, 2000

- Pratt, A. B. , Mastroianni, M. : How Corsini Four-R Scholls Work. Pratt, Mastroianni, 1984.

- Říčan, P.: S Romy žít budeme, jde o to jak. Praha: Portál, 1998

- Smith, Ch.: Trieda plná pohody. Praha: Portál, 1994

- Walton, F. X., Powers, G. : Ako vychádzať s deťmi. Nové Zámky: Psychoprof, 2002.

- Webb, L. , Brigman, G. , Campbell, C. : Linking school counselors and student success: A replication of the Student Success Skills approach targeting the academic & social competence of students. Professional School Counseling, 2005, 8, č. 5, s. 404 - 411.

Annex 3 – Evaluation of the first training session for teachers and teacher assistants

Informácie  o odborno-metodickom seminári

Dátum: 	30.- 31. augusta 2005

Miesto: 	Prešov, Košice

Témy:

- Predstavenie modifikovaných učebných osnov pre potreby tranzitívnych tried. Zohľadnenie individuálnych potrieb žiakov

- Multikultúrne kompetencie učiteľa a asistenta učiteľa

- Diferenciácia učenia a vyučovania z aspektu individuálnych a kultúrnych odlišností žiakov

Počet účastníkov: 71

Vyhodnotenie

- Čo bolo na seminári najväčším prínosom:

- riešenie konkrétnych problémov z praxe

- oboznámenie sa zo základnými pojmami projektu, podmienkami a kritériami zriadenia tranzitívnych tried

- oboznámenie sa s modifikovanými učebnými osnovami

- tvorba časovo-tematických plánov

- analýza učebných osnov, obsahy

- výmena skúseností s inými učiteľmi

- práca s textom

- nové informácie o rómskej komunite, o živote Rómov, ich zvyky a obyčaje

- podstata diferencovaného vyučovania

- nové formy učenia v tranzitívnej triede

- príjemná atmosféra

- Čo sa v dôsledku tohto seminára zmení vo vyučovaní učiteľov:

- obsah vyučovania

- tempo vyučovania

- celý prístup vzhľadom na učebné osnovy a potrebu pedagogickej tvorivosti a náročnosti výberu a uplatnení metód

- ešte to neviem posúdiť, ale určite sa veľa zmení

- naruší sa vyučovanie na ZŠ, následne zatiaľ nič

- zmena v prístupoch, posun k individualizácii, zohľadňovanie schopností, záujmov žiakov pri výbere cieľov, posudzovaní výkonov

- užšia spolupráca medzi ŠZŠ a ZŠ (s tranzitívnou triedou)

- budú sa používať IVP

- užšia spolupráca učiteľa s rodičmi žiakov

- uplatnenie nových metód, princípov, flexibilita, tvorivosť, reflexia

- trieda, zloženie triedy

- potrebujem viac informácií

- diferenciácia vyučovania, variabilita podnetov podľa individuálnych potrieb žiakov

- Celkové hodnotenie uskutočneného seminára:

1		   2              	  3	         	   4 		5

málo hodnotný 					veľmi hodnotný

- O ktoré ďalšie témy na budúcich seminároch je záujem:

- metodika vyučovania

- individuálne vzdelávacie plány

- praktické ukážky, didaktické hry

- výmena skúseností z praxe iných škôl, otvorené hodiny, priame ukážky z jednotlivých predmetov

- komunikácia s rodičmi

- integrácia z tranzitívnej triedy do triedy ZŠ

- doplnkové aktivity na zvýšenie kvality vyučovania

- náplň práce asistenta učiteľa

- práca v rómskej komunite

- tímová práca - pedagóg, psychológ, špeciálny pedagóg – priame ukážky, stretnutia

- diferenciácia na vyučovacej hodine

- práca s integrovanými žiakmi

- práca v centrách aktivít

- ďalšie informácie o realizácii projektu

- nástroje zlepšovania dochádzky

- Poznámky týkajúce sa seminára:

- pestrosť aktivít v časti multikultúrne kompetencie učiteľa

- časovo náročné, veľa novej teórie, postupovať pomaly

- obsah prakticky zameraný, osobná účasť nevyhnutná

- pre učiteľky ZŠ viesť aj samostatné semináre na témy učiteľ – žiak, modifikovanie učebných cieľov

- seminár náročný na celodenné sústredenie

- seminár naplnil osobné očakávania

- projekt posunúť na základné školy, kde je veľa slabých žiakov

- Očakávania participantov v rámci odborno-metodických seminárov

Poznať a získať zručnosti v nasledovných oblastiach:

- Zvládnuť úlohu asistenta učiteľa, jeho povinnosti

- Využitie vyučovacích metód a pomôcok, tvorba IVP

- Ukážky vyučovacích hodín alebo jej časti, štruktúra vyučovacích hodín

- Usporiadanie tranzitívnej triedy

- Súbor aktivít pre deti v triedach s limitovaným priestorom

- Motivácia rodičov na dosiahnutie pravidelnej dochádzky detí a spolupráce so školou

- Zosúladiť individuálne a frontálne vyučovanie, vedieť pracovať s učebnými plánmi a osnovami, zostaviť mesačný plán

- Motivácia voľnočasových aktivít

- Odstrániť rečové bariéry a zvýšiť slovnú zásobu žiakov

- Integrácia žiakov, práca s IVP v triedach ZŠ, vyrovnávanie rozdielov

- hodnotenie a sebahodnotenie žiakov

- poznanie inovatívnych metód

- Práca s hyperaktívnymi žiakmi

- Modifikácia učebných osnov

- Práca v centrách učenia

Otázky participantov:

- Je možnosť vrátiť sa zo ZŠ do tranzitívnej triedy ŠZŠ?

- Aká bude pedagogická dokumentácia tranzitívnych tried?

- Ako sa zabezpečí účasť učiteľov ZŠ na pozorovaniach v ŠZŠ počas vyučovania?

- Či budú následné semináre aj pre vedenie školy?

- Či sa doplní aj materiálne vybavenie ZŠ integrujúcich žiakov?

- Aké bude ocenenie učiteľov tranzitívnych a integrujúcich tried?