|  | Slovak Republic |
| --- | --- |
| Report No. M/SR/CIV/03006 SMSC: Civil Society Date of Issue of the Report: 12 February 2004 Reporting Period: 1.9.2003 – 31.12.2003 | Sectoral Components covered: Political Criteria and Minorities Institution issuing the Report: Aid Co-ordination Unit |

Table of Contents

Introduction	2

Executive Summary	3

Glossary of Acronyms	5

1. PROJECT BASIC DATA	7

1.1 Financial Data in €	7

1.2 Risks, Assumptions and Conditions	9

1.3 Administrative Changes	12

2. MONITORING DATA	13

2.1 Monitoring of Contracts and Deviations	13

2.2 Achievement of Objectives	16

2.3 Monitoring of Co-financing Costs in €	20

3. CONCLUSIONS	21

4. Proposed corrective actions for decision by SMSC and update of the recommendations of interim evaluation follow-up table	24

4.1 Proposed corrective actions for decision by SMSC	24

4.2 Update of the recommendations of the interim evaluation follow-up table	25

ANNEXES	28

Annex 1: Contact List	28

Annex 2: Sources of Information	30

Annex 3: Agenda	31

Annex 4: Contracting Schedule for SR0103.02 Infrastructure for Roma Settlements ……………NA

# Introduction

This Monitoring Report (MR) provides basic information on the stage of implementation of the Phare assistance under the Sectoral Monitoring Subcommittee (SMSC) Civil Society for the period between 1 September 2003 – 31 December 2003 (cut-off date). It provides regular and updated information on the last project developments to all the parties involved or interested in monitoring progress of the projects under the SMSC. In addition, this document may be used as a source of information to brief the European Commission representatives and the evaluators on the state of play of project implementation.

| Type of Report | Sectoral Monitoring Report |
| --- | --- |
| Country | Slovak Republic |
| SMSC | Civil Society |
| Sectoral component | Political Criteria and Minorities |
| Projects covered | SK0013 ACCESS SK0002 Improvement of the Situation of the Roma in the SR SR0103.01 Support to the Roma Minority in the Educational Field SR0103.02 Infrastructure for Roma Settlements 2002/000.610.03 Further integration of Roma children in educational field and improved living conditions 2003-004-995-01-05 Support to Integration of Roma in Education 2003-004-995-01-06 Improved Access to Health Care for Roma Minority in the SR |
| Report number | M/SR/CIV/03006 |
| Reporting Period | 1 September 2003 – 31 December 2003 (cut-off date) |
| Date of issue | 12 February 2004 |
| Programme Implementing Unit | Civil Society Development Foundation - SK0013 DPC, Slovak Government Office - SK0002; SR0103.01; SR0103.02; 2002/000.610.03 Phare Implementation Unit, Ministry of Education of the SR - 2003-004-995-01-05 Foreign Aid Project Unit, Ministry of Health of the SR - 2003-004-995-01-06 |
| Implementing Agency | CSDF - SK0013 CFCU - SK0002; SR0103.01; 2002/000.610.03 (activity 1); 2003-004-995-01-05 and 06 RDSA - SR0103.02; 2002/000.610.03 (activity 2 and 3) |
| Institution issuing the Report | Aid Co-ordination Unit |
| Previous Sectoral Monitoring Report | M/SR/CIV/03005 (issued: 29.09.2003) |
| Connected Interim Evaluation Reports | No. R/SK/JHA/03.044 (issued: 10.03.2003) No. R/SK/CIV/03.045 (issued: 26.03.2003) No. R/SK/CIV/03.048 (issued: 09.12.2003) |

# Executive Summary

The Sectoral Monitoring Report (MR) covers seven projects in the field of the Sectoral Monitoring Sub-committee (SMSC) - Civil Society (CIV) and its Sectoral Component – Political Criteria and Minorities for the reporting period 1September 2003 – 31 December 2003.

The MR provides basic financial data, follow-up of the risks, assumptions and conditions of the projects, essential information on administrative changes, delays and deviations, achievement of objectives and co-financing costs.

The readers of the MR are supposed to get familiar with the respective project fiches if more information regarding the projects is needed. Annex 2 provides a list of further documents related to the projects.

An interim evaluation report for the CIV sector was issued by the EMS on 9 December 2003. A debriefing meeting is scheduled for 3 February 2004. Due to the holiday season and undeveloped internal procedures on substitutability within the administration of some implementing stakeholders the debriefing meeting will fail to be organised within the one-month period after the issue of the report as required by the IE Guide. This could cause that some of the recommendations will be no longer relevant (see part 4.1 for a corrective action).

On 13 November 2003 the EMS delivered training on indicators with particular focus on institution building (IB) projects in CIV sector. The formulation of objectively measurable IB indicators proofed to be very problematic, particularly in Roma projects where collection of official statistical data according to the nationality is not permitted. The process of reformulation of indicators would require an in-depth insight into each project. That is why the ACU has prepared a technical assistance project proposal on indicators' (re)formulation to be financed from Phare 2003 Unallocated Institution Building Facility (Steering Committee's recommendation is needed).

The ACU delivered training on Phare monitoring with a special focus on MR compilation. The training on monitoring is to be organised regularly by the ACU before each MR cut-off date in order to guarantee accountable Phare monitoring function.

The SMSC is encouraged to consider the inclusion of the Civil Society Sector into the ECOSOC SMSC as an independent sectoral component or as a part of Social Affairs and Human Resources Development sectoral component. This would enable to reduce the number of SMSCs to three comparable in size (possible measure for adoption by the SMSC included in part 4.1).

### SK0013 ACCESS

ACCESS supported initiatives and strengthened the operational capacity of non-governmental and non-profit organisations (NGOs/NPOs) through co-financing grants for projects of relevance to acquis implementation and to certain social need priorities.

The total allocation for grants in Slovakia of € 900 000 was successfully contracted and divided between micro-projects and projects under the Networking Facility. 18 organisations did not receive the whole amount of the final payment because of some ineligible expenses. The total amount of unspent funds represents € 8 419 and is subject for return to the European Commission.

Monitoring of performed activities at the level of grant recipients was carried out by the CSDF as the last project activity. The monitoring and final reports delivered by grantees have shown that there are promising prospects for sustainability of the activities performed by NGOs after the end of Phare intervention.

SK0002 Improvement of the Situation of the Roma in the SR

The aim of this project was to strengthen the position of the Roma national minority and to create conditions for better integration of the Roma into the society while maintaining their ethnic identity.

Some € 96 000 out of € 309 000 of co-financing allocation remains to be spent during the year 2004.

The project focused on increasing mutual tolerance between the local Roma and non-Roma communities through the training of field-workers and local Roma and non-Roma leaders and establishment and running of 10 community centres in locations with high concentration of Roma.

Facilitating the entry of young Romas into the labour market consisting of reinforcing the professional capacity of trainers/counsellors active in the labour field; providing integrated counselling, training and apprenticeship opportunities for young, unqualified, Roma secondary school dropouts aged between 15 and 18 years; offering a module-based program to unemployed Roma between 18 and 26 years old; and implementing pilot training and transfer of professional experience in incubators.

The third part of the project deals with increasing the level of education at various types of schools. This includes reinforcing pre-school education for children, involving mothers into the education process; fostering elementary education by establishing preparatory classes and utilizing intensive whole-day care and alternative education methods; offering vocational training to youngsters who left school without completing the compulsory 10 year school attendance; and strengthening the capacity of universities to support the university education of Roma teachers, assistants and teachers for schools with a high share of Roma students.

Besides the technical assistance supporting the schools in the implementation of the alternative educational forms, supplies of teaching devices, IT equipment and furnishing has been provided to institutions involved, in order to create appropriate conditions for teaching and learning.

The project was delayed that caused that execution of many activities was cumulated at the end of its implementation. Now the main attention should be paid to the sustainability of its outcomes. The cut-off date of the monitoring report does not enable to fully cover this issue. A debriefing meeting on interim evaluation recommendations will be organised in this respect early 2004. Approved recommendations should be appropriately fulfilled and closely followed up.

SR0103.01 Support to the Roma Minority in the Educational Field

The project is directly related to the series of Phare projects. Its purpose is to improve the educational standard of the Roma national minority, and support tolerance and integration to the society.

The main focus of the project is on:

- Reintegration of children from special schools into standard primary schools via reviewing the test batteries used for placement of children to schools.

- Equipment and implementation of the modules that involve parents into education of children, full time day-care, assistant teachers, etc.

- Establishment and operation of 10 community centers.

The institutions involved will be provided with necessary school equipment as well, to facilitate the change of education to the required level.

SR0103.02 Infrastructure for Roma Settlements

The project focuses on the priority region of Slovakia – east, where the concentration of the Roma inhabitants is the highest. The aim of the project is to raise the living standards of the Roma by taking the basic, up till now missing infrastructure to the settlements (e.g. drinking water supply, sewage systems and road communications) and thus create better conditions for the integration of the Roma into the society. Alongside the infrastructure building, community work will be carried out as well.

Serious delay in project implementation (unsettled land ownership in the Roma municipalities and missing building permits, insufficient administrative capacity of the RDSA) resulted in extension of contracting and disbursement periods by one year. The prepared tender documentation for subproject 2 and 3 needed several corrections following the requirements of the ECD due to its poor quality and the non-respect of PRAG rules. This further delayed the project implementation. It is inevitable that the RDSA submits all the necessary documents to the ECD in July at the latest allowing to launch of tenders in August 2004. In case of unsuccessful tenders there will be no time left to relaunch the tenders (detailed contracting schedule for individual activities provided in Annex 4). In case of two villages (Letanovce and Svinia) the conditions for infrastructure construction were not met (building permits not issued). The project co-ordinators (DPC with RDSA) should consider a proposal for funds reallocation to other Roma settlements already prepared for infrastructure construction.

Funds for subsequent Social Housing are available in 2004 State Budget.

2002/000.610.03 Further integration of Roma children in the educational field and improved living conditions

The overall objectives of the project are the continuing improvement of the educational standard of the Roma population and the improvement of the living conditions of socially disadvantaged Roma groups of inhabitants.

The main goals of the project are:

Successful implementation of the integrated system of educating the Roma, through establishing classes in specialized primary schools where students will receive education that will adequately prepare them for continuing education at standard primary schools. This will also enable Roma children to attend a standard primary school in the place of their residence. In addition, the schools will be provided with necessary school equipment (including teaching aids and furnishing) with the purpose of raising the tuition quality.

Technical assistance to municipalities in their preparation for infrastructure projects (water distribution, sewage systems, wastewater treatment plants, roads, pavements and electricity wiring) aimed at improving the living conditions of socially disadvantaged groups of Roma inhabitants. This will consist of preparation of technical documentation, notably the preparation of technical documentation required under Slovak Regulations (e.g. building permits, land use certificates, Environmental Impact Assessments) and a full set of tender documentation for public works.

2003-004-995-01-05 Support to Integration of Roma in Education

The project purposes are to support and ease the passage from primary to secondary education for Roma children coming from disadvantaged environment; implement the multicultural education at secondary schools; prepare pupils for entering the labour and business environment.

The project is in the phase of tender documentation preparation. The Ministry of Education addresses the regional administrative educational structures in order to select primary and secondary schools for an involvement to the project. The actual project implementation should cover the second half of 2004 and the 2004/2005 school year.

# 2003-004-995-01-06 Improved Access to Health Care for Roma Minority in the SR

# The project purposes are to improve the access of Roma in targeted regions to health care and to enhance their knowledge and consciousness about healthy lifestyle.

# Ministry of Health is selecting the suitable settlements (villages) with public buildings for the health centres and for the deployment of mobile medical units (terrain ambulance cars).

# Glossary of Acronyms

# Acronym			Description

ACU				Aid Co-ordination Unit

CIV				Civil Society

CFCU				Central Finance and Contracting Unit

CSDF				Civil Society Development Foundation

DPC				Department of Project Co-ordination

ECOSOC			Economic and Social Cohesion

FM				Financing Memorandum

FWC				Framework Contract

ECD				Delegation of the European Commission in the Slovak Republic

IA				Implementing Agency

IE				Interim Evaluation

JHA				Justice and Home Affairs

M				Monitoring

MCRD				Ministry of Construction and Regional Development of the SR

ME				Ministry of Education of the SR

MLSAF			Ministry of Labour, Social Affairs and Family of the SR

MR				Monitoring Report

NA				Not Applicable

NAC				National Aid Co-ordinator

NAO				National Authorising Officer

NF				National Fund

NGO				Nongovernmental Organisation

NLO				National Labour Office

No				Number

NP				National Programme

NPO				Non-Profit Organisation

PAA				Pre-accession Advisor

PAO				Programme Authorising Officer

PF				Project Fiche

Phare				Poland and Hungary Assistance for Restructuring of their Economies

PIU				Programme Implementing Unit

PP				Plenipotentiary for Roma Communities

Q				Quarter

RDSA				Regional Development Support Agency

SAC				Sectoral Aid Co-ordinator

SFK				Administration of Financial Control (Správa finančnej kontroly)

SHMR				Section of Human Rights and Minorities

SK				Slovak currency (koruna)

SMSC				Sectoral Monitoring Subcommittee

SPI				State Pedagogical Institute

SPO				Senior Programme Officer

SR				Slovak Republic

TD				Tender Dossier

ToR				Terms of Reference

VAT				Value Added Tax

WWTP				Waste Water Treatment Plant

# 1. PROJECT BASIC DATA

## 1.1 Financial Data in €

Financing Memorandum

| FM Title | FM signature date | Phare allocation | Phare actual contracted | Phare actual disbursed | Co-financing allocation | Co-financing actual contracted | Co-financing actual disbursed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2000 Slovakia National Programme | 21.12.2002 | 3 800 000 | 3 655 232 | 3 386 476 | 309 000 | 212 636 | 212 636 |
| Special Programme for strengthening the Civil Society and preparing for accession of the ten candidate countries | 21.12.2000 | 900 000 | 900 000 | 884 760 | - | - | - |
| 2001 Slovakia National Programme | 17.01.2002 | 10 000 000 | 1 818 194 | 489 801 | 9 075 000 | 85 000 | 0 |
| 2002 Slovakia National Programme | 10.01.2003 | 1 000 000 | 0 | 0 | 50 000 | 0 | 0 |
| 2003 Slovakia National Programme | 03.11.2003 | 2 250 000 | 0 | 0 | 570 000 | 0 | 0 |

SMSC/ Sectoral Component

| SMSC Title | Phare allocation | Phare actual contracted | Phare actual disbursed | Co-financing allocation | Co-financing actual contracted | Co-financing actual disbursed |
| --- | --- | --- | --- | --- | --- | --- |
| Civil Society/ Political Criteria and Minorities | 17 950 000 | 6 373 426 | 4 761 037 | 10 004 000 | 297 636 | 212 636 |

Projects

| Project Code | Project Title | Full contracting planned (date) | Current full contracting estimated (date) | Full contracting actual (date) | Contracting deadline | Disbursement deadline |
| --- | --- | --- | --- | --- | --- | --- |
| SK0013 | ACCESS | 30.11.2002 | - | 30.11.2002 | 30.11.2002 | 30.11.2003 |
| SK0002 | Improvement of the Situation of the Roma in the SR | 30.06.2001 | - | 31.12.2002 | 31.12.2002 | 31.12.2003 |
| SR0103.01 | Support to the Roma Minority in the Educational Field | 30.06.2002 | - | November 2003 | 30.11.2003 | 30.11.2004 |
| SR0103.02 | Infrastructure for Roma Settlements | III. Q 2002 | November 2004 | - | 30.11.2004 | 30.11.2005 |
| 2002/000.610.03 | Further integration of Roma children in the educational field and improved living conditions | III. Q 2003 | I. Q 2004 | - | 30.11.2004 | 30.11.2005 |
| 2003-004-995-01-05 | Support to integration of Roma in Education | III. Q 2004 | III. Q 2004 | - | 30.11.2005 | 30.11.2006 |
| 2003-004-995-01-06 | Improved Access to Health Care for Roma Minority in the SR | III. Q 2004 | III. Q 2004 | - | 30.11.2005 | 30.11.2006 |

| Project Code | Phare allocation | Phare actual contracting | % | Phare actual disbursed | % | Co-financing allocation | Co-financing actual contracting | % | Co-financing actual disbursed | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SK0013 | 900 000 | 900 000 | 100 | 884 760 | 98.3 | - | - | - | - | - |
| SK0002 | 3 800 000 | 3 655 232 | 96.2 | 3 386 476 | 89.1 | 309 000 | 212 636 | 68.8 | 212 636 | 68.8 |
| SR0103.01 | 1 700 000 | 1 633 234 | 96.1 | 309 820 | 18.2 | 675 000 | 85 000 | 12.6 | 0 | 0 |
| SR0103.02 | 8 300 000 | 184 960 | 2.2 | 179 981 | 2.2 | 8 400 000 | 0 | 0 | 0 | 0 |
| 2002/000.610.03 | 1 000 000 | 0 | 0 | 0 | 0 | 50 000 | 0 | 0 | 0 | 0 |
| 2003-004-995-01-05 | 1 000 000 | 0 | 0 | 0 | 0 | 110 000 | 0 | 0 | 0 | 0 |
| 2003-004-995-01-06 | 1 250 000 | 0 | 0 | 0 | 0 | 460 000 | 0 | 0 | 0 | 0 |

## 1.2 Risks, Assumptions and Conditions

| Project Code | Risks | Follow-up |
| --- | --- | --- |
| SK0013 | The weak institutional and professional capacity of the NGO/NPO to develop and implement projects satisfactorily, availability of co-financing | Consultancies were provided prior to individual Calls for Proposals by the CSDF staff. Number of submitted projects (over 200 in total) exceeded expectations, despite the lack of co-financing from the state budget; NGOs were able to guarantee 10% co-financing contribution. All supported projects were monitored and proved that the NGO as final beneficiaries of Phare assistance are able to deal with the risks well. |
|  | The absence of a real partnership between NGOs/NPOs involved in a project | Awarded projects included component of the partnerships among NGOs and relevant partner institutions on either NGO, local government level. |
|  | NGOs/NPOs with fraudulent objectives; misappropriation of grants | No misappropriation of funds recognised; ineligible expenses were not reimbursed to the beneficiaries. |
|  | Management capacity of implementing bodies | CSDF completed its reform, adjusted financial management and recording to PRAG rules, simplified bank operation to EUR, clarified inaccuracies in reporting. CSDF was audited by the EC, Slovak authorities and SFK at the MF SR. In December 2003 CSDF won the public competition for the Slovak foreign development aid and became an ACU for the Bratislava Belgrade Fund with a total allocation of SK 55 million for 2004. |
| 2003-004-995-01-06 | The sum planned in the programming phase for the renovation of health centres could be insufficient after selection of suitable locations for health centres | NA to the cut-off date. |

| Project Code | Assumptions | Follow-up |
| --- | --- | --- |
| SK0002 | Involvement of governmental and local authorities | Governmental and local authorities directly participating in the project implementation. |
|  | Ongoing public administration reform | Public Administration Reform is being implemented. |
|  | Increased support from state budget | Budget increased via various programmes related to the Basic Theses of the Slovak Government policies of the integration of Roma communities. Data from Office of Plenipotentiary for Roma Communities show the following rise in funds (in mil. SK): 1999 (14.6); 2000 (29.3); 2001 (30.1); 2002 (47.6). |
|  | Effective co-operation among all involved implementing authorities and beneficiaries of Phare assistance and their full involvement in the implementation process | All parties involved in the project were cooperating on daily basis. There were problems with effective communication with the PAA and beneficiaries of the project witch were not solved during the project implementation. |
|  | Common strengths of Ministry of Education, Ministry of Labour, Social Affairs and Family, National Labour Office and NGOs to implement National Strategy for Minorities | The relevant ministries were involved in elaboration of concrete steps of the Strategy. |
|  | Sufficient financial resources available from the National Labour Office budget and on community level | The resources are available via Publicly Beneficial Works Funds. |
|  | The Roma community is interested in education | In the communities affected by the project a rise of interest in education and participation in the project and everyday life of the villages was noted. |
|  | Effective communication and co-operation between Roma parents and school administrators | In the communities affected by the project a rise of interest in education was noted, especially of parents sending their children to schools thanks to involvement of the assistant teachers. |
|  | State budget available for implementation of national strategy | The Office Plenipotentiary's budget is not sufficient for national strategy implementation. Line ministries have allocated own resources for Roma issues but the Office does not have an overall view of these resources for 2004 to the cut-off date. Office of Plenipotentiary's budget covers mainly urgent matters such as emergency cases in Roma communities (floods, fire, landslide). In 2004 almost half of the budget is allocated for consolidation of the Central Office and establishment of the Regional Offices. |
|  | Strong commitment of teachers | In the communities affected by the project, teachers are committed to improve the educational level of Roma. |
| SR0103.01 | Roma community increased interest in education | In the communities affected by the project a rise of interest in education was noted. |
|  | Ongoing improvement of the living conditions of the Roma minority | Phare and State Budget financing available for the purpose of improvement of living conditions. Steps for allocating further funding in both the State Budget and within Structural Funds were made. |
|  | Increased focus of NGO sector in this field | NGOs expressing interest in project implementation and cooperating on the implementation. |
|  | Rising awareness about possibilities offered by new educational system | Ministry of Education and Slovak Government Office provide space in their Internet web sites for publication of information. Conferences and seminars on the project outputs are organised. Articles in specialised papers are being published. |
|  | Effective communication and co-operation between Roma parents and school administrators | Ongoing in those localities that are part of the project. |
|  | Support from local authorities and self-government | Local authorities and self-governments are actively participating in the activities. |
| SR0103.02 | Implementation of the Educational programme for Roma minority | Educational programmes ongoing. |
|  | Active employment measures implemented by National Labour Office | The National Labour Office will be restructured as of 1 January 2004 with a greater focus on active employment measures. |
|  | The social housing programme ongoing and sufficient funds allocated | Funds are available by means of 2004 State Budget. |
|  | Tolerance developing programmes ongoing | Programmes implemented. |
|  | Municipalities actively participating in Public Beneficial Works | Municipalities employing people. |
|  | Roma population involved in the works | NA to the cut-off date. |
| 2002/000.610.03 | Effective cooperation of stakeholders | Stakeholders are cooperating at tender documentation preparation but it is already delayed. |
|  | Strong commitment of teachers, pedagogues, psychologists and scientists concerned | NA to the cut-off date. |
|  | Information for possibilities for financing infrastructure construction available | Funds will be available mainly through the Structural Funds. |
|  | Intensive involvement of Roma parents in the process of education | NA to the cut-off date. |
|  | Roma community interested in education | NA to the cut-off date. |
| 2003-004-995-01-05 | Strong commitment of teachers and Roma education experts | NA to the cut-off date. |
|  | Roma community interested in education | NA to the cut-off date. |
|  | Intensive promotion of the possibilities in education | NA to the cut-off date. |
|  | Support from school administrations and self-government | NA to the cut-off date. |
|  | Involvement of Roma parents in their children’s education | NA to the cut-off date. |
|  | Cooperation with the private sector | NA to the cut-off date. |
| 2003-004-995-01-06 | Selection of ten appropriate settlements (villages) with public building suitable for reconstruction to become health centre in the first phase of the project. Additionally, it is necessary to define ten settlements in charge of the mobile medical unit deployment | Ministry of Health is selecting the suitable settlements. |
|  | Facilities and services developed under the project will be used as planned | NA to the cut-off date. |
|  | Staff can be retained in positions for which they were trained | NA to the cut-off date. |
|  | Continued positive response to the project activities | NA to the cut-off date. |
|  | Positive response of the target communities to the project | NA to the cut-off date. |
|  | Positive response of the local communities to the project | NA to the cut-off date. |
|  | Funding of medical services by insurers available when needed | NA to the cut-off date. |

| Project Code | Conditions | Follow-up |
| --- | --- | --- |
| SK0002 | Adequate human resources will be made available by the involved institutions | Administrative capacities of the DPC were strengthened. |
|  | Active Roma community involvement in the relevant municipalities | Romas were directly involved in project implementation. |
|  | Legislation coming into validity (by September 2002 the Ministry of Education will enlist the position of Assistant Teachers among the pedagogical personnel of the schools and enlist them in the necessary legislation, including their job description. The former pilot projects “Mother and Child kindergartens and Preparatory classes in the primary schools” will be also included into the national curriculum by September 2002) | The position of Assistant Teacher introduced in the legislation (for more details see part 3 Conclusions). |
| SR0103.01 | Active Roma community involvement in the relevant municipalities | Romas are directly involved in project implementation. |
|  | Legislation coming into validity | The position of Assistant Teacher introduced in the legislation. Legislation on experimental classes valid. |
| SR0103.02 | Slovak Land Fund assisting in the legislation of land ownership | Yes |
|  | Before launching the project the approval of mayors backed by the statement of the municipality councils must be issued, the approval will include the following information: the municipality will actively participate in the project implementation; the municipality will agree with the supportive community work in the Roma settlement; approval of Roma participation via Public Beneficial Works; cadastre printout – ensuring the legality of land | There are ongoing problems with Letanovce and Svinia settlements (new municipality councils disagree with the agreed proposals of assistance – in Letanovce after negotiations the proposal agreed upon, land ownership not clarified, in Svinia the Municipality council disagree with the project implementation). See part 4.1 for a proposed corrective action. |
| 2002/000.610.03 | The Slovak Government will support programmes for integration of the Roma minority into the Slovak society | Approved Basic Theses of the Slovak Government policies of the integration of Roma communities. |
|  | Adequate human resources will be made available by the involved institutions | Administrative capacities at DPC available. |
| 2003-004-995-01-05 | Cofinancing timely available | Co-financing available through State Budget. Beneficiary in cooperation with the National Fund and CFCU should prepare a co-financing contracting and disbursement time-schedule (see part 4.1 for a proposed corrective action.). |
|  | Good co-operation and intensive involvement of municipalities | NA to the cut-off date. |
| 2003-004-995-01-06 | National co-financing of 50% of the salaries for the field workers available by the time of signature of the relevant service contract at the latest | Beneficiary in cooperation with the National Fund and CFCU should prepare a co-financing contracting and disbursement time-schedule (see recommendation in part 4.1 for more details). |

## 1.3 Administrative Changes

| Project Code | Where (PIU, IA, ECD, ACU…) | Description and Consequences |
| --- | --- | --- |
| SK0013 | CSDF | The number of CSDF employees is gradually decreasing due to the fact that the Foundation, with the completion of the 2000 Phare project implementation, will be phased out. Currently 3 full-timers and 3 part-timers are working for the Foundation. CSDF as an ACU for Bratislava Belgrade Fund will have 4 employees in 2004 and 2005. |
| 2002/000.610.03 | DPC | Mr M. Hojsík (responsible for SK0002 project) replaced in December 2003 by Ms L. Hencelová who took responsibility for 2002/000.610.03 project. |
| SK0002 SR0103.01 2002/000.610.03 2003-004-995-01-05 2003-004-995-01-06 | CFCU | Ms Galabová has become a CFCU programme manager for Roma projects. |
| 2003-004-995-01-05 | Ministry of Education | Number of Phare Implementation Unit staff decreased by one employee. Current number of employee (3) should be sufficient for implementation of Phare projects administered by the Ministry of Education. |

# 2. MONITORING DATA

## 2.1 Monitoring of Contracts and Deviations

| Contract Code | Current Activity of the Contract | Contracting planned (date) | Contracting actual (date) | Phare Allocation in € | Contracting actual Phare % of allocation | Contracting Actual Phare in € | Disbursement actual Phare % of allocation | Disbursement actual Phare in € |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SK0013 ACCESS |
| Grant Scheme Call for Proposal 1 Grant Scheme Call for Proposal 2 | Implementation of 60 supported projects + their monitoring | 28.02.2002 30.08.2002 | June 2002 30.11.2002 | 900 000 | 100 | 900 000 | 98.3 | 884 760 |
| SK0002 Improvement of the Situation of the Roma in the SR |
| SK0002.01.01.0005 Better conditions for Roma self-realization in the education system | Completed | 30.06.2001 | 31.12.2002 | 950 000 | 100 | 949 580 | 100 | 949 580 |
| SK0002.01.01.0006 Improved conditions for mutual tolerance between Roma and non-Roma inhabitants of municipalities | Completed | 30.06.2001 | 31.12.2002 | 690 000 | 93.7 | 646 767 | 93.7 | 646 767 |
| SK0002.01.01.0007 Improved conditions for young Roma people to enter the labour market | Completed | 30.06.2001 | 31.12.2002 | 620 000 | 91.4 | 566 544 | 80.3 | 497 553 |
| SK0002.01.01.0008 – 0009 – 00010 – 00011 Equipment for Community Centres, Schools and regional Training Centres | Completed | 30.06.2001 | 31.12.2002 | 990 000 | 94.9 | 939 846 | 85.4 | 845 861 |
| SK0002/SK00/IB-OT-01 – Twinning programme | Completed | 30.06.2001 | 28.12.2001 | 550 000 | 100 | 550 000 | 80.8 | 444 219 |
| SR0103.01 Support to the Roma Minority in the Educational Field |
| Framework Contract AMS/451 Lot No. 8 – Reintegration of socially disadvantaged children from special schools into the standard primary schools | Implementation – test batteries are being prepared and verified | 30.06.2001 | 19.12.2002 | 199 999 | 94.5 | 189 000 | 80 | 151 200 |
| International Open Tender - Equipment for schools and Community Centres | Implementation | November 2003 | 30.11.2003 | 1 170 000 | 95.3 | 1 114 572 | 0.1 | 1 537 |
| Restricted International Service Tender | Implementation – establishment of CC and activities in communities | September 2003 | 10.09.2003 | 330 000 | 99.9 | 329 661 | 47.6 | 157 084 |
| 2002/000.610.03 Further integration of Roma children in the educational field and improved living conditions |
| Component 1: Restricted International Service Tender: Reintegration of children from socially disadvantaged environment form special schools into regular primary schools | Preparation of ToR | November 2003 | - | 300 000 | 0 | 0 | 0 | 0 |
| Component 2: Service Order (Framework Contract): Identification of municipalities to receive support and reviewing existing technical documentation | Preparation of ToR | November 2003 | - | 100 000 | 0 | 0 | 0 | 0 |
| Component 3: Restricted International Service Tender: Preparation of technical documentation for municipalities with high share of socially disadvantaged groups of inhabitants | Preparation of ToR | November 2003 | - | 550 000 | 0 | 0 | 0 | 0 |
| Component 4: Local Open Tender: Supply for schools | Preparation of Technical Specification | November 2003 | - | 50 000 | 0 | 0 | 0 | 0 |
| 2003-004-995-01-05 Support to Integration of Roma in Education |
| International Restricted Service Tender - Technical Assistance | Preparation of ToR | II. Q 2004 | - | 890 000 | 0 | 0 | 0 | 0 |
| International Open Supply Tender - Equipment | Preparation of Technical Specifications | III. Q 2004 | - | 110 000 | 0 | 0 | 0 | 0 |
| 2003-004-995-01-06 Improved Access to Health Care for Roma Minority in the SR |
| Local Open Tender – Supply (educational tools and medical equipment for health centres) | Selection of suitable localities for Health Centres | III. Q 2004 | - | 95 000 | 0 | 0 | 0 | 0 |
| International Open Tender – Supply (Supply of Mobile Medical Units) |  | III. Q 2004 | - | 450 000 | 0 | 0 | 0 | 0 |
| Framework Contract – Service (Training) |  | III. Q 2004 | - | 40 000 | 0 | 0 | 0 | 0 |
| International Restricted Tender – Service (30 field workers, 2 co-ordinators, 1 project leader and 1 assistant) |  | III. Q 2004 | - | 590 000 | 0 | 0 | 0 | 0 |
| Local Open Tender – Works (Renovation of rooms for health centres) |  | III. Q 2004 | - | 75 000 | 0 | 0 | 0 | 0 |

| Project Code | Contracting planned (date) | Contracting actual (date) | Phare allocation in € | Contracting actual Phare % of allocation | Contracting actual Phare in € | Disbursement actual Phare % of allocation | Disbursement actual Phare in € | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SR0103.02 Infrastructure for Roma Settlements |
| Activity 1 – Co-ordination of implementation | November 2003 | - | 470 000 | 0 | 0 | 0 | 0 | The Terms of Reference on Co-ordination of implementation submitted by the DPC on 30.12.2003 and subsequently to be delivered to the ECD for approval (January 2004). |
| Activity 2 – Preparation of Technical Documentation | November 2003 | - | 930 000 | 19.9 | 184 960 | 19.4 | 179 981 | For the first group of municipalities (11) tender documentation elaborated. For the second group of municipalities (19) 9 tenders launched. Tender Openings and Evaluations (Activity 2 – Preparation of technical documentation and TD) took place on 3 – 4 December 2003. Evaluation Reports for the municipalities Slavošovce and Ostrovany, Brzotín, Trenč and Belina, Rakúsy and Veľká Lomnica approved by the ECD. The Evaluation Reports for the rest of municipalities from the second group of municipalities to be submitted to ECD for approval in January 2004. |
| Activity 3 – Construction Works | November 2003 | - | 6 900 000 | 0 | 0 | 0 | 0 | Works Procurement Notice for the municipalities Huncovce, Pečovská Nová Ves, Stráne pod Tatrami, Klenovec and Varhaňovce (tender for the construction of electricity) and Slavošovce to be published in January 2004. Evaluation Report for the Municipality Arnutovce to be approved by the ECD in January 2004 and subsequently contract dossier will be prepared. Evaluation Report for the Municipalities Drahňov and Varhaňovce to be submitted to ECD for approval in January 2004. Contracts for the Municipalities Soľ, Ďurkov, Šumiac, Klenovec and for the Association of Municipalities VIRO to be signed in January 2004. |

| Project Code/ Contract Code | Deviation in the substance of the project/ contract/ activity (including delays) | Consequences/ Corrective Actions |
| --- | --- | --- |
| SK0002 | Originally planned incubators were not functional at the time of implementation. Contractor requested extension of period for equipment delivery The list of schools needed to be adjusted to the current situation in project implementation. | The list of incubator was adjusted to the current development in project implementation (number of incubators increased). Time schedule for equipment delivery was prolonged. Several schools were replaced in the original list. |
| SK0002 | Contracting and disbursement of co-financing delayed. | Some € 96 000 out of € 309 000 of co-financing allocation remains to be spent during the year 2004. |
| SR0103.01 | Framework contract prolonged. ToRs and TS delayed due to lack of administrative capacities at the DPC and due to the time needed for ensuring the VAT of co-financing. Equipment contracts were prolonged with EURO Financ (by 29 March), TECTON (by 27 February) and PERGAMON (by 27 February). | The implementation of FWC prolonged till February 2004 because of the changes in personnel requested by the contractor. Period of execution of TA for Community Centers shortened. VAT secured, budget of co-financing raised. Reasons for prolongation are as follows: EURO Financ (producers and importers were occupied by supply to the retail); TECTON (most of the distributors, transporters and other stakeholders are closed at the end of the year); PERGAMON (too many public holidays during the 60-day delivery period). |
| SR0103.02 | Substantial delays in project contracting due to the unsettled land ownership and missing building permits. | Contracting and disbursement periods extended by one year. This should lead to project implementation in those villages (settlements) with building permits. See Annex 4 for a detailed contracting schedule. |
| 2000 – 2002 CIV projects | Due to the holiday season and undeveloped internal procedures on substitutability within the administration of some implementing stakeholders the debriefing meeting for a CIV Interim Evaluation Report failed to be organised within the one-month period after the issue of the report as required by the IE Guide. | This could cause that some of the recommendations will be no longer relevant. All implementing authorities should develop internal procedures on substitutability in order to prevent repetition of such a situation. |

## 2.2 Achievement of Objectives

| Project Code | Indicator Level | Description | Unit | Target Value | Target Date | Actual Value | Accomplished in % | Remarks/ Follow-up |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SK0013 ACCESS |
| SK0013 | Overall Objective | To promote the implementation of the acquis communautaire in policy areas in which the third sector plays an important implementation and advocacy role, and to raise popular awareness and acceptance in these areas | - | - | - | - | - | Activities carried out by individual projects indicate real fulfilment of tasks related to the policy impact (proclamations, statement, legislation drafts as planned in individual projects), strengthening the inclusion of the individual groups in the transformation process. Individual projects’ outputs and results (publications, trainings, engagement and participation of the target groups in acquis related process at local level) demonstrated that the NGOs developed precise and targeted methods of continual raise of their operational capacity. As one of the examples can serve the REC publication Common European indicators for the sustainable development of cities (environment protection) and the Manual on social services produced by S.P.A.C.E. in the field of social services. |
| SK0013 | Overall Objective | To encourage the inclusion and participation of individuals and groups who risk being economically, socially or politically marginalized in the transformation process | - | - | - | - | - |  |
| SK0013 | Immediate Objective | To alleviate specific problems in the areas of environmental protection and socio-economic development and the reduction of marginalisation | - | - | - | - | - |  |
| SK0013 | Immediate Objective | To strengthen the institutional and operational capacity of NGOs/ NPOs | - | - | - | - | - |  |
| SK0013 | Immediate Objective | To involve the NGOs/ NPOs of the candidate countries in the activities of the European-wide NGO/ NPOs platforms and networks | - | - | - | - | - |  |
| SK0013 | Result | Involvement of civil society institutions measured by number of beneficiaries | Number | - | 31.12.2002 | 60 | - | Indicator was additionally formulated by the CSDF. Target value not indicated in programming document |
| SK0002 Improvement of the Situation of the Roma in the SR |
| SK0002 | Overall Objective | Increased participation of Roma in the self-government (by 10% in 2006 compared to 2002) | % | 10 | 31.12.2006 | - | - | The annual statistical data on participation of children at schools in 2003 are not available to the cut-off date as a matter of time. However, the measurability will be debased by the fact that nationality is recorded according to the self-identification with Roma nationality that is very low in this community. |
| SK0002 | Overall Objective | Increased participation of Roma in the education system (by 15% in 2003 compared to 2001) | % | 15 | 31.12.2003 | - | - |  |
| SK0002 | Immediate Objective | Increased number of Roma graduates at all level of education (by 10% in 2003 compared to 2001) | % | 10 | 31.12.2003 | - | - |  |
| SK0002 | Overall Objective | Increased public funds available for Roma minority projects (by 15% in 2003 compared to 2001) | % | 15 | 31.12.2003 | - | - | Figures for 2003 not available to the cut-off date. Data from Office of Plenipotentiary for Roma Communities show the following rise in funds (in mil. SK): 1999 (14.6); 2000 (29.3); 2001 (30.1); 2002 (47.6). |
| SK0002 | Immediate Objective | Increased number of Roma finding permanent job | % | 10 | 31.12.2003 | - | - | Incubators employing trained Romas for a period between half and two years. Nine of them committed themselves for future employment of some 45 trained Romas for up to two years. |
| SK0002 | Result | Increased number of field-workers in Roma settlements (by 30 in 2003) | Number of workers | 30 | 31.12.2003 | 30 | 100 | - |
| SK0002 | Result | Increased number of Roma participating in local planning in the selected municipalities (by 20% in 2003 compared to 2001) | % | 20 | 31.12.2003 | 30 | 150 | Educated guess made by contractors based on information from mayors. |
| SK0002 | Result | 4 relevant training modules developed, verified and implemented | Number of trainings | 4 | 31.12.2003 | 4 | 100 | - |
| SK0002 | Result | Training seminars for staff providing special training delivered (30 trainers trained) | Number of trainers | 30 | 31.12.2003 | 30 | 100 | - |
| SK0002 | Result | Number of Roma receiving integrated counselling, training and work experience increased by 1000 | Number of Roma | 1000 | 31.12.2003 | 1230 | 123 | - |
| SK0002 | Result | Increased number of Roma children attending preschool institutions (kindergartens) (by 15% in 2003 compared to 2001) | % | 15 | 31.12.2003 | - | - | The annual statistical data on participation of children at schools in 2003 are not available to the cut-off date as a matter of time. However, the measurability will be debased by the fact that nationality is recorded according to the self-identification with Roma nationality that is very low in this community. |
| SK0002 | Result | Decreased number of Roma children attending elementary schools for handicapped children (by 10% in 2003 compared to 2001) | % | 10 | 31.12.2003 | - | - |  |
| SK0002 | Result | Increased number of Roma attending secondary schools (by 10% in 2003 compared to 2001) | % | 10 | 31.12.2003 | - | - |  |
| SR0103.01 Support to the Roma Minority in the Educational Field |
| SR0103.01 | Overall Objective | Increased participation of Roma in the education system (by 10% in 2004 compared to 2002) | % | 10 | 31.12.2004 | - | - | NA to the cut-off date |
| SR0103.01 | Immediate Objectives | Increased number of Roma graduates at all levels of education (by 10% in 2004 compared to 2002) | % | 10 | 31.12.2004 | - | - | NA to the cut-off date |
| SR0103.01 | Immediate Objective | Increased number of Roma community members participating in the education system (by 30% in 2004 compared to 2002) | % | 30 | 31.12.2004 | - | - | NA to the cut-off date |
| SR0103.01 | Result | By the end of 2004, 50 additional kindergartens operating the “mother and child” module | Number | 50 | 31.12.2004 | - | - | NA to the cut-off date |
| SR0103.01 | Result | Strengthened whole-day care system at 70 additional schools | Number | 70 | 31.12.2004 | - | - | NA to the cut-off date |
| SR0103.01 | Result | 40 twins schools focusing at reintegration of Roma children to the regular education system | Number | 40 | 31.12.2004 | - | - | NA to the cut-off date |
| SR0103.01 | Result | Establishment and operating further 10 community centres | Number | 10 | 31.12.2004 | - | - | NA to the cut-off date |
| SR0103.02 Infrastructure for Roma Settlements |
| SR0103.02 | Overall Objective | Rate of Roma living in shacks without basic infrastructure reduced | - | - | - | - | - | NA to the cut-off date |
| SR0103.02 | Overall Objectives | Rate of deceases caused by bad hygienic conditions reduced | - | - | - | - | - | NA to the cut-off date |
| SR0103.02 | Overall Objective | Number of permanently employed Roma increased | - | - | - | - | - | Project can offer only interim employment for unqualified labour force which could be considered just as an assumption for possible later permanent employment elsewhere. |
| SR0103.02 | Immediate Objective | Utilities (water, transport, electricity) for up to 52.000 citizens in the 30 selected municipalities in line with EU standards | Number | 52 000 | 30.11.2004 | - | - | NA to the cut-off date |
| SR0103.02 | Immediate Objective | Living standards for up to 20% of the Roma living in the settlements improved | % | 20 | 30.11.2004 | - | - | NA to the cut-off date |
| SR0103.02 | Immediate Objective | Conditions created for participation of up to 20 municipalities in the Social Housing Programme | Number | 20 | 30.11.2004 | - | - | NA to the cut-off date |
| SR0103.02 | Result | Building permits issued for the 30 municipalities | Number | 30 | March 2003 | 28 | 93.3 | Issue of building permits was considerably delayed due to unsettled land ownership. |
| SR0103.02 | Result | 48.000 m water distribution network operational | Metre | 48 000 | 30.11.2004 |  | - | NA to the cut-off date |
| SR0103.02 | Result | 55.000 m of sewerage operational and connected to WWTPs | Metre | 55 000 | 30.11.2004 | - | - | NA to the cut-off date |
| SR0103.02 | Result | 82.000 m2 roads reconstructed and/ or built | Metre2 | 82 000 | 30.11.2004 | - | - | NA to the cut-off date |
| SR0103.02 | Result | 9.200 m of new mains | Metre | 9 200 | 30.11.2004 | - | - | NA to the cut-off date |
| SR0103.02 | Result | 7.6000 m of new public lightning | Metre | 7 600 | 30.11.2004 | - | - | NA to the cut-off date |
| 2002/000.610.03 Further integration of Roma children in the educational field and improved living conditions |
| 2002/000.610.03 | Overall Objective | Increased participation of Roma in the education system | - | - | - | - | - | NA to the cut-off date |
| 2002/000.610.03 | Overall Objective | Municipality offices using the technical documentation | - | - | - | - | - | NA to the cut-off date |
| 2002/000.610.03 | Immediate Objective | Increased number of Roma studying at standard primary schools | - | - | - | - | - | NA to the cut-off date |
| 2002/000.610.03 | Immediate Objective | Increased number of municipalities using the technical documentation for construction of infrastructure | - | - | - | - | - | NA to the cut-off date |
| 2002/000.610.03 | Result | 20 classes of standard primary schools established at special primary schools | Number of classes | 20 | 30.11.2005 | - | - | NA to the cut-off date |
| 2002/000.610.03 | Result | 30 municipalities having technical documentation regarding infrastructure available | Number of municipalities | 30 | 30.11.2005 | - | - | NA to the cut-off date |
| 2003-004-995-01-05 Support to Integration of Roma in Education |
| 2003-004-995-01-05 | Overall Objective | Increased number of Roma graduates at primary schools | Number | - | - | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Overall Objective | Increased number of Roma graduates at secondary schools | Number | - | - | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Immediate Objective | Tutoring programme for preparation of children for secondary education introduced to schools | Programme | - | - | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Immediate Objective | Multicultural development training programmes approved and becoming integral part of the Slovak secondary education system | Programme | - | - | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Immediate Objective | Training programmes preparing pupils for labour/business environment approved and introduced to secondary schools | Number of classes | - | 30.11.2006 | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Result | Elaborated and approved teaching materials of the tutoring programme | Teaching materials | - | 30.11.2006 | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Result | 160 teachers trained on tutoring | Number of teachers | 160 | 30.11.2006 | 0 | 0 | NA to the cut-off date |
| 2003-004-995-01-05 | Result | Elaborated and approved multicultural methods and teaching materials | Methods and materials | - | 30.11.2006 | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Result | 100 teachers of secondary schools trained on multiculturalism | Number of teachers | 100 | 30.11.2006 | 0 | 0 | NA to the cut-off date |
| 2003-004-995-01-05 | Result | Elaborated and approved teaching materials and methods for courses on labour market/business | Materials and methods | - | 30.11.2006 | - | - | NA to the cut-off date |
| 2003-004-995-01-05 | Result | Teachers of at least 30 secondary schools trained in the business preparation courses | Number | 30 | 30.11.2006 | 0 | 0 | NA to the cut-off date |
| 2003-004-995-01-05 | Result | 30 secondary schools implementing the courses for business preparation | Number | 30 | 30.11.2006 | 0 | 0 | NA to the cut-off date |
| 2003-004-995-01-06 Improved Access to Health Care for Roma Minority in the SR |
| 2003-004-995-01-06 | Overall Objective | Roma life expectancy and mortality rates approach national Slovak averages | % | - | - | - | - | NA to the cut-off date |
| 2003-004-995-01-06 | Immediate Objective | Roma mortality rates approach national Slovak averages | % | - | - | - | - | NA to the cut-off date |
| 2003-004-995-01-06 | Result | 30 trained field workers and 2 co-ordinators working in Roma settlements by II. Q 2004 | Number | 30 + 2 | II. Q 2004 | 0 | 0 | NA to the cut-off date |
| 2003-004-995-01-06 | Result | The co-operation with relevant doctors in selected Roma settlements ensured by II. Q 2004 | - | - | II. Q 2004 | - | - | NA to the cut-off date |
| 2003-004-995-01-06 | Result | The number of outpatient doctor visits per capita increased | Number | - | 30.11.2006 | - | - | NA to the cut-off date |
| 2003-004-995-01-06 | Result | Mobile Medical units and permanent health centres operational | Number | 10 + 10 | 09/2005 | 0 | 0 | NA to the cut-off date |
| 2003-004-995-01-06 | Result | Roma health education is organised at least twice a week in selected localities | Number | 2 | 09/2005 | 0 | 0 | NA to the cut-off date |

## 2.3 Monitoring of Co-financing Costs in € (without VAT)

| Project number | Type of co-financing costs | Contracted | Disbursed | Comments |
| --- | --- | --- | --- | --- |
| SK0002 | Community centres reconstruction | 19 000 | 19 000 | Entire allocation spent |
|  | School reconstructions | 143 636 | 143 636 | Further 96 364 to be spent by the end of 2004 |
|  | Equipment for incubators | 50 000 | 50 000 | Entire allocation spent |
| SR0103.01 | Supply of equipments for community centres and schools | 85 000 | 0 | - |
|  | School refurbishment | 0 | 0 | 330 000 to be contracted in 2004 |
|  | Community centres refurbishment | 0 | 0 | 40 000 to be contracted in 2004 |
|  | Running costs of community centres | 0 | 0 | 220 000 to be contracted in 2004 |
| SR0103.02 | Construction works | 0 | 0 | Joint co-financing (8.4 million) will be contracted and disbursed together with Phare part of tendering. |
| 2002/000.610.03 | Supply of equipment for the 20 classes in specialized primary schools | 0 | 0 | 50 000 to be contracted in 2004 - 2005. |
| 2003-004-995-01-05 | Supply of equipment to 30 schools | 0 | 0 | Co-financing will be available through the State Budget. |
| 2003-004-995-01-06 | Mobile Medical Units | 0 | 0 | Co-financing will be available through the State Budget. |
|  | Field workers – personal costs | 0 | 0 |  |
|  | Roma educational tools | 0 | 0 |  |
|  | Renovation of health centres | 0 | 0 |  |
|  | Medical equipment | 0 | 0 |  |
| SK0013 | NGOs provide the 10% contribution within the budget items and provide support documentation for the real contribution made, mostly in categories of human resources (salaries, benefits), communication expenses, equipment and office supplies. The contribution must be proved as the real payment made or service provided defined as costs sharing made prior to reimbursement from Phare. |

# 3. CONCLUSIONS

Overall Assessment/ Lessons to be learned/ Project Outcomes

SK0013 ACCESS

The project focuses on consolidation of NGOs, support to democratic practices namely in the field of inclusion of marginalized groups. As of 31 November 2003 the CSDF monitored all supported projects (60). All beneficiaries provided final financial and technical reports within the required deadline. CSDF prepared a document with a short description of all supported projects. The document will serve as a basis for an ACCESS 2000 publication describing good practices and lessons learned.

In general, it can be stated that all projects monitored so far were in compliance with the contract. Monitoring results proved that activities within individual projects were carried out by the final beneficiaries according to the schedule. No serious irregularities or problems were observed. The reasons for these observations can be identified in an improvement of the financial flow through the National Fund and stabilized management at the CSDF. Minimal share of contracted amount was not eligible for the final reimbursement.

Activities carried out by individual projects indicate real fulfilment of tasks related to the policy impact (proclamations, statement, legislation drafts as planned in individual projects) by the end of the disbursement date. Moreover, supported activities have very good prospects for sustainability after Phare intervention. CSDF experience and expertise will be utilised in Bratislava Belgrade Fund for which it will fulfil the role of aid co-ordinator.

# SK0002 Improvement of the Situation of the Roma in the SR

Despite having to cope with a shortened implementation period (late contracting) the project objectives were achieved, regarding employment and community work part, more than originally planned (see part 2.2 for objectively measurable indicators).

Respective municipalities will finance Community Centres for three years.

The 2003 State budget reserved SK 27.5 mil. for 232 teacher assistants and 0-classes teachers, actualised in September 2003 to 440 persons (SK 70.7 mil.), that is 219 working persons and 221 reserve work positions. Funds for teacher assistants are available in 2004 State Budget (exact figures not available to the cut-off date).

Donation Agreements between the Ministry of Finance and final beneficiaries regarding equipment were still not signed due to insufficient administrative capacity. The CFCU shall accomplish this duty in the first quarter 2004.

Regarding social field workers, the MLSAF has allocated in their budget for the year 2004 SK 6.6 mil. for 50 social field workers. An edict that shall be approved by the Ministry of Finance legislative commission is being elaborated. The commission will define and approve particular criteria for providing grants for selected communities and establish a special commission, which will select the communities (the Pilot programme of social field workers is not connected with Phare social field workers and it will be financed and covered by the Office of Plenipotentiary).

Regarding legal status of social field workers, Act No 195/98 Coll. on social support concerns only social work and does not govern social fieldwork. That is why the MLSAF is planning to change the existing state and is preparing a law about social legal protection of children and social prevention, in which the social fieldwork will be integrated and the legal status of social field workers would be set down.

30 trained counsellors out of total 32 persons were contracted by the labour offices for at least six months under special conditions as Public Workers from     1 July to 31 December 2003. The issue of future employment conditions for the trained pool was pointed out in the letter to the MLSAF and TA team representatives discussed the issue with the advisor to the minister during the project implementation. Since the NLO will be transformed to a state institution (Central Office of Labour, Social Affairs and Family) as of January 2004, according to the valid employment legislation the Central Office cannot secure the employment of trained pool of 30 Roma assistants without legislation changes. To promote the sustainability of the project the Central Office submitted comments concerning Roma assistant position to the draft of the Catalogue of Job Description in civil service recently developed as a Slovak Government Directive (interministerial commenting ongoing).

The programme in incubators continues after 30.11.2003 directly under supervision of the National Labour Office. Nine out of 34 incubators involved in the project signed the contracts of future cooperation for at least two years when all of them were supplied with technical equipment financed from state budget co-financing as well as NLO co-financing supporting job positions creation and requalification courses. 74 job positions were created for unemployed young Roma people for the period from six months to two years and three requalification courses has been executed for at least 45 candidates.

Satisfaction with twinning part of the project was uneven. To the cut-off date there is no tangible intent to utilise benefits from PAA' performance by Slovak authorities. Therefore one of the IE recommendations (debriefing to be held early 2004) requires to specify this issue.

SR0103.01 Support to the Roma Minority in the Educational Field

The project activities have started. The subproject regarding preparation of test batteries proves to be a key one, preparing grounds for better integration of Roma into the regular school system and should pave the way for further intervention in this field. The outputs of the programme are being incorporated into the Conception of Integrated Education of Roma Children prepared by the Ministry of Education. The test battery will be made available for each Pedagogic-Psychology Advisory Centre at the end of the project and will be further verified by Phare 2002 as well as by the Research Institute of Child Psychology and Pathopsychology (an organisation governed by the Ministry of Education). Due to the complexity of the test preparation, as well as the necessity to divide the tasks into two parts (school readiness tests and differential diagnosis), the TA-contract has been prolonged till the end February 2004.

The TA to establish of community centres went through the inception phase. The recipient of the assistance (DPC) is reporting problems in communication between the consortia partners and reporting requirements. The VAT issue in co-financing was solved, the plans for community centres refurbishment are agreed upon with the mayors and community centre leaders, future social workers are being selected.

Problems may occur in implementation of the educational part of the project since the assistance teachers should be placed in all institutions that will be equipped and refurbished. The 2004 State Budget reserves funds for assistant teachers. The exact number of the financed positions is not available to the cut-off date. The funds are transferred to schools according to law No 597/2003: the establishers of schools (in agreement with the directors of schools) address their requirements to the regional school offices that summarize the requirements of the region to a demand for the state budget administered by the Ministry of Education. Phare Implementation Unit in the Ministry informed each regional school office, as well as each school involved in the project about the condition of applying for a teacher assistant according to the aforementioned law in force (in addition to the law No 596/2003 about school administration).

Due to uncooperative approach of one school and changes in number of pupils in some others, the Ministry of Education requested the change of the list of schools involved in project implementation (December 2003).

SR0103.02 Infrastructure for Roma Settlements

The experience with the project implementation has shown that the projects under EU assistance shall be adequately designed and fulfil all implementation conditions before receiving assistance (projects focusing on works should include only those settlements where the land ownership is clarified and sufficient administrative capacity in the implementing agency is secured).

It is inevitable that the RDSA submits all the necessary documents to the ECD in July at the latest allowing the launch of tenders in August 2004 (detailed contracting schedule for individual activities provided in Annex 4). In case of two villages (Letanovce and Svinia) the conditions for infrastructure construction were not met (building permits not issued); corrective action proposed in part 4.1.

2002/000.610.03 Further integration of Roma children in the educational field and improved living conditions

Project is in its pre-contracting stage. Sustainability of project part focusing on preparation technical documentation for municipalities through further infrastructure interventions is not ensured to the MR cut-off date. Possibility to utilise Structural Funds in this respects should be considered.

# 4. Proposed corrective actions for decision by SMSC and update of the recommendations of interim evaluation follow-up table

## 4.1 Proposed corrective actions for decision by SMSC*

| Project Code | Proposed Action | Decision (yes/no) | Implementing Body | Deadline | Remarks | Update on previously approved actions |
| --- | --- | --- | --- | --- | --- | --- |
| Date of the SMSC: 9 October 2003 |
| SK0002 | Ensure the sustainability of the project, especially in creating positions for the Roma in counselling services in the newly created institutions. | Y | National Labour Office | By the end of 2003 | - | According to the information provided by the NLO the newly established positions is being incorporating into the appropriate legal documents by the MLSAF (see part 3 Conclusions for more details). |
| SK0002 | Ensure sustainability of the project outcomes, the schools working, assistant teachers employed and curricula used. | Y | Ministry of Education | By the end of 2003 | - | Curricula implemented in schools and made available for the public. Funds for assistant teachers allocated in State Budget (for more details see part 3 Conclusions). |
| SK0002 | In cooperation with the Contractor, ensure the sustainability of the project, especially in further functioning of community centers. | Y | SHRM | By the end of 2003 | - | The municipalities took over the provision of running costs of the community centres and employment of community centre workers. |
| SR0103.01 | Ensure that the test batteries will be further verified and flowingly used in practice. | Y | Ministry of Education | February 2004 | - | The FM 2002 continues in the activities. Moreover, the Research Institute of Child Pedagogy and Patopsychology in co-operation with regional institutions will further verify and use the newly created test batteries. |
| SR0103.02 | Ensure timely administration of the tendering processes in a satisfactory quality. | Y | MCRD/ RDSA | With immediate effect | - | Tendering process is seriously delayed. Extension of contracting and disbursement period by one year was approved. Detailed contracting schedule provided in Annex 4. |
| 2002/000.610.03 | Ensure that the quality of the prepared tender documentation (ToRs and TS) is satisfactory and in line with the outcomes of the previous projects. | Y | Ministry of Education | With immediate effect | - | Already delayed tender documents are under preparation. |
| SK0002 | Office of the Plenipotentiary for Roma Communities should clarify the availability of budget for national strategy implementation (short-term or/ and national strategy). | Y | Office of Plenipotentiary for Roma Communities | With immediate effect | - | The Office Plenipotentiary's budget is not sufficient for national strategy implementation. Line ministries have allocated own resources for Roma issues but the Office does not have an overall view of these resources to the cut-off date. Office of Plenipotentiary's budget covers mainly urgent matters such as emergency cases in Roma communities (floods, fire, landslide). In 2004 almost half of the budget is allocated for consolidation of the Central Office and establishment of the Regional Offices. |
| Date of the SMSC: 19 February 2004 |
| SK0002 | Donation Agreements between the Ministry of Finance and final beneficiaries regarding equipment were still not signed due to unavailable administrative capacity. The CFCU shall accomplish this duty. |  | CFCU | 30.03.2004 |  |  |
| SR0103.02 | In case of two villages (Letanovce and Svinia) the conditions for infrastructure construction were not met (building permits not issued). The project co-ordinators (DPC with RDSA) should consider a reallocation of funds to other Roma settlements already prepared for infrastructure construction. |  | DPC RDSA | With immediate effect |  |  |
| - | Administrations of some implementing authorities lack internal procedures on substitutability. That is also why the debriefing meeting for a CIV IE Report will fail to be organised within the one-month period after the issue of the report as required by the IE Guide. This could cause that some of the recommendations will be no longer relevant. Internal procedures on substitutability should be developed by each implementing authority in order to prevent repetition of such a situation. |  | Implementing authorities (including ECD) | With immediate effect |  |  |
| SR0103.01 SR0103.02 2002/000.610.03 | The ACU is responsible for national co-ordination of Phare programme. Aid Co-ordinators are appointed for individual sectors to follow the projects' implementation. ACU is not invited to monthly meetings. DPC, RDSA and Ministry of Education should invite responsible ACU Aid Co-ordinators to their monthly meetings. |  | DPC RDSDA Ministry of Education | With immediate effect |  |  |
| 2003-004-995-01-05 2003-004-995-01-06 | Problems with timely availability of co-financing were experienced in previous Phare projects. In other to avoid repetition of such a situation the Phare 2003 beneficiaries (Ministry of Education and Health) in co-operation with the NF and CFCU should prepare a co-financing contracting and disbursement time-schedule of these projects. |  | Ministry of Education Ministry of Health NF CFCU | 30.04.2004 (next MR cut-off date) |  |  |
| All | The SMSC is encouraged to consider the inclusion of the Civil Society Sector into the ECOSOC SMSC as an independent sectoral component or as a part of Social Affairs and Human Resources Development sectoral component. This would enable to reduce the number of SMSCs to three comparable in size. |  | SMSC members | 19.02.2004 |  |  |

## * The up-date is provided only to the recommendations relevant to the cut-off date of the report.

## 4.2 Update of the recommendations of the interim evaluation follow-up table*

| Recommendation number | Applied | Responsibility for Follow-up | Deadline | Details of action/ Remarks | Update |
| --- | --- | --- | --- | --- | --- |
| Interim Evaluation Report No. R/SK/JHA/03.044 (10.03.2003) |
| Regional Support Development Agency needs immediately to increase the speed on preparing and contracting the construction works under SR0103.02. Moreover, the Agency should also initiate that progress is done with regard to the complementarity of the State Social Housing Programme and should regularly inform the European Commission Delegation on the progress achieved. In the event that – due to further delays – the original implementation schedule appears to be not realistic anymore, the Aid Co-ordination Unit, together with the European Commission Delegation should consider in time the re-allocation of parts of the SR-0103.02 funds towards other recipient areas. | Y | RDSA ECD ACU | With immediate effect | No need for reallocation was recognised during the relevant SMSC meeting on 25.3.2003. Ms Novotná, SAC, requested the RDSA to indicate the needs for reallocation. She received e-mail that no needs for reallocation are envisaged. ECD is awaiting a letter from Minister of Construction and Regional Development concerning the State Social Housing Programme. | Extension of contracting and disbursement period by one year. Social Housing Programme secured through the 2004 State Budget. Detailed contracting schedule is in Annex 4. |
| Interim Evaluation Report No. R/SK/CIV/03.045 (26.03.2003) |
| Aid Co-ordination Unit together with involved implementing authorities should initiate a participatory process in order to refine Indicators of Achievement and making them applicable for monitoring and evaluation purposes. The next sectoral monitoring report should foresee to apply relevant Indicators, in order to regularly measure any project progress. Proposals for improved indicators, which might be possibly considered by the relevant Parties, are presented in Annex 1. | Y | Recipients ACU ECD | ongoing assignment | Sectoral monitoring report for all projects covered by the Civil Society sector made recommendation to reformulate the indicators in order to make them measurable. CSDF already reformulated some of its indicators in a measurable way. Further activities in this field will be done mainly by Phare assistance recipients supported by relevant ACU and ECD project managers. The assistance of the EMS consortium can be also utilised in this respect. | On 13 November 2003 the EMS delivered training on indicators with particular focus on institution building (IB) projects in CIV sector. The formulation of objectively measurable indicators in IB proofed to be very problematic, particularly in Roma projects where collection of official statistics data according to the nationality is not permitted. The process of reformulation of indicators would require an in-depth insight into each project. That is why the ACU has prepared a technical assistance project on indicators (re)formulation to be financed from Phare 2003 Unallocated Institution Building Facility (recommendation of Steering Committee is needed). |
| Interim Evaluation Report No. R/SK/CIV/03.048 (09.12.2003)** |
| The Office of PP together with the SHRM and the Ministry of Labour, Social Affairs and Family (MLSAF) should clarify the unclear legal status of Roma field workers, should define their future financing and should present this commitment by means of a relevant document to the ECD and ACU. |  | Office of PP SHRM MLSAF | With immediate effect | NA to cut-off date | NA to cut-off date |
| The Office of PP in co-operation with the SK0002 Pre-Accession Adviser (PAA) should submit a committing document to the ECD and the ACU showing where and when the outputs from the SK0002 twinning are going to be included into the Government’s official documents, including the Roma Strategy. |  | Office of PP PAA | With immediate effect | NA to cut-off date | NA to cut-off date |
| National Labour Office (NLO) in co-operation with MLSAF should present a binding position document to the ECD and ACU, regarding the future employment conditions for the trained pool of 32 Roma employment counsellors. |  | NLO MLSAF | With immediate effect | NA to cut-off date | NA to cut-off date |
| The Ministry of Education (ME) should present a document to the ECD and ACU showing the detailed plans for the incorporation of the outcomes of the SR0103.01 Component into the Roma Education Strategy, including a relevant Action Plan for the implementation of the project outcomes and their dissemination. |  | ME | With immediate effect | NA to cut-off date | NA to cut-off date |
| The Ministry of Construction and Regional Development (MCRD) should submit to the ECD and ACU written commitment, showing the intended use of the 2002 part, focusing on the preparation of technical documentation for further Roma infrastructure interventions. If no clear commitment can be demonstrated in terms of how and by when future infrastructure interventions will be undertaken by the Slovak Government, the respective funds should be re-allocated. |  | MCRD | With immediate effect | NA to cut-off date | NA to cut-off date |

# * The up-date is provided only to the recommendations relevant to the cut-off date of the report.

** Debriefing meeting scheduled for 3 February 2004.

# ANNEXES

## Annex 1: Contact List*

| Name and Position | Institution | Address | Phone | Fax | e-mail | Relevant to project(s) |
| --- | --- | --- | --- | --- | --- | --- |
| Mr Dieter Thiel Head of Phare/ISPA Section | ECD | Panská 3 811 01 Bratislava | 02/544 31 718 | 02/544 32 980 | dieter.thiel@cec.eu.int | All |
| Mr Ivan Fecenko Phare ACU Director | ACU Office of the Government of the SR | Námestie slobody 1 813 70 Bratislava 1 | 02/572 95 516 | 02/544 30 056 | ivan.fecenko@vlada.gov.sk | All |
| Ms Ľubica Slimáková NF Director | NF Ministry of Finance of the SR | Štefanovičová 5 817 82 Bratislava 15 | 02/595 83 310 | 02/595 82 594 | lslimakova@mfsr.sk | All |
| Mr Dietmar Aigner | EMS Bratislava Office | Hviezdoslavovo nám. 14 811 02 Bratislava | 02/544 19 286 | 02/544 19 285 | dietmar_aigner@ems-phare.net | All |
| Ms Viera Gažíková EMS evaluator | EMS | Námestie slobody 1 813 70 Bratislava 1 | 02/572 95 516 | 02/544 30 056 | viera_gazikova@ems-phare.net | All |
| Mr Pavol Demeš PAO | CSDF | Ružová dolina 6 821 06 Bratislava | 02/502 21 552 | 02/502 21 553 | pdemes@gmfus.org | SK0013 |
| Ms Katarína Vajdová CSDF Director (SAC) | CSDF | Ružová dolina 6 821 06 Bratislava | 02/502 21 552 | 02/502 21 553 | vajdova@changenet.sk | SK0013 |
| Ms Ivana Škodová ECD task manager | ECD | Panská 3 811 01 Bratislava | 02/544 31 718 | 02/544 32 980 | ivana.skodova@cec.eu.int | All |
| Ms Judit Young CSDF project manager | CSDF | Ružová dolina 6 821 08 Bratislava | 02/502 21 556 | 02/502 21 553 | young@changenet.sk | SK0013 |
| Ms Kinga Novotná SAC | Department of Project Co-ordination Office of the Government of the SR | Námestie slobody 1 813 70 Bratislava 1 | 02/572 95 273 | 02/572 95 424 | kinga.novotna@vlada.gov.sk | SK0002; SR0103.01; SR0103.02; 2002/000.610.03 |
| Ms Silvia Czuczorová PAO | CFCU Ministry of Finance of the SR | Štefanovičova 5 817 82 Bratislava | 02/5958 2537 | 02/5958 2559 | cfcu.sczuczorova@mfsr.sk | SK0002; SR0103.01; 2002/000.610.03; 2003-004-995-01-05 and 06 |
| Ms Júlia Štepánková SPO | Ministry of Education of the SR Department of European Integration | Hanulova 5/b 813 30 Bratislava | 02/692 02 251 | 02/692 02 259 | stepan@education.gov.sk | SK0002; SR0103.01 2003-004-995-01-05 |
| Mr Vladimír Belovič SAC | Ministry of Education of the SR Department of European Integration | Hanulova 5/b 813 30 Bratislava | 02/692 02 216 | 02/692 02 219 | belovic@education.gov.sk | 2003-004-995-01-05 |
| Ms Denisa Kútyová Aid Coordinator | ACU Office of the Government of the SR | Štefánikova 2 813 70 Bratislava | 02/572 95 520 | 02/544 30 056 | denisa.kutyova@vlada.gov.sk | All but SK0013 |
| Mr Martin Orth Aid Coordinator - Monitoring | ACU Office of the Government of the SR | Štefánikova 2 813 70 Bratislava | 02/572 95 533 | 02/544 30 056 | martin.orth@vlada.gov.sk | All |
| Mr Igor Urbančík DPC project manager | Department of Project Co-ordination Office of the Government of the SR | Námestie slobody 1 813 70 Bratislava 1 | 02/572 95 183 | 02/572 95 424 | igor.urbancik@vlada.gov.sk | SR0103.01; co-financing of SR0002 and SR0102.02 |
| Mr Vojtech Kišš DPC project manager | Department of Project Co-ordination Office of the Government of the SR | Námestie slobody 1 813 70 Bratislava 1 | 02/572 95 311 | 02/572 95 424 | vojtech.kiss@vlada.gov.sk | SR0103.01 (supply of equipment); 2002/000.610.03 |
| Mr. Marek Hojsík DPC project manager | Department of Project Co-ordination Office of the Government of the SR | Námestie slobody 1 813 70 Bratislava 1 | 02/572 95 208 | 02/572 95 424 | marek.hojsik@vlada.gov.sk | SK0002 |
| Ms Lucia Hencelová DPC project manager | Department of Project Co-ordination Office of the Government of the SR | Námestie slobody 1 813 70 Bratislava 1 | 02/572 95 208 | 02/572 95 424 | lucia.hencelova@vlada.gov.sk | 2002/000.610.03 |
| Ms Sofia Daskalová Adviser | Office of the Government of the SR Office of Plenipotentiary for Roma Communities | Lamačská cesta 8 813 70 Bratislava | 02/572 95 747 | 02/572 95 816 | sofia.daskalova@vlada.gov.sk | SK0002 |
| Ms Valéria Kubalová Director | National Labour Office | Župné námestie 5-6 812 67 Bratislava | 02/592 00 740 | 02/592 00 747 | valeria.kubalova@nup.sk | SK0002 |
| Ms Darina Laciková Project Co-ordinator | National Labour Office | Župné námestie 5-6 812 67 Bratislava | 02/592 00 742 | 02/592 00 747 | darina.lacikova@nup.sk | SK0002 |
| Ms Martina Galabová CFCU programme officer | CFCU | Štefanovičova 5 817 82 Bratislava | 02/5958 2537 | 02/5958 2559 | cfcu.mgalabova@mfsr.sk | SK0002; SR0103.01; 2002/000.610.03; 2003-004-995-01-05 and 06 |
| Mr Július Slovák PAO, SAC and Director General | Ministry of Construction and Regional Development of the SR RDSA | Špitálska 8 816 44 Bratislava | 02/597 53 414 | 02/597 53 428 | slovak@build.gov.sk | SR0103.02; 2002/000.610.03 |
| Ms Alena Šoltysová Director | Ministry of Construction and Regional Development of the SR RDSA, Implementation Department | Špitálska 8 816 44 Bratislava | 02/597 53 420 | 02/529 32 845 | soltysova@build.gov.sk | SR0103.02; 2002/000.610.03 |
| Ms Anna Polnišerová Project Co-ordinator | Ministry of Construction and Regional Development of the SR RDSA, Implementation Department | Špitálska 8 816 44 Bratislava | 02/597 53 415 | 02/597 53 428 | polniserova@build.gov.sk | SR0103.02 |
| Mr Juraj Krecháč RDSA project manager | Ministry of Construction and Regional Development of the SR RDSA, Implementation Department | Špitálska 8 816 44 Bratislava | 02/597 53 415 | 02/597 53 428 | krechac@build.gov.sk | SR0103.02 |
| Ms Zuzana Škublová SAC | Ministry of Health | Limbova 2 Bratislava | 02/593 73 268 | 02/547 77 465 | zuzana.skublova@health.gov.sk | 2003-004-995-01-06 |
| Mr Peter Tatár Project manager | Ministry of Health | Limbova 2 Bratislava | - | 02/547 77 465 | tatar@okstrana.sk | 2003-004-995-01-06 |

* Contractors are not included.

## Annex 2: Sources of Information

| Document title and/ or number | Author | Date of Issue | Location | Relevant to project(s) |
| --- | --- | --- | --- | --- |
| Financing Memorandum 2000 - ACCESS | - | 21.12.2000 | ACU, ECD, Phare Recipients | SK0013 |
| Financing Memorandum 2000 Slovakia NP | - | 21.12.2000 |  | SK0002 |
| Financing Memorandum 2001 Slovakia NP | - | 17.01.2002 |  | SR0103.01 SR0103.02 |
| Financing Memorandum 2002 Slovakia NP | - | 10.01.2003 |  | 2002/000.610.03 |
| Financing Memorandum 2003 Slovakia NP | - | 03.11.2003 |  | 2003-004-995-01-05 2003-004-995-01-06 |
| Project Fiches | Phare Recipients | NA | ACU, ECD, Phare Recipients | SR0103.01 SR0103.02 2002/000.610.03 2003-004-995-01-05 2003-004-995-01-06 |
| Sectoral Monitoring Report M/SR/CIV/03005 SMSC meeting minutes | ACU | 29.09.2003 | ACU, ECD, Phare Recipients | SK0013 SR0103.01 SR0103.02 2002/000.610.03 |
| Project Monitoring Reports | Phare Recipients | January 2004 | Phare Recipients, ACU | All |
| Contractor’s Reports | Contractors | NA | Phare Recipients | SK0013 SR0103.01 SR0103.02 2002/000.610.03 |
| Perseus Financial Status | CFCU, RDSA, NF | 31.12.2003 | ACU | All |
| IE Report No. R/SK/CIV/03.048 | EMS | 09.12.2003 | ACU. ECD, Phare Recipients | SK0013 SR0103.01 SR0103.02 |
| IE Report No. R/SK/JHA/03.044 + follow-up table | EMS | 10.03.2003 |  |  |
| IE Report No. R/SK/CIV/03.045 + follow-up table | EMS | 26.03.2003 |  |  |
| CSDF keeps separate file on every individual grant/ project. The list of documents contained in the file is structured as follows: bank statements, cash flow diary, application/ confirmation for the VAT recovery from the Tax Office, copies of documents confirming 10 contribution, copies of documents for the grant expenses, final budget evaluation, final report, monitoring minutes of the Programme Manager, miscellaneous (e.g. letters about the change of statutory representative, amendments, changes in deadlines approved by ECD, publications etc). The documentation is archived at the CSDF five years after the files were audited. | SK0013 |

## Annex 3: Agenda

| Project code | Last monthly meeting Date/ place | Next monthly meeting Date/ place | Last Steering Committee meeting Date/place | Next Steering Committee meeting Date/ place |
| --- | --- | --- | --- | --- |
| SK0013 | 24.11.2003/ CSDF | - | 10.09.2001/ CSDF | - |
| SK0002 | 03.12.2003 | - | 03.12.2003 | - |
| SR0103.01 | 16.12.2003 | - | - | January 2004 |
| SR0103.02 | 20.11.2003 | - | - | January 2004 |
| SR2002/000.610.03 | - | - | - | January 2004 |
| 2003-004-995-01-05 | - | NA to the cut-off date. | - | - |
| 2003-004-995-01-06 | - | January 2004/ Ministry of Health | - | I. Q 2004/ Ministry of Health |